## Slide 1
William Pellico
Fermilab Workshop on Megawatt Rings & IOTA/FAST Collaboration Meeting
7 May 2018
PIP – Proton Improvement Program

## Slide 2: Outline
PIP Start
  What was the reason PIP was begun
  The initial steps
  The goals or pillars of PIP
Framework
  Operational “Project” like campaign
  PIP Tasks
    Related issues
    Strategic goal of task
Overall view of completion of PIP
  Success in meeting objective
  Moving forward
Conclusion
Pic of Linac, Booster & MI-8 Line

## Slide 3: Why?
In 2010 the Proton Source (PS) was not part of the future plan.
  Tevatron was still going but the next phase of FNAL took center stage
    We would be moving from Energy to Intensity but also staging for the next energy frontier option
  Project ‘X’ (ILC based SRF) was being planned as the solution
  Other Technologies – Wakefield, ILC (SRF), NML, Muon facility were all being pushed.
However, the planned projects and those already approved were going to need a PS until the large replacement accelerators upgrades were completed.
  NOvA was due to come on line in 2013 (700 KW)
  MicroBooNE (CD-1) was to start taking beam in 2015
  Talk/Plans about G-2 and Mu2e as our rare process program

## Slide 4: Initial Steps – Get PIP going
Convince management it was a good and necessary use of $$
  Workshop to discuss Proton Source
  Talks were given on Linac, Pre_Acc and Booster accelerators
  Accelerator Advisory Committee – very supportive
Proton Source Workshop 2010
Proton Source Task Force Report 2010
Proton Improvement Plan (PIP) Outline Document 2011
PIP Handbook and PIP Baselined with Labor and Budget Profile 2012

## Slide 5: 2011 Goals for the Proton Improvement Plan
The Proton Improvement Plan should enable Linac/Booster operation capable of
  Delivering 2.25E17 protons/hour (at 15 Hz) in 2016
while
  Maintaining Linac/Booster availability > 85%, and
  Maintaining residual activation at acceptable levels
and also ensuring a useful operating life of the proton source through 2025.
The scope of the Proton Improvement Plan includes
  Upgrading/Replacing components to increase the Booster repetition rate
  Replacing components that have (or will have) poor reliability
  Replacing components that are (or will soon become) obsolete
  Studying beam dynamics to diagnose performance limitations
  Implementing operational changes to reduce beam loss
Several important activities were well underway (started under ops)

## Slide 6: PIP Development
Approval from DOE and Laboratory with signoff on PIP 2011
PIP was not a DOE Project – but a ‘campaign’ that used project like tools for control
A baseline RLS with WBS was created in 2012 with 30 tasks
  Change and Control document approved (Project Structure)
  PIP was to be carved out of operations and embedded in AD
    Cost initially did not include labor
  2.25E17 pph
  15 Hz
  Viability/Reliability of >85% through 2025
This Photo by Unknown Author is licensed under CC BY-NC-SA

## Slide 7: Pillar of PIP: 15 Hz Operations
Booster was designed as a 15 Hz rapid cycling synchrotron, RCS, however beam operations were never planned to run at that rate.
  RF systems were limited to about 7.5 Hz
    Cavity breakdown, due to heating and sparking
    Cavity drive systems limits
    RF system anode supplies limited to ~12 Hz
  Kicker systems could not run above 9 Hz
  Data acquisition never run above 7.5 Hz
  Other pulsed systems had been updated to 15 Hz under Proton Plan upgrade – needed for Booster Neutrino Beam program.

## Slide 8: Pillar of PIP: 2.25 E17 pph
2.25 E17 pph
  Needed to be accomplished without increasing the 2012 loss/activation level.
    Level was about 1 watt per meter
    The maximum flux at that time was about 1.1e17 pph
    Shielding assessment limit of 1.8E17 pph
      Not all loss points were adequately covered by safety rad detectors
    Could not achieve this by increasing protons per pulse alone
    Needed to increase the Booster efficiency by several percent
    Needed better control of losses – loss points
    Needed to develop a beam loss protection system with Rad Safety

## Slide 9: Pillar of PIP: Viability till 2025 and Reliability >85%
The Pre-Acc (Cockcroft Walton Design), Linac and Booster were started in late 1960s. Much of the hardware was and in some cases original.
  Replace systems with obsolete hardware
    This included hardware components that would not likely be available going forward
  Replace systems difficult to maintain
    Systems requiring significant upkeep labor
    Systems with specialized hardware that required unique tooling and skillset not found elsewhere
  Replace systems that had a significant contribution to downtime

## Slide 10: PIP: Task Structure Nov 2011 – Addressed the PIP Goals
Proton Improvement Plan Bill Pellico Bob Zwaska, Deputy Elmie Peoples-Evans, Project Controls Mary Convery, Installation Coordinator Valeri Lebedev, Free Agent
Booster Keith Gollwitzer
Linac Fernanda G. Garcia
RFQ Injector C. Y. Tan
200 MHz Accelerating System Fernanda G. Garcia
HLRF ???
Linac Modulator Trevor Butler
7835 Procurement Fernanda G. Garcia
Instrumentation Craig Drennan
Utilities Patrick Karns
Power Distribution Steve Hayes
Booster RF John Reid
Anode PS Rene Padilla
Bias Supplies Pat Sheahan
New Tuners Matt Slabaugh Ralph Pasquinelli
New Cavities Valeri Lebedev
Cavity Test Stand Pat Sheahan John Reid
Cavity 20 Matt Slabaugh John Reid
Accelerator Physics Bob Zwaska
Booster Cogging Kiyomi Seiya
Booster Instabilities & Feedback Bob Zwaska
Injection Painting Valeri Lebedev
Radiation Shielding Peter Kasper
Alignment & Aperture Kiyomi Seiya
Booster Notcher Bruce Hanna
Power Distribution Steve Hayes
95LCW System Maurice Ball
Vacuum Systems Dave Augustine
Solid State Upgrade John Reid
Modulators Rene Padilla
Driver Amplifiers Tom Kubicki
Cavity & Tuner Refurb. Matt Slabaugh Mary Convery
Controls Upgrade Mike Kucera
Cooling System David Hixson
400 MeV Optics Matching & Collimation Valeri Lebedev
Linac Notch Creation Dave Johnson
Linac Lattice , Orbits and Collimation Hyung Jin Kim
Accelerator Physics Valeri Lebedev
Vacuum Systems Dave Augustine
Power Amplifiers Steve Kotz
Installation Rene Padilla Steve Kotz
Instrumentation Craig Drennan
Dampers Nathan Eddy
Controls Craig Drennan
Utilities Todd Sullivan
Booster Collimation Valeri Lebedev
BPM Upgrade Nathan Eddy
Task structure developed as PIP looked to meet HEP needs and AD resources. Some tasks were dropped others added: 30 to 33

## Slide 11: PIP: HEP needs Nov 2011
g-2
Mu2e
8 GeV 
120 GeV 
NOvA Shutdown
LBNE
Start of PIP – Did not leave much time

## Slide 12: PIP: Funding and Labor Profile Constraints - RLS
Due to budget and labor constraints as well as needing time to engineer solutions, the RLS developed and prioritized:
  Get to 15 Hz which would allow beam to all users at a reduced rate.
  Reduce/control losses to allow an increase in flux
  Complete PIP by removing obsolete and unreliable hardware
  Usually these tasks shared benefits – to increase the rep rate often required removing obsolete/unreliable hardware.

## Slide 13: PIP: 15 Hz
Identify all systems not capable of 15 Hz
  Booster RF System
    Anodes: Replace original anodes with modern dry transformer sys
    Cavities: Refurbish all cavities - replacing/repairing/adding cooling
    Drive Systems (Bias Supplies) – Developed a SS drive and updated Bias supply to handle power
    Power distribution to tuners (Bus Bar) – improved bus connections
  Controls/Data acquisitions
    15 Hz clock with no gaps – many systems used null in processing
    Beam diagnostics – collecting BPM data at 15 Hz
  Booster Kickers
    Inadequate cooling of loads
    Inadequate cooling of thyratron

## Slide 14
15 Hz Capable
17 cavities done

## Slide 15: PIP: Beam Loss Reduction & Increase Flux 2.25E17 pph
Linac Laser Notching: create a notch at 750 KeV injection required for Booster extraction kickers
Beam Physics
  Capture: Optimize multiturn injection & Lattice corrections
  Acceleration: Aperture improvements – alignment of magnets
  Transition: Modifying Booster low level to provide improved jump
  Extraction: Stabilize lock to MI and Improved Cogging (magnetic)
Booster 2nd Harmonic Cavity (wide band perpendicular biased)
Booster Digital Dampers – both longitudinal and transverse
Booster Notching System: Shorter/Faster kickers and new beam dump absorber
New Shielding assessment – Development of new TLM system

## Slide 16: PIP: Highlights – Plots of Beam Charge and Calc Energy Loss
If you have to double the flux and keep beam loss energy the same:
Reduce Booster cycle loss by 50%
Control the loss point in critical areas
Joules loss cut in half
2011
2018

## Slide 17
Loss Limit reaching PIP goal of 2.4E17 pph – running above 2.1E17 pph
Flux Ramp UP
Continues
Chart: Hourly flux [protons / hour]

## Slide 18
Cavity Refurbishment
NOvA Shutdown
15 Hz Capable
New Shielding Plan
Flux Milestone
PIP: History of PS Flux ramp-up from~1E17 pph to over 2.4E17 pph
Beam Flux

## Slide 19: PIP: Obsolescence/Reliability - > 85%
Pre-Acc
  Replaced Cockcroft-Walton with modern RFQ system
Linac
  Replaced Linac 7651 tube in driver sys with SS
  Replacing 7835 Modulator with Marx modulator
  Upgraded Linac vacuum system and controls
  Commissioned worlds first 200 MHz klystron – Proof of Principle
Booster
  RF Systems (nearly every part of drive system)
  Added additional cavities – hot spares provide 20% overhead
  Upgraded Low Level System
  BPM system – converting over to modern digital system
  Vacuum pumps, LCW cooling and Power distribution systems
  New Booster Cavities – higher voltage and wider apertures

## Slide 20: PIP: Viability and Reliability >85%
Chart: Booster Maintenance Overtime Hours
| 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017
Mintenance Overtime Hours | 188.75 | 122.25 | 160.25 | 100.25 | 152.5 | 73.75 | 51.75 | 8.5
Chart: Proton Source Department Count
| 1993 | 1998 | 2003 | 2008 | 2013 | 2018
Head Count | 34 | 28 | 31 | 27 | 26 | 26
Chart: Linac RF System Downtime
| 2000 | 2001 | 2002 | 2003 | 2004 | 2005 | 2006 | 2007 | 2008 | 2009 | 2010 | 2011 | 2012 | 2013 | 2014 | 2015 | 2016 | 2017 | 2018
LE | 49.0133 | 71.1567 | 109.5467 | 125.36 | 90.8633 | 78.4833 | 96.5067 | 189.04 | 217.1133 | 158.2633 | 182.8767 | 207.9567 | 54.54 | 67.1167 | 150.6833 | 98.6 | 96 | 123.6333 | 46.5667
HE | 30.4467 | 64.0167 | 69.5767 | 181.2033 | 32.3867 | 58.3467 | 56.2033 | 107.4 | 139.89 | 45.8467 | 37.2367 | 33.4367 | 42.3667 | 13.0167 | 39.3 | 85.4 | 396 | 287.65 | 61.5667
Shutdown
Shutdown
PS is running at about 92% uptime
Not all systems upgraded
Infant mortality on some new systems
Shutdown
Shutdown

## Slide 21: PIP: Injector Line Viability and Reliability >85%
Not as ‘cool’ looking
But great uptime!

## Slide 22: PIP: Viability and Reliability >85%
54 cell Linac Marx Modulator
2 more Booster RF stations
Station 21
Station 22
DTL roughing stations
New Power Station
Upgraded LCW System
Hardware
Reliability
Examples

## Slide 23
Proton Improvement Plan Bill Pellico, Project Manager Fernanda G. Garcia, Deputy Project Manager Kenneth Domann, Project Controls C.Y. Tan, Senior Scientist
Booster Salah Chaurize
200 MHz RF Power System Fernanda G. Garcia
High-Level RF Fernanda G. Garcia
Linac Modulator
Fernanda G. Garcia
7835 Procurement Fernanda G. Garcia
Instrumentation Craig Drennan
Utilities
Matthew Gardner
Power Distribution Ryan Crawford
RF John Reid
Anode Supply Ryan Crawford
Bias Supply Pat Sheahan
New Tuners Matt Slabaugh
Replacement Cavities
Tom Kroc
Cavity 1013 Matt Slabaugh John Reid
Accelerator Physics CY Tan
Booster Collimation Valery Kapin
Radiation Shielding Keith Gollwitzer
Alignment & Aperture Kiyomi Seiya
Booster Notcher Salah Chaurize
Low-Conductivity Water System David Hixson
Power Distribution Ryan Crawford
Vacuum System Dave Augustine
Solid State Upgrade John Reid
Power Amplifier Steve Kotz
Driver Module Tom Kubicki
Cavity Test Stand Pat Sheahan
Linac Notch Creation Dave Johnson
Simulations & Studies Valery Kapin
Accelerator Physics Valeri Lebedev
Vacuum System Dave Augustine
Modulator Rene Padilla
Installation Rene Padilla Steve Kotz
Instrumentation Craig Drennan
Dampers Nathan Eddy
Utilities Todd Sullivan
Booster Cogging Kiyomi Seiya
Beam Position Monitors Nathan Eddy
Simulation & Studies
CY Tan
Linac Fernanda G. Garcia
Cavity & Tuner Refurb. Matt Slabaugh
RFQ Injector C. Y. Tan
Beam Position Monitors Peter Prieto
Low-Cond. Water System
Matt Gardner
Perpendicular Cavity CY Tan
Cavities 21&22
Matt Slabaugh
Stations 21&22
Rene Padilla
Utility Pumps
Todd Sullivan
PIP: The End is Near
Over the past several years adjustments have been made to accommodate changes in planning: PIP II and PIP +
PIP 33 tasks went to 36
200 MHz Klystrons removed
Booster Cavity moved to PIP+
All remaining task are on schedule to finish this summer shutdown.

## Slide 24: Summary
After 7 official and 2 planning years – PIP is ending a very successful upgrade to the Proton Source. The benefits have been significant and have made possible the lab’s promise to deliver the protons needed for our HEP program.
Completing the project under budget.
Developing new technologies for the community.
Training engineers, scientist and post docs along the way