## Slide 1
Mike Tartaglia
All Experimenters and Laboratory Status Meeting
February 19, 2018
TD Operations Status

## Slide 2: Magnet Sector
Accelerator Support
  MLAW spare magnet: winding both coils complete, preparing first coil for epoxy impregnation.
  MSD Technicians responding to Switchyard magnet water leaks.
LARP/HL-LHC AUP
  Cold Mass Development: Welding SS shell on a short model is complete. Prep for test early March.
  Long coil fabrication in progress: QXFA107 impregnation complete, preparing coil 108 for reaction, coil 109 inner layer wound, preparing for insulation curing next.
  ORC walk through completed of backup coil winder and tensioner, all recommendations implemented
  LCLS II
    Test and qualification of the quadrupoles continues: SPQA126 and 127 arrived, inspected.
    Prepared to begin SPQA126 test today.
  Mu2e –
  TS prototype in IB2 for SSW measurement system commissioning.
  First production module splice procedure not followed by vendor; Mu2e physicists visiting to inspect.
  Good progress on dished heads (top plates) A and B in HAB – prep for D.H. B vacuum leak check
  PS/DS coil insertion in the shell is delayed. Not much progress last week.
  Solenoid Instrumentation, Monitoring and Controls CRR: go-ahead to proceed with construction
  G-2
    – Inner coil winding of the inflector completed, winding on outer form has been authorized
  IB1 Infrastructure
    – VMTF/VTS switchboard upgrade: installation completed, SRF testing resumed

## Slide 3: Cryogenic Sector
Cryogenic Test Facilities
  Meson Detector Building
    No testing last week
  Cryomodule Test Facility
    LCLS-II F1.3-07 removed, F1.3-09 expected at CMTF this week; bypass valve re-routing to avoid T-A oscillations
  Industrial Building 1
    Stand 3: LCLS-II magnet testing
    VTS and Plant maintenance during switchboard power outage; resumed VTS operations
  Other facilities:
    Supporting g-2 operation at Muon campus, purifier back on line.
    System at 300 K waiting for IOTA completion and maintenance at FAST
    System at 300 K awaiting Dished Head B commissioning at Heavy Assembly building (HAB)
Engineering
  Procurements
    LCLS-II: Fabrication of distribution boxes in progress, delivery in July. Delivery of transfer lines expected in May.
    Mu2e: Fabrication of distribution box in progress, expect delivery in May. Feedbox RFP issued, bids due 2/20.
    PIP-II Cave Transfer Line procurement, delivery expected in May
  HL-LHC AUP
    L4 WBS created for cryo-mechanical upgrades of the horizontal test stand at Magnet Test Facility (EVMS in March)
  Sub-Kelvin Cryogenics
    SuperCDMS Snolab – CD2/3 review Jan. 24-26, awaiting formal response
    Nexus - on track for regrigerator delivery soon, NuMI hall preparations proceeding
    ADMX (5K systems) – providing technical assistance on plant and recovery system

## Slide 4: SRF Sector
R&D (same report as last week)
  High Q, High Gradient: Nitrogen infusion studies continue
  Nb3Sn coating and Plasma processing continue
  Nb/Cu equipment relocated to new location, installation is in progress.
  Third quantum computing cavity EP is in progress. RF prep for other quantum computing cavity is in progress.
LCLS-II: CM06 BPM leaking problem. LCLS-II cryomodules are all waiting for BPM solution
  BPM study in progress –new hardware tested & successful, will repeat tests and propose a final plan tomorrow.
  1.3 GHz cavities
    CAV0161 qualified, CAV0158, 162 need re-processing
  3.9 GHz cavities
    3HRI02 dressed, waiting for test prep. 3HRI03 to be removed from HTS, remove magnetic shield, re-install next week to test.
  CM03 repair: dis-assembly completed. Rebuild in progress (fill in job between cryomodules).
  CM04 pending final modification (cryo-valve gas guard, CAV1 support) before shipping to SLAC.
  CM05 coupler #4 leak repair is postponed. We may need to roll back to WS4 to fix BPM, and then re-install warm end couplers
  CM06 developed leak due to BPM.
  CM07 test was completed at CMTF. Q0 is now 2.7e10. Cryomodule fully met the spec. But it needs to rolled out of vacuum vessel to fix BPM.
  CM08 Helium circuit leak check was completed. Plan to implement BPM fix this week
  CM09 plan to ship on 2/19 to CMTF for test.
  CM10 is in WS3. BPM fix is in progress before thermal shield weldment.
  CM11 at WS1 is waiting for BPM solution.
PIP-II
  Spoke Cavity S112 developed vacuum leak; Spoke Cavity S107 will assembly coupler and install at STC on 2/23