## Slide 1
Vyacheslav Yakovlev
All Experimenters and Laboratory Status Meeting
March 5, 2018
TD Operations Status

## Slide 2: SRF Sector Update 2018-02-26
R&D
  Quantum computing measurement continues.
  High Q0 high gradient: Nitrogen infusion program continues.
  Nb3Sn continues cavity preparation and coating. One cavity had a very nice coating appearance. It is being prepared to be tested.
  Plasma processing continues.
  Nb/Cu vacuum chamber installation is in progress.
LCLS-II : With BPM studies showing good results, LCLS-II cryomodules assembly has started briefly, only stopped again by
the Project Director. A Quality Assurance Audit is mandated in the week of 3/5.
  For as built cryomodules, we plan to in-situ replace Grade2 Titanium bolt with grade 5 titanium stud. A BPM is being prepared to test this procedure to improve statistics.
  CM03 repair: dis-assembly was completed. Rebuilt started and will be a long process since it is a filler job between cryomodules.
  CM02, CM04 pending final modification (cryo-valve gas guard, CAV1 support and BPM) before shipping to SLAC.
  CM05 warm end couplers were dis-assembled. Beamline was back filled to Nitrogen at 796 torr. It is ready for cold mass extraction from vacuum vessel.
  CM06 is still at SLAC due to BPM leak. A dummy cryomodule will be shipped to get vibration data before CM06 comes back.
  CM07 is still at CMTF. It needs to be moved to ICB to fix BPM. Pending shipping instrument (Demagnetized geophone)
  CM08 Helium circuit leak check was completed. BPM fix is planned pending SLAC approval.
  CM09 is ahead of CM08 at CMTF test cave. Installation completed. Cool down has started.
  CM10 is in WS3. BPM fix is on hold before thermal shield weldment.
  CM11 WS1 resumed as BPM solution is finalized. Yet it was stopped due to stop work order from the Project Director.
  CM12 WS0 completed.
PIP-II
  Spoke Cavity S110 is now assembled with a unity coupler and is being installed at STC.
  Spoke Cavity S112 is being processed for qualification test.

## Slide 3: Magnet Sector
HL- LHC, AUP
Coil fabrication in progress. Coil QXFA107 is in final cleaning process after impregnation.
Coils QXFA107-109 are in different production stage.
Short model MQXFS1d shell is in IB1 for test preparation.
  LCLS II
  Test and qualification of the quadrupoles continues,
  SPQA125-126 has returned from cold testing and is being processed for stretched-wire and survey.
  SPQA127 is cold tested.
  Mu2e
  First Transport Solenoid production module fabrication is completed. It has been crated and waiting for shipment paperwork and customs clearance. Unit will be air shipped to the U.S.
  Work continues on the second test “dish-head” at HAB. The second dish-head will be commissioned with leads shorted together with a superconducting cable ~ mid March.
  Potting of the faux Detector solenoid (DS2) coil (for the long insertion test) was successfully completed at General Atomic in Tupelo.
  Accelerator Support
  Disassembly of IQB310 and IQB169 for MI is complete.
  Parts for the Booster biased cavity solenoid are available.
  Stacking and bonding the rectangular lamination blocks is complete.
  Preparing to measure sextupole MSD184, and MI quadrupole 7346
G-2
Winding of the inner coil of for the new g-2 inflector is complete.
Outer coil parts are being modified in the machine shop.
MDP 15-17 T dipole R&D
  Coil fabrication for 15 T dipole continues. Outer coil HFD-CL-004 is in preparation for impregnation
  Winding and curing of layer 1 in HFD_CL1_004 coil is complete, preparation to L2 winding has started.

## Slide 4: Cryogenic Sector – Engineering Department
  LCLS-II Procurements
    Distribution Boxes – Fabrication in progress, delivery expected in July
    Surface Transfer Line Procurement – Fabrication in progress, delivery expected in May
    Providing SLAC with guidance on installation activities for tunnel components, tunnel components are being installed with a 3rd party contractor
  Mu2e Procurement
    Distribution Box – Fabrication in progress, delivery expected in early May
    Feed Boxes – Currently evaluating technical proposals (5 bids were received)
  HL-LHC AUP
    L4 manager created to manage all cryo-mechanical tasks, working with project to determine details and scope
    Generating resource loaded schedule (project to begin practice EVMS reporting in April)
  Meson Controls Upgrade
    Project is underway – control cabinet construction, networking and initial programming, preparing for system shutdown in June for to switch system over to new control system
  PIP-II Activities and Procurement
    External Cave Transfer Line fabrication in progress (in-house), completion expected in March
    PIP-II Cave Transfer Line procurement, delivery expected in May/June
    Installation to begin in March with external cave TL segments and supports followed by cave TL
  Sub-Kelvin Cryogenics
    SuperCDMS Snolab – CD2/3 review held in January. Awaiting formal sign-off and ESAAB
    ADMX (5K systems) – providing technical assistance on plant and recovery system through May
    Nexus – Refrigerator delivery later in April, NuMI hall preparations proceeding well
    Quantum Lab – Final ORC cryogenic approval given
    Facilities:
Fermilab Accelerator Science and Technology (FAST): System at 300K for IOTA completion and maintenance
Meson Detector Building: System at 4 K, No testing last week, Spoke cavity testing this week
Cryomodule Test Facility: LCLS-II F1.3-09 CM delivered February 21, installed, cool down this week
Industrial Building 1: Stand 3: One LCLS-II magnet test;
VTS stands: Four R&D and six LCLS-II cavities tested
Muon Campus: Supporting g-2 operation, replaced G2 dry expander
Heavy Assembly Building: Plant cool down expected next week for testing of the second cryostat head