## Slide 1
Jay Theilacker
All Experimenters and Laboratory Status Meeting
March 12, 2018
TD Operations Status

## Slide 2: SRF Sector Update 2018-02-26
R&D
  Quantum computing measurement continues.
  High Q0 high gradient: Nitrogen infusion program continues. Furnace troubleshooting/improvement is in progress
  Nb3Sn continues cavity preparation and coating. One cavity had a very nice coating appearance. It is being prepared to be tested.
  High field Q slope: HF rinsing study is in progress
  Plasma processing continues.
  Nb/Cu vacuum chamber installation is in progress.
LCLS-II : With BPM studies showing good results, LCLS-II cryomodules assembly has started briefly, only stopped again by
the Project Director. A Quality Assurance Audit is in progress. BPM studies continues.
  CM03 repair: dis-assembly was completed. Rebuilt started and will be a long process since it is a filler job between cryomodules.
  CM02, CM04 and CM05 beam line were back filled and warm end coupler were dis-assembled. They are ready for extraction and repair BPM. Actual repair is pending for approval.
  CM06 is still at SLAC due to BPM leak. A dummy cryomodule will be shipped to get vibration data before CM06 comes back.
  CM07 is still at CMTF. It needs to be moved to ICB to fix BPM. Pending shipping instrument (Demagnetized geophone)
  CM08 Helium circuit leak check was completed. BPM fix is planned pending SLAC approval.
  CM09 is at CMTF test cave. Cool down complete. All cavities reached 21 MV/m. Three cavities showed field emission. Two cavities had field emission during vertical test. String assembly is acceptable considering one cavity had field emission degradation. All cavities can run nominal gradient despite field emission.
  CM10 is in WS3. BPM fix is on hold before thermal shield weldment.
  CM11 WS1 resumed as BPM solution is finalized. A request for resume work is being sought.
  CM12 WS0 completed.
  CM13 cavities were identified
PIP-II
  Spoke Cavity S111 passed qualification test. Coupler installation is planned for 3/13.
  Spoke Cavity S112 was assembled and is being installed in STC for qualification test.

## Slide 3: Magnet Sector
HL- LHC, AUP – Coil fabrication for LHC inner triplet quadrupoles continues. Coils QXFA107 is measured by CMM. Practice welding of a stainless steel shell on short model MQXFS1d is complete. Leak test of the shell was successful. Magnet in the test facility in preparation to the cold test.
  LCLS II – test and qualification of the quadrupoles continues, SPQA126-127 has returned from cold testing and is being processed for stretched-wire and survey. SPQA128-129 and SPQA127 delivery is expected on March 14th
  Mu2e – First Transport Solenoid production module fabrication is complete. It has been crated and arrived in Chicago this weekend. Progress is being made on finalizing the shipment paperwork and customs clearing.
    Dished Head B in HAB – passed leak check, wrapping MLI over He pipes. Dished Head A – will be ready for TSUN1 test in April
    The vacuum impregnation of the Detector Solenoid model coil at General Atomic was successfully completed. Plan is to insert the model coil onto the shell next week.
    Detailed drafting of the 3-meter AC dipole magnet for mu2e is developing well with the guidance of AD and their requirements.
  Accelerator Support – Refurbishment of IQB magnets for MI in progress. Disassembly of IQB310 and IQB169 is complete. Parts for the Booster biased cavity solenoid are available and core stacking and bonding is in progress.
G-2 – Winding on the outer coil has just started. Still some outer coil parts are being modified in the machine shop.
MDP 15-17 T dipole R&D
  Coil fabrication for 15 T dipole continues. Two coils are in preparation for impregnation or reaction.

## Slide 4: Cryogenic Sector – Engineering Department (3-12-2018)
  LCLS-II Procurements
    Distribution Boxes – Fabrication in continues at vendor, delivery expected in July
    Surface Transfer Line Procurement – Fabrication in progress at vendor, delivery expected in May
    Providing SLAC with guidance on installation activities for tunnel components, tunnel components are being installed with a 3rd party contractor
  Mu2e Procurement
    Distribution Box – Fabrication in progress, delivery expected in early May
    Feed Boxes – Technical evaluation of proposals completed (6 bids were received)
  HL-LHC AUP
    L4 manager created to manage all cryo-mechanical tasks, working with project to determine details and scope
    Resource loaded schedule has been submitted (project to begin practice EVMS reporting in April)
  Meson Controls Upgrade
    Project is underway – control cabinet construction, networking and initial programming, preparing for system shutdown in June for to switch system over to new control system
    Possibility that shutdown is delayed due to the need for extended cavity testing
  PIP-II Activities and Procurement
    External Cave Transfer Line fabrication in progress (in-house), completion expected in March
    PIP-II Cave Transfer Line procurement, delivery expected in May/June
    Installation to begin in March with external cave TL segments and supports followed by cave TL
  Sub-Kelvin Cryogenics
    SuperCDMS Snolab – CD2/3 review held in January. Awaiting formal sign-off and ESAAB
    ADMX (5K systems) – providing technical assistance on plant and recovery system through May
    Nexus – Refrigerator delivery later in April, NuMI hall preparations proceeding well
    Quantum Lab – Final ORC cryogenic approval given
    Facilities:
Meson Detector Building: Spoke cavity testing completed last week, cool down of new cavity this week
Cryomodule Test Facility: LCLS-II F1.3-09 CM cool down complete, testing began
Industrial Building 1: VTS stands: Two R&D and three LCLS-II cavities tested
Muon Campus: Supporting g-2 operation
Heavy Assembly Building: Purification in progress prior to Head B commissioning run