## Slide 1
Jay Theilacker
All Experimenters and Laboratory Status Meeting
March 19, 2018
TD Operations Status

## Slide 2: SRF Sector
R&D
  Quantum computing measurement continues.
  High Q0 high gradient: Nitrogen infusion program continues. Furnace troubleshooting/improvement is in progress
  Nb3Sn continues cavity preparation and coating. One cavity had a very nice coating appearance. Initial test showed improved Q-slope, however it was not as good as Cornell’s best cavity which had little Q-slope.
  High field Q slope: HF rinsing study is in progress
  Plasma processing continues.
  Nb/Cu vacuum chamber installation is in progress.
LCLS-II
  A new BPM assembly procedure and hardware continues to be successful following thermal cycle testing. A Quality Assurance Audit this week. Additional BPM studies planned.
  CM03 dis-assembly was completed. Rebuild started as a filler job between cryomodules.
  CM02, CM04 and CM05 beam line were back filled and warm end coupler were dis-assembled. They are ready for extraction and repair BPM. Actual repair is pending for approval.
  CM06 is still at SLAC due to BPM leak. A dummy cryomodule will be shipped to get vibration data first
  CM07 is at CMTF and needs to be moved to ICB to fix BPM. Pending shipping instrument (Demagnetized geophone)
  CM08 Helium circuit leak check was completed. BPM fix is planned pending SLAC approval.
  CM09 is at CMTF test cave. Q0 measurements exceed specification. 24 hour unit test completed.
  CM10 is in WS3. BPM fix is on hold before thermal shield weldment.
  CM11 WS1 resumed as BPM solution is finalized.
  CM12 WS0 completed.
  CM13 cavities were identified
PIP-II
  Spoke Cavity S111 Coupler installation experience a leak that was fixed with a new coupler. Cold test ~Mar 26
  Spoke Cavity S112 was qualified in STC with no field emission. Coupler installation next

## Slide 3: Magnet Sector
HL- LHC, AUP
Coil fabrication for LHC inner triplet quadrupoles continues. Electrical checkout of coil QXFA107 in progress. Mechanical measurements of coil QXFA108 after reaction is complete. The power lead preparation is complete and splicing is in progress.
The SC cable for coil QXFA110 is in-house. Winding expected to begin in about 4 weeks once the winding mandrel is freed (now used for QXFA109 coil).
Electrical checkout of MQXFS1d short model started in preparation to a cold test.
  LCLS II
  Test & qualification of the quadrupoles continues: SPQA128 and SPQA129 are received and in preparation for testing
  SPQA126 warm measurements and survey are complete. It will be shipped to JLAB together with SPQA128.
  Mu2e
  First Transport Solenoid production module is in-house, in preparation for incoming inspection.
  Dish head B passed all warm tests in HAB, completed wrapping MLI over He pipes, zero-magnet (shorted bus) cold commissioning test to start this week.
  Dished Head A – getting ready for the first production unit test in April.
G-2
Baking the spare MSE core is planned for this week.
Outer coil winding for the new inflector has been begun.
MDP 15-17 T dipole R&D
  Coil fabrication for 15 T dipole continues. Winding of the inner coil continues, two coils are in preparation for impregnation or reaction.
  Work on the mechanical model resumed.
Accelerator Support
  Nova M1 dipole thermal tests performed, started integral field measurements
  Measured FMI quadrupole 7346

## Slide 4: Cryogenic Sector
  LCLS-II Procurements
    Distribution Boxes – Fabrication continues at vendor, delivery expected in July
    Surface Transfer Line Procurement – Visiting vendor this week to check fabrication progress, delivery expected in May
    Providing SLAC with guidance on installation activities for tunnel components
    Attending Director’s Review at SLAC this week
  Mu2e Procurement
    Distribution Box – Fabrication in progress, delivery expected in early May
    Feed Boxes – Technical evaluation of proposals completed and awaiting pricing (6 bids were received)
  HL-LHC AUP
    Resource loaded schedule has been submitted (project to begin practice EVMS reporting in April)
  Meson Controls Upgrade
    Project is underway in parallel with existing controls, preparing for system shutdown in June to switch system over
    Possibility that shutdown is delayed due to the need for extended cavity testing (awaiting confirmation)
  PIP-II Activities and Procurement
    External Cave Transfer Line fabrication in progress (in-house), all sections completed except for final tie-in piece
    PIP-II Cave Transfer Line procurement, delivery expected in May/June
    Preparing for field installation at CMTF beginning with the external cave TL segments and supports followed by cave TL (once it arrives from the vendor)
  Sub-Kelvin Cryogenics
    SuperCDMS Snolab – CD2/3 ESAAB delayed until May due to budget and funding profile details still to be resolved within the Office of Science
    ADMX – Procurement of dilution refrigerator has been delayed due to vendor refusing to sign DOE vendor liability contract. Entering negotiations with the second qualified vendor
    Nexus – Refrigerator delivery later in April, NuMI hall preparations proceeding well
    Quantum Lab – Final ORC cryogenic approval given
    Facilities:
Meson Detector Building: Spoke cavity testing in STC, 3.9 GHz LCLS-II cavity testing in HTS
Cryomodule Test Facility: LCLS-II F1.3-09 CM measurements continue
Industrial Building 1: VTS stands: Two R&D and three LCLS-II cavities tested last week
Muon Campus: Supporting g-2 operation
Heavy Assembly Building: Refrigerator cooled down for test cryostat Head B commissioning