## Slide 1
Michael Tartaglia/Jay Theilacker
All Experimenters and Laboratory Status Meeting
April 02, 2018
TD Operations Status

## Slide 2: SRF Sector
LCLS-II 1.3 GHz Cryomodules
  A Quality Assurance Audit was completed. Future BPM will use Grade 5 Titanium studs and stainless steel nut. More tests of the BPM assembly procedure are expected this week.
  CM03 dis-assembly was completed. Rebuild started as a filler job between cryomodules.
  CM02, CM04, CM05, and CM07 beam line were back filled and warm end coupler were dis-assembled. They are ready for extraction and repair BPM. Actual repair is pending for approval.
  CM06 is still at SLAC due to BPM leak. A dummy cryomodule will be shipped to get vibration data first
  CM07 is transported back to ICB to fix BPM. It is being back filled to atmosphere pressure to prepare for BPM fix.
  CM08 Helium circuit leak check was completed. BPM fix is planned pending SLAC approval.
  CM09 is being warmed up due to cryoplant failure (see cryogenic status update). All test were completed however. It will need BPM fix after transported to ICB.
  CM10 is in WS3. BPM fix is on hold before thermal shield weldment.
  CM11 WS1 re-start is pending this week.
  CM12 WS0 completed.
  CM13 cavities were identified
LCLS-II Cavity Preparations
  1.3 GHz: No activity as we have no fresh vendor cavities and one re-HPR cavity is still in assembly process.
  3.9 GHz: 3HRI03 HTS is in progress. Cavity was installed back into the HTS cryostat. Helium vessel heater test is in progress.
PIP-II
  Spoke Cavity S111 had a high power coupler. During STC installation, a dent was discovered on coupler. It is being evaluated.
  Spoke Cavity S112 Coupler installation was completed and 120C baking is in progress.
  1-cell 650 MHz cavity (B9AS-AES-006) encountered EP issue. Investigation is in progress.

## Slide 3: SRF Sector
R&D
  Quantum computing measurement continues.
    One 2.6 GHz cavity reached very good base line test with great Q0 (5e10 at 1.45K, flat Q curve mostly) and gradient (31 MV/m)
    Second 2.6 GHz cavity has a real Qubit inside and will be tested in Quantum lab at ultra low temperature.
  High Q0 high gradient: Nitrogen infusion program continues. Furnace troubleshooting/improvement is in progress
  High field Q slope: HF rinsing study is in progress
  Nb3Sn group continues cavity preparation and coating.
  Plasma processing continues.
  Nb/Cu vacuum chamber installation is in progress.
S. Posen

## Slide 4: Magnet Sector
HL- LHC, AUP
Coil fabrication for the LHC inner triplet quadrupoles continues. Coil QXFA108 is getting ready for impregnation.
Coil QXFA109 is on hold until the reaction tooling becomes available.
Electrical checkout of MQXFS1d short model completed. Next mounting to top plate, insertion into VMTF for test.
  LCLS II
  Test & qualification of the quadrupoles continues: SPQA129 cold test in progress. SPQA128 ready for cold test.
  Mu2e
  Survey and SSW magnetic measurements of 1st TS Unit completed.
  The coils for next TS unit have all been completed, shells are nearly complete. Final shell machining required.
  Dished Head B checkout complete, assembly under vacuum. ORC walkthrough and cool down this week.
  Dished Head A – getting ready for the first production unit test in April.
  TSu Inner bore and thermal shield arrived last week. It was unloaded off the truck with custom designed below the hook (BTH) lifting fixture.
G-2
Outer coil winding for the new inflector is in progress.
MDP 15-17 T dipole R&D
  Coil fabrication for 15 T dipole continues. Reaction of the inner coil is in progress.
  Performed Mechanical model strain gauge studies in liquid nitrogen.
Accelerator Support
  Nova M1 dipole integral field measurements completed. Preparing Hall probe for saturation study.
  MSD184 sextupole thermal test performed. Strength and Harmonics measurements set up.
  Winding of a replacement coil for the leaking MDCC is in progress.
  Our technicians were requested to repair a water leak for FAST and expect to report to IOTA this week to re-position power flags on the Lambertson coil we previously fabricated.

## Slide 5: Cryogenic Sector
  LCLS-II Procurements
    Distribution Boxes – Fabrication continues at vendor, delivery expected in July
    Surface Transfer Line Procurement – Some modification to process bellows, delivery now expected in July
    Providing SLAC with guidance on installation activities for tunnel components – Final welding in tunnel commencing
  Mu2e Procurement
    Distribution Box – Fabrication in progress, delivery expected in May/June
    Feed Boxes – Technical evaluation of proposals completed and awaiting pricing (6 bids were received)
  HL-LHC AUP
    Beginning EVMS practice reporting this month. Working on Stand 4 upgrade tasks.
  Meson Controls Upgrade
    Project is underway in parallel with existing controls, preparing for system shutdown in June to switch system over
    Possibility that shutdown is delayed due to the need for extended cavity testing (still awaiting confirmation)
  PIP-II Activities and Procurement
    External Cave Transfer Line fabrication in progress (in-house), final tie-in piece in fabrication, all others complete
    PIP-II Cave Transfer Line procurement, delivery expected in May/June
    Field installation at CMTF have begun with the external cave TL segments and supports followed by cave TL (once it arrives from the vendor)
  Sub-Kelvin Cryogenics
    SuperCDMS Snolab – Waiting for ESAAB and official CD2/3 which is expected in May
    ADMX – Procurement issues with vendor have been resolved, expecting PO to be placed soon with a delivery of about 6 months. Finalizing details of new cold electronics packaging, i.e. optimization of magnetic shielding design for the sensitive electronics
    Nexus – Cryogenic review (5032) documents expected in a few weeks
    Facilities:
Meson Detector Building: 3.9 GHz LCLS-II cavity testing in HTS
Cryomodule Test Facility: LCLS-II F1.3-09 CM testing last week. Unexpected plant shutdown (see next slide)
Industrial Building 1: VTS stands: Three R&D cavities tested last week, Stand 3: One LCLS-II magnet tested
Muon Campus: Supporting g-2 operation
Heavy Assembly Building: Refrigerator cold for upcoming cryostat Head B commissioning

## Slide 6: Cryogenic Sector
  CMTF Cryogenic Plant Heat Exchanger Failure
    Refrigerator tripped off at 1am on Friday morning
    Restarted the plant and refilled the cryomodule during the day shift
    After reaching steady state, high helium losses were observed
    Losses appear to be from high pressure helium to low pressure nitrogen in one of the nitrogen pre-cooling heat exchangers
    Plant and cryomodule are warming up slowly through heat leak
    Meeting with refrigerator vendor Tuesday morning to determine best course of action (short term and long term)
    It is likely that the short term solution will be to cut out the exchanger, install bypasses and to operate without nitrogen precooling
    The next LCLS-II cryomodule is not expected for ~ 5 weeks
    We will work on a repair schedule to see if we can fit within the 5 week timeframe