## Load List
DUNE Loads | [6 empty] | Package Dimensions |  |  | Package Dimensions
Description | Contact | Date | Total Number of Units | Weight per unit | Units per package | Type of package | Width | Height | Length | Width | Height | Length | Package weight | Number of packages per trip | Type of trip | Number of Hoist Trips | Comment | Reference
|  |  |  | kg |  |  | m | m | m | in | in | in | kg |  |  | ea.
Photon Detector |  |  | 800 | 5 | 27 | Pallet | 0.9 | 1.2 | 0.9 |  |  |  | 135 | 3 | Cage | 10 | We assume 720 units + 80 spares. One unit includes PMT + mechanics + base + cable. Package weight does not include the pallet weight. In total, 10 trips x 3 packages x 27 PMTs . 1 trip per month (3 sectors/month)
Photon Detector |  |  | 1056 | 5 | 27 | Pallet | 0.9 | 1.2 | 0.9 |  |  |  | 135 | 2 | Cage | 20 | We assume 960 units + 96 spares. One unit includes PMT + mechanics + base + cable. Package weight does not include the pallet weight. In total, 20 trips x 2 packages x 27 PMTs. 2 trips per month (4 sectors/month)
[20 empty] | Length in | width in
[19 empty] | Cage Compartment | 145.5 | 54.5
Euro Pallet
Dimensions: 1200×800×144 mm. Pallet weight is approximately 20–24 kg, depending on wood moisture. The manufacturing process is precisely defined. The EURO pallet has a load capacity of up to 1500 kg; no more than three EURO pallets may be stacked.
Three euro pallets will fit in a cage.

## development
Laydown space needs
Dimensions
Description | Quantity per week | weight | Width | Height | Length | Total Length | Comment
| ea. | kg | m | m | m
Dataroom Setup
Installation SP Setup
DSS feedthroughs
Cleanroom
Install Equipment
Endwall Installation Phase | [5 empty] | 37.4
Endwall transport boxes | 6 |  | 1.5 | 2.5 | 5 | 30
Misc. Beams | 1 |  | 1 | 0.5 | 5 | 5
Misc. pallets | 2 |  | 0.8 |  | 1.2 | 2.4
APA-CPA installation phase
APA transport box | 6 |  | 1.5 | 2.8 | 6.8 | 40.8
Field cage top bottom modules
Cables
Misc. pallets |  |  | 0.8 |  | 1.2
DP CE installation phase
CE chimny installation | 27 |  | 0.8 | 2 | 2.5 | 33.75 | 240 CE chimneys need to be installed in 2 months. This corresponds to 9 weeks or 27 per week. I assume you can stack one CE crate on another when transporting or storing. Check with Dario.
DP Endwall installation phase
DP CRP installation phase

## Images
| Length in | width in
Cage Compartment | 145.5 | 54.5