## Slide 1
Jay Theilacker
All Experimenters and Laboratory Status Meeting
April 23, 2018
TD Operations Status

## Slide 2: SRF Sector
R&D
  Quantum computing measurement continues.
  High Q0 high gradient: Nitrogen infusion program continues.
  Nb3Sn group continues cavity preparation and coating. Additional cavity coating is in progress.
  High field Q slope: HF rinsing study is in progress
  Plasma processing continues.
  Nb/Cu vacuum chamber installation is in progress.
LCLS-II
  Retro-fit BPM procedure was approved by SLAC, all work restarted.
  CM03 dis-assembly was completed. Rebuild started as a filler job between cryomodules.
  CM02, CM04 CM05 and CM07 beam line were back filled and warm end coupler were dis-assembled. They are ready for extraction and repair BPM. Actual repair is pending for approval.
  CM06 is back at ICB, an autopsy procedure is in progress to diagnose the problem areas.
  CM08 BPM fix is in progress. BPM bolts were all replaced and torqued to spec. Clean room connection is in progress. Evacuation and leak check is planned for Tuesday (4/24).
  CM09 tests at CMTF test cave were completed. Warm-up is completed.
  CM10 is in WS3. BPM fix is on hold before thermal shield weldment.
  CM11 WS2 started. This is the first cryomodule after LCLS-II restart.
  CM12 WS0 completed. It is pending lolli-pop support from CM11.
  CM13 cavities were identified
PIP-II
  Spoke cavity S113 and S114 were both qualified with a lower power coupler.
LARP
    One RF deflecting cavity was prepared and ready to test

## Slide 3: Magnet Sector
HL- LHC, AUP
Coil fabrication for LHC interaction region (IR) quadrupoles is progressing well.
Manufacturing & Inspection Plan (MIP) still not approved by CERN, coil QXFA110 winding on hold.
Structural and Electrical Design Criteria Review of the IR (MQXF) magnets for the HL-LHC AUP next week.
Short magnet MQXFS1d cool down is complete, quench tests are expected this week.
  LCLS II
  Testing is idle, suspected instrumentation issues gave way to the discovery of inadequately bonded heat-sinks within SPQA129. This magnet was returned to the vendor, Milhous for repair. SPQA130 are prepared for test.
  Mu2e
  Warm tests of the first TS production module are proceeding. Single stretched wire measurements completed last week. Electrical, leak and pressure tests were successfully completed, dimensional measurements will continue in HAB.
  The second dish head for the TS test facility at HAB is being commissioned with the leads shorted together with a length of superconductor. System cooldown complete. High current tests will be done this week..
  Dimension measurements of the TSu inner bore are on-going. Leak check of the inner thermal shield piping took place last week. There appears to be a leak in the thermal shield piping. Vendor has been notified and a plan for repair is being prepared.
  Milhous Company reports that the ISA sextupole’s first magnet’s coils are being potted. The cores are in production. The lead engineer on the project is scheduled to visit Milhous the week of May 7th.
G-2
  Inflector coil winding is close to completion. Now winding the last turns of the outer coil.
MDP 15-17 T dipole R&D
  Lead splicing in the inner coil HFD-CL1-002 is on hold due to safety issues with the soldering cart wiring.
Accelerator Support
The Booster solenoid winding is complete. The coil is being pumped-down for potting. The EDWA bend dipole for muon beamline has been returned to IB2 to resolve a problem with interference between the coil supports and the measurement probe support.

## Slide 4: Cryogenic Sector
  LCLS-II Procurements
    Distribution Boxes – Fabrication continues at vendor, delivery expected in July.
    Surface Transfer Line Procurement – Delivery expected in July
    Providing SLAC with guidance on installation activities for tunnel components – Final welding in tunnel commencing
    DOE review schedule for May 8-10 at SLAC
  Mu2e Procurement
    Distribution Box – Fabrication in progress, delivery expected in May/June
    Feed Boxes – Contract in process of awarding contract
  HL-LHC AUP
    Began EVMS practice reporting this month. Working on Stand 4 upgrade tasks. Waiting for final docs from CERN.
  Meson Controls Upgrade
    Project is underway in parallel with existing controls, preparing for system shutdown in June to switch system over
    Possibility that shutdown is delayed due to the need for extended cavity testing (awaiting confirmation and schedule)
  PIP-II Activities and Procurement
    External Cave Transfer Line fabrication in progress (in-house), final tie-in piece in fabrication, all others complete
    PIP-II Cave Transfer Line procurement, delivery expected in May/June
    Field installation at CMTF have begun with the external cave TL segments and supports followed by cave TL (once it arrives from the vendor)
  Sub-Kelvin Cryogenics
    SuperCDMS Snolab – Operations review schedule for June 19 in Germantown, internal E-Tank review on May 18
    ADMX – Procurement issues with vendor ongoing (several iterations with DOE on legal waiver regarding procurement liability) verbally committed to expediting the delivery as much as possible to avoid schedule slippage
    Nexus – Cryogenic review (5032) documents expected in a few weeks
    Facilities:
Meson Detector Building: Three Spoke cavities tested in STC, HTS warm, HTSC cooldown and testing
Cryomodule Test Facility: LCLS-II F1.3-09 CM testing last week. Plant is under repair
Industrial Building 1: 3 x LCLS-II cavities (CAV0139, CAV0153, CAV0323); 2 x 1.3 GHz single cell cavities for R&D
      VMTF testing of HL-LHC model magnet, Cryo plant is experiencing low capacity due to contamination
Muon Campus: Supporting g-2 operation Support g-2 operation
Heavy Assembly Building: Test of cryostat Head B underway

## Slide 5: Cryogenic Sector
  CMTF Cryogenic Plant Repair Update
    Successful leak check of recuperative N2/He heat exchanger
    Piping modifications will be finished early this week.
    Pressure test and sniffer leak check this week
    Vacuum shell reinstalled next week