## Slide 1: Far detector Construction Schedule
Dario Autiero (IPNL Lyon) and Takuya Hasegawa (KEK)
April 19, 2018

## Slide 2: Construction Schedule
Targeting having an initial draft construction schedule for RRB meeting in April
Should be very high-level (10-20 activities and/or milestones per consortia)
To facilitate putting this together, we will provide 10-15 high-level, global milestones for the consortia activities to plug into

## Slide 3: High-level Global Milestones
RRB Approval of TDR - 09/2019
Beneficial Occupancy of CUC Counting room -
Beneficial Occupancy of Integration Test Facility -
Begin integration/testing of Detector #1 components at ITF - 02/2022
Begin integration/testing of Detector #2 components at ITF – 11/2023
Construction of steel frames for Cryostats #1 and #2 complete -
Beneficial occupancy of cryostat #1 –
Cryostat #1 ready for TPC installation – 05/2023
Begin closing TCO for cryostat #1 – 05/2024
Cryostat #1 ready for filling
Detector #1 ready for operations
Beneficial occupancy of cryostat #2 –
Cryostat #2 ready for TPC installation – 08/2024
Begin closing TCO for cryostat #2 – 08/2025
Cryostat #2 ready for filling -
Detector #2 ready for operations -

## Slide 4
DP-Electronics Construction Schedule
Start of chimneys production 1/2023 (Production of chimneys (240) and tests, 1 year)
Start of uTCA infrastructure production 1/2023 (Production uTCA infrastructure components (240 crates for CRO), 6 months, including LRO crates (*) )
Start of analog FE production 1/2023 (Production analog FE cards (ASICS + 2400 cards) and tests, 1 year)
Start of digitization cards production 1/2023 (Production CRO digitization cards (2400) and tests, 1 year, including also LRO cards)
Start of White Rabbit production 1/2023 (Production White Rabbit components (switches + 240 end nodes for CRO) and tests, 6 months, including LRO end nodes)
 Note that the productions may be started earlier than needed for shipment to SURF in order to match funding profiles, distribute expenditures more evenly with time and have more time for QA/QC. The start of productions can be as early as happening by end of 2021
Cryostat #2 ready for TPC installation – 08/2024
Chimneys installation 8/2024 -11/2024, 3 months (4 units/day)
Optical fibers cabling, uTCa and White Rabbit installation 11/2024, 1 month
Low voltage cabling and blades insertion in the chimneys 11-12/2024, 2 months
Installation of digitization cards and commissioning of the system 1/2025, 1 month
Begin closing TCO for cryostat #2 – 08/2025
(*) Note: baseline assumption for LRO, to be confirmed by PD Consortium simulations is 1PM/m2  720 channels, 144 channels/crate, 5 crates