## All (hidden)
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
1 | DUNE Milestones | 260 days | Mon 4/2/18 |  | Mon 4/1/19 |  | 0%
1.1 | Submit DUNE Technical Proposal (internal) | 0 days | Mon 4/2/18 |  | Mon 4/2/18 |  | 0%
2 | Slow Controls & Cryo Instrumentation Consortium | 40 days | Fri 12/1/17 |  | Thu 1/25/18 |  | 0%
2.1 | Cryogenic Instrumentation | 523 days | Fri 12/29/17 |  | Tue 12/31/19 |  | 0%
2.1.1 | Finalize FT requirements/locations for Instrumentation devices | 0 days | Fri 12/29/17 |  | Fri 12/29/17 |  | 0%
2.1.2 | Form a CFD steering group that will guide the next steps for CFD for the consortium | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.1.3 | Produce list of needed CFD simulations | 21 days | Thu 2/15/18 |  | Thu 3/15/18 |  | 0%
2.1.4 | Produce list of E-field simulations needed for Instrumentation design | 21 days | Thu 2/15/18 |  | Thu 3/15/18 |  | 0%
2.1.5 | Perform needed CFD Studies | 140 days | Fri 3/16/18 |  | Thu 9/27/18 |  | 0%
2.1.6 | Produce needed E-field simulation studies for instrumentation designs | 140 days | Fri 3/16/18 |  | Thu 9/27/18 |  | 0%
2.1.7 | Perform E-field Shielding studies for Instrumentation designs for DP | 87 days | Fri 3/16/18 |  | Mon 7/16/18 |  | 0%
2.1.8 | Define preliminary hardware/software/mechanical interfaces | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.1.9 | Define requirements for Instrumentation devices (No. of devices, locations, Sensitivity requirements etc.) | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
2.1.10 | For Internal Cryogenic Piping, converge on a conceptual design and layout | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.1.11 | Investigate applicability of SP instrumentation designs to DP detector | 66 days | Fri 3/30/18 |  | Fri 6/29/18 |  | 0%
2.1.12 | Develop design for Purity Monitors (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.13 | Develop design for Static T-Gradient Thermometers (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.14 | Develop design for Dynamic T-Gradient Thermometers (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.15 | Develop design for Individual Sensors (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.16 | R & D to develop design for Cold Cryogenic Cameras (including support system and feedthroughs) | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.17 | R & D to develop design for Warm Inspection Cameras (including support system and feedthroughs) | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.18 | R & D to develop design for Light Emitting System (including support system and feedthroughs) | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.2 | Slow Controls | 489 days | Thu 2/15/18 |  | Tue 12/31/19 |  | 0%
2.2.1 | Define slow controls mechanical and software interfaces | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.2.2 | Define slow controls hardware requirements & layout | 0 days | Sat 3/31/18 |  | Sat 3/31/18 |  | 0%
2.2.3 | Define slow controls software/firmware requirements | 0 days | Sat 3/31/18 |  | Sat 3/31/18 |  | 0%
2.2.4 | Specify requirements for common rack layout and packaging | 86 days | Mon 4/2/18 |  | Mon 7/30/18 |  | 0%
2.3 | TP/TDR | 315 days | Mon 1/15/18 |  | Fri 3/29/19 |  | 0%
2.3.1 | TP/TDR outline and table of contents (down to section headings) defined | 0 days | Mon 1/15/18 |  | Mon 1/15/18 |  | 0%
2.3.2 | Prepare & Submit Technical Proposal for internal review | 0 days | Sat 3/31/18 |  | Sat 3/31/18 |  | 0%
3 | APA Consortium | 301 days | Thu 2/1/18 |  | Fri 3/29/19 |  | 0%
3.1 | Requirements on FD APA | 43 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.1.1 | Assess requirement on wire spacing and wire plane gap uniformity | 21 days | Thu 2/1/18 |  | Thu 3/1/18 |  | 0%
3.1.2 | Assess requirements on wire tension for APA frames | 31 days | Thu 2/1/18 |  | Thu 3/15/18 |  | 0%
3.1.3 | Assess cabling requirements for CE and PD | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.1.4 | Define mounting structure for PD | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2 | Modification of APA frame to make it compatible with FD 10kton module | 87 days | Thu 2/1/18 |  | Fri 6/1/18 |  | 0%
3.2.1 | Define modified APA frame design | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2.2 | Define linkage for the 2-APA assembly | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2.3 | Define yoke for the 2-APA assembly and interface with the HV field cage | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2.4 | Final FEA analysis | 45 days | Mon 4/2/18 |  | Fri 6/1/18 |  | 0%
3.2.5 | Board design for prototype APA frame | 45 days | Mon 4/2/18 |  | Fri 6/1/18 |  | 0%
3.4 | Winder modifications | 217 days | Thu 2/1/18 |  | Fri 11/30/18 |  | 0%
3.4.1 | Determine Improvements to the winder | 97 days | Thu 2/1/18 |  | Fri 6/15/18 |  | 0%
3.6 | Specifications and schedule for Integration and Installation | 217 days | Thu 2/1/18 |  | Sat 12/1/18 |  | 0%
3.6.1 | Define tests and integration procedures at the Integration Facility and schedule | 217 days | Thu 2/1/18 |  | Sat 12/1/18 |  | 0%
3.6.2 | Define APA installation steps at SURF and schedule | 217 days | Thu 2/1/18 |  | Sat 12/1/18 |  | 0%
3.7 | TP/TDR | 260 days | Fri 3/30/18 |  | Fri 3/29/19 |  | 0%
3.7.1 | APA Technical Proposal - Submit for Internal Review | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
3.7.2 | Define interface with CE and PD, including cabling | 0 days | Mon 4/16/18 |  | Mon 4/16/18 |  | 0%
4 | Dual Phase Electronics Consortium | 324 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
4.1 | Technical Activities | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
4.1.1 | Prepare Costing for Technical Proposal | 20 days | Mon 2/26/18 |  | Fri 3/23/18 |  | 0%
4.1.2 | Initial Development of Installation Schedule | 20 days | Mon 2/26/18 |  | Fri 3/23/18 |  | 0%
4.1.4 | Installation and Commissioning of PD-DP | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
4.2 | TP/TDR | 264 days | Fri 3/23/18 |  | Fri 3/29/19 |  | 0%
4.2.1 | Editing of TP | 0 days | Fri 3/23/18 |  | Fri 3/23/18 |  | 0%
4.2.2 | DP-Elec Technical Proposal - Submit for Internal Review | 0 days | Mon 3/26/18 |  | Mon 3/26/18 |  | 0%
5 | DAQ Consortium | 324 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
5.1 | Technical Activities | 285 days | Mon 2/19/18 |  | Fri 3/22/19 |  | 0%
5.1.1 | Initial Drafts of Interface documents completed | 0 days | Mon 2/19/18 |  | Mon 2/19/18 |  | 0%
5.1.2 | Performance and functional specifications document completed | 0 days | Mon 2/19/18 |  | Mon 2/19/18 |  | 0%
5.1.3 | Develop Initial system cost estimate | 30 days | Mon 2/19/18 |  | Fri 3/30/18 |  | 0%
5.1.4 | DAQ cost and infrastructure requirements document completed | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
5.1.5 | Develop First SP prototype DAQ hardware | 160 days | Mon 2/19/18 |  | Fri 9/28/18 |  | 0%
5.2 | TP/TDR | 324 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
5.2.1 | Editing of TP | 65 days | Mon 1/1/18 |  | Fri 3/30/18 |  | 0%
5.2.2 | DAQ Technical Proposal - Submit for Internal Review | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
6 | Dual Phase Photon Detector Consortium | 334 days | Tue 12/12/17 |  | Mon 3/25/19 |  | 0%
6.1 | Photosensors | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
6.1.2 | Installation and Commissioning of PD-DP | 300 days | Mon 1/1/18 |  | Fri 2/22/19 |  | 0%
6.2 | PMT calibration system | 320 days | Sun 12/31/17 |  | Fri 3/22/19 |  | 0%
6.2.1 | Define calibration requirements | 61 days | Sun 12/31/17 |  | Fri 3/23/18 |  | 0%
6.2.2 | System design | 115 days | Mon 3/26/18 |  | Fri 8/31/18 |  | 0%
6.3 | Simulation & Physics | 320 days | Sun 12/31/17 |  | Mon 3/25/19 |  | 0%
6.3.1 | Develop Light Simulation Tools | 109 days | Sun 12/31/17 |  | Wed 5/30/18 |  | 0%
6.4 | TP/TDR | 334 days | Tue 12/12/17 |  | Mon 3/25/19 |  | 0%
6.4.1 | Complete Initial Pass of Interfaces | 0 days | Tue 12/12/17 |  | Tue 12/12/17 |  | 0%
6.4.2 | Complete Draft Production schedule and intial cost estimate | 0 days | Thu 3/22/18 |  | Thu 3/22/18 |  | 0%
6.4.3 | DP-PD Technical Proposal - Submit for Internal Review | 0 days | Mon 3/26/18 |  | Mon 3/26/18 |  | 0%
7 | HV System Consortium | 325 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
7.1 | Field Cage R&D | 205 days | Mon 2/19/18 |  | Fri 11/30/18 |  | 0%
7.1.1 | Additional studies of SP field cage design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.1.3 | Additional studies of DP field cage design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.2 | Cathode Panel Assembly R&D | 205 days | Mon 2/19/18 |  | Fri 11/30/18 |  | 0%
7.2.1 | Additional studies of SP cathode design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.2.3 | Additional studies of DP cathode design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.3 | HV Feedthrough R&D | 281 days | Mon 1/1/18 |  | Mon 1/28/19 |  | 0%
7.3.1 | Complete necessary R&D on Feedthrough design | 281 days | Mon 1/1/18 |  | Mon 1/28/19 |  | 0%
7.5 | TP/TDR | 265 days | Mon 3/26/18 |  | Fri 3/29/19 |  | 0%
7.5.1 | HV Technical Proposal - Submit for Internal Review | 0 days | Mon 3/26/18 |  | Mon 3/26/18 |  | 0%
8 | Single Phase Cold Electronics Consortium | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
8.2 | FE ASIC | 53 days | Mon 1/1/18 |  | Thu 3/15/18 |  | 0%
8.2.1 | Design and Layout of revision 8 FE ASIC | 43 days | Mon 1/1/18 |  | Wed 2/28/18 |  | 0%
8.2.2 | Review design and layout of revision 8 FE ASIC | 10 days | Thu 3/1/18 |  | Wed 3/14/18 |  | 0%
8.2.3 | Submission of revision 8 FE ASIC (address issues with baseline) | 0 days | Thu 3/15/18 |  | Thu 3/15/18 |  | 0%
8.3 | SLAC CRYO ASIC | 86 days | Wed 2/28/18 |  | Wed 6/27/18 |  | 0%
8.3.1 | Submission of DUNE specific of SLAC CRYO ASIC | 0 days | Wed 2/28/18 |  | Wed 2/28/18 |  | 0%
8.3.2 | Production run of SLAC cryo ASIC | 44 days | Wed 2/28/18 |  | Mon 4/30/18 |  | 0%
8.4 | Alternative Options | 30 days | Mon 4/2/18 |  | Mon 5/14/18 |  | 0%
8.4.2 | Finish SBND studies of commercial ADC chips | 0 days | Mon 4/2/18 |  | Mon 4/2/18 |  | 0%
8.5 | BNL-FNAL-LBNL ADC ASIC | 205 days | Mon 1/1/18 |  | Fri 10/12/18 |  | 0%
8.5.1 | Design and Layout of BNL-FNAL-LBNL ADC ASIC | 109 days | Mon 1/1/18 |  | Thu 5/31/18 |  | 0%
8.6 | COLDATA ASIC | 205 days | Mon 1/1/18 |  | Fri 10/12/18 |  | 0%
8.6.1 | Design and Layout of COLDATA ASIC | 109 days | Mon 1/1/18 |  | Thu 5/31/18 |  | 0%
8.8 | TP/TDR | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
8.8.1 | Define requirements for Single Phase TPC Cold Electronics | 36 days | Mon 1/1/18 |  | Mon 2/19/18 |  | 0%
8.8.2 | Finalize APA interfaces | 60 days | Mon 1/1/18 |  | Fri 3/23/18 |  | 0%
8.8.3 | SP-Elec Technical Proposal - Submit for Internal Review | 0 days | Fri 3/23/18 |  | Fri 3/23/18 |  | 0%
8.8.4 | Define testing criteria for longevity / reliability of cold ASICs | 86 days | Mon 1/1/18 |  | Mon 4/30/18 |  | 0%
9 | Single Phase Photon Detector | 325 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
9.1 | Physics/Simulation | 298 days | Tue 1/2/18 |  | Thu 2/21/19 |  | 0%
9.1.1 | Preliminary assessment of Physics requirements for Photon Detection system | 59 days | Tue 1/2/18 |  | Fri 3/23/18 |  | 0%
9.1.3 | Run simulations studies to better quantify physics requirements for Photon Detection | 195 days | Mon 3/26/18 |  | Fri 12/21/18 |  | 0%
9.2 | Light Collectors | 299 days | Mon 1/1/18 |  | Thu 2/21/19 |  | 0%
9.2.1 | Development of next generation ARAPUCA technology | 237 days | Mon 1/1/18 |  | Tue 11/27/18 |  | 0%
9.2.2 | Testing of next generation ARAPUCA design | 245 days | Mon 2/26/18 |  | Fri 2/1/19 |  | 0%
9.2.3 | Analysis of next generation ARAPUCA test data | 219 days | Mon 4/23/18 |  | Thu 2/21/19 |  | 0%
9.3 | Photosensors | 257 days | Thu 3/1/18 |  | Fri 2/22/19 |  | 0%
9.3.1 | Sample-lots of candidate photosensors in hand, along with testing facilities | 133 days | Thu 3/1/18 |  | Mon 9/3/18 |  | 0%
9.3.2 | Testing of candidate photosensors and photosensor ganging | 222 days | Thu 3/29/18 |  | Fri 2/1/19 |  | 0%
9.4 | Electronics/Cabling | 300 days | Mon 1/1/18 |  | Fri 2/22/19 |  | 0%
9.4.1 | Development of optimized electronics readout and cabling design | 237 days | Mon 1/1/18 |  | Tue 11/27/18 |  | 0%
9.4.2 | Prototyping and testing of optimized electronics readout and cabling | 245 days | Mon 2/26/18 |  | Fri 2/1/19 |  | 0%
9.4.3 | Analysis of optimized electronics test data | 220 days | Mon 4/23/18 |  | Fri 2/22/19 |  | 0%
9.5 | TP/TDR | 324 days | Tue 1/2/18 |  | Fri 3/29/19 |  | 0%
9.5.1 | Establish preliminary criteria for PD technology down-select (included in TP) | 59 days | Tue 1/2/18 |  | Fri 3/23/18 |  | 0%
9.5.2 | SP-Photon Detector Technical Proposal - Submit for Internal Review | 0 days | Fri 3/23/18 |  | Fri 3/23/18 |  | 0%

## SC & Cryo
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
2 | Slow Controls & Cryo Instrumentation Consortium | 40 days | Fri 12/1/17 |  | Thu 1/25/18 |  | 0%
2.1 | Cryogenic Instrumentation | 523 days | Fri 12/29/17 |  | Tue 12/31/19 |  | 0%
2.1.1 | Finalize FT requirements/locations for Instrumentation devices | 0 days | Fri 12/29/17 |  | Fri 12/29/17 |  | 0%
2.1.2 | Form a CFD steering group that will guide the next steps for CFD for the consortium | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.1.3 | Produce list of needed CFD simulations | 21 days | Thu 2/15/18 |  | Thu 3/15/18 |  | 0%
2.1.4 | Produce list of E-field simulations needed for Instrumentation design | 21 days | Thu 2/15/18 |  | Thu 3/15/18 |  | 0%
2.1.5 | Perform needed CFD Studies | 140 days | Fri 3/16/18 |  | Thu 9/27/18 |  | 0%
2.1.6 | Produce needed E-field simulation studies for instrumentation designs | 140 days | Fri 3/16/18 |  | Thu 9/27/18 |  | 0%
2.1.7 | Perform E-field Shielding studies for Instrumentation designs for DP | 87 days | Fri 3/16/18 |  | Mon 7/16/18 |  | 0%
2.1.8 | Define preliminary hardware/software/mechanical interfaces | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.1.9 | Define requirements for Instrumentation devices (No. of devices, locations, Sensitivity requirements etc.) | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
2.1.10 | For Internal Cryogenic Piping, converge on a conceptual design and layout | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.1.11 | Investigate applicability of SP instrumentation designs to DP detector | 66 days | Fri 3/30/18 |  | Fri 6/29/18 |  | 0%
2.1.12 | Develop design for Purity Monitors (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.13 | Develop design for Static T-Gradient Thermometers (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.14 | Develop design for Dynamic T-Gradient Thermometers (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.15 | Develop design for Individual Sensors (including support system and feedthroughs) from ProtoDUNE reference | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.16 | R & D to develop design for Cold Cryogenic Cameras (including support system and feedthroughs) | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.17 | R & D to develop design for Warm Inspection Cameras (including support system and feedthroughs) | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.1.18 | R & D to develop design for Light Emitting System (including support system and feedthroughs) | 197 days | Fri 3/30/18 |  | Mon 12/31/18 |  | 0%
2.2 | Slow Controls | 489 days | Thu 2/15/18 |  | Tue 12/31/19 |  | 0%
2.2.1 | Define slow controls mechanical and software interfaces | 0 days | Thu 2/15/18 |  | Thu 2/15/18 |  | 0%
2.2.2 | Define slow controls hardware requirements & layout | 0 days | Sat 3/31/18 |  | Sat 3/31/18 |  | 0%
2.2.3 | Define slow controls software/firmware requirements | 0 days | Sat 3/31/18 |  | Sat 3/31/18 |  | 0%
2.2.4 | Specify requirements for common rack layout and packaging | 86 days | Mon 4/2/18 |  | Mon 7/30/18 |  | 0%
2.3 | TP/TDR | 315 days | Mon 1/15/18 |  | Fri 3/29/19 |  | 0%
2.3.1 | TP/TDR outline and table of contents (down to section headings) defined | 0 days | Mon 1/15/18 |  | Mon 1/15/18 |  | 0%
2.3.2 | Prepare & Submit Technical Proposal for internal review | 0 days | Sat 3/31/18 |  | Sat 3/31/18 |  | 0%

## APA
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
3 | APA Consortium | 301 days | Thu 2/1/18 |  | Fri 3/29/19 |  | 0%
3.1 | Requirements on FD APA | 43 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.1.1 | Assess requirement on wire spacing and wire plane gap uniformity | 21 days | Thu 2/1/18 |  | Thu 3/1/18 |  | 0%
3.1.2 | Assess requirements on wire tension for APA frames | 31 days | Thu 2/1/18 |  | Thu 3/15/18 |  | 0%
3.1.3 | Assess cabling requirements for CE and PD | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.1.4 | Define mounting structure for PD | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2 | Modification of APA frame to make it compatible with FD 10kton module | 87 days | Thu 2/1/18 |  | Fri 6/1/18 |  | 0%
3.2.1 | Define modified APA frame design | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2.2 | Define linkage for the 2-APA assembly | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2.3 | Define yoke for the 2-APA assembly and interface with the HV field cage | 42 days | Thu 2/1/18 |  | Sun 4/1/18 |  | 0%
3.2.4 | Final FEA analysis | 45 days | Mon 4/2/18 |  | Fri 6/1/18 |  | 0%
3.2.5 | Board design for prototype APA frame | 45 days | Mon 4/2/18 |  | Fri 6/1/18 |  | 0%
3.4 | Winder modifications | 217 days | Thu 2/1/18 |  | Fri 11/30/18 |  | 0%
3.4.1 | Determine Improvements to the winder | 97 days | Thu 2/1/18 |  | Fri 6/15/18 |  | 0%
3.6 | Specifications and schedule for Integration and Installation | 217 days | Thu 2/1/18 |  | Sat 12/1/18 |  | 0%
3.6.1 | Define tests and integration procedures at the Integration Facility and schedule | 217 days | Thu 2/1/18 |  | Sat 12/1/18 |  | 0%
3.6.2 | Define APA installation steps at SURF and schedule | 217 days | Thu 2/1/18 |  | Sat 12/1/18 |  | 0%
3.7 | TP/TDR | 260 days | Fri 3/30/18 |  | Fri 3/29/19 |  | 0%
3.7.1 | APA Technical Proposal - Submit for Internal Review | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
3.7.2 | Define interface with CE and PD, including cabling | 0 days | Mon 4/16/18 |  | Mon 4/16/18 |  | 0%

## DP-Elec
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
4 | Dual Phase Electronics Consortium | 324 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
4.1 | Technical Activities | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
4.1.1 | Prepare Costing for Technical Proposal | 20 days | Mon 2/26/18 |  | Fri 3/23/18 |  | 0%
4.1.2 | Initial Development of Installation Schedule | 20 days | Mon 2/26/18 |  | Fri 3/23/18 |  | 0%
4.1.4 | Installation and Commissioning of PD-DP | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
4.2 | TP/TDR | 264 days | Fri 3/23/18 |  | Fri 3/29/19 |  | 0%
4.2.1 | Editing of TP | 0 days | Fri 3/23/18 |  | Fri 3/23/18 |  | 0%
4.2.2 | DP-Elec Technical Proposal - Submit for Internal Review | 0 days | Mon 3/26/18 |  | Mon 3/26/18 |  | 0%

## DAQ
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
5 | DAQ Consortium | 324 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
5.1 | Technical Activities | 285 days | Mon 2/19/18 |  | Fri 3/22/19 |  | 0%
5.1.1 | Initial Drafts of Interface documents completed | 0 days | Mon 2/19/18 |  | Mon 2/19/18 |  | 0%
5.1.2 | Performance and functional specifications document completed | 0 days | Mon 2/19/18 |  | Mon 2/19/18 |  | 0%
5.1.3 | Develop Initial system cost estimate | 30 days | Mon 2/19/18 |  | Fri 3/30/18 |  | 0%
5.1.4 | DAQ cost and infrastructure requirements document completed | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%
5.1.5 | Develop First SP prototype DAQ hardware | 160 days | Mon 2/19/18 |  | Fri 9/28/18 |  | 0%
5.2 | TP/TDR | 324 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
5.2.1 | Editing of TP | 65 days | Mon 1/1/18 |  | Fri 3/30/18 |  | 0%
5.2.2 | DAQ Technical Proposal - Submit for Internal Review | 0 days | Fri 3/30/18 |  | Fri 3/30/18 |  | 0%

## DP-PD
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
6 | Dual Phase Photon Detector Consortium | 334 days | Tue 12/12/17 |  | Mon 3/25/19 |  | 0%
6.1 | Photosensors | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
6.1.2 | Installation and Commissioning of PD-DP | 300 days | Mon 1/1/18 |  | Fri 2/22/19 |  | 0%
6.2 | PMT calibration system | 320 days | Sun 12/31/17 |  | Fri 3/22/19 |  | 0%
6.2.1 | Define calibration requirements | 61 days | Sun 12/31/17 |  | Fri 3/23/18 |  | 0%
6.2.2 | System design | 115 days | Mon 3/26/18 |  | Fri 8/31/18 |  | 0%
6.3 | Simulation & Physics | 320 days | Sun 12/31/17 |  | Mon 3/25/19 |  | 0%
6.3.1 | Develop Light Simulation Tools | 109 days | Sun 12/31/17 |  | Wed 5/30/18 |  | 0%
6.4 | TP/TDR | 334 days | Tue 12/12/17 |  | Mon 3/25/19 |  | 0%
6.4.1 | Complete Initial Pass of Interfaces | 0 days | Tue 12/12/17 |  | Tue 12/12/17 |  | 0%
6.4.2 | Complete Draft Production schedule and intial cost estimate | 0 days | Thu 3/22/18 |  | Thu 3/22/18 |  | 0%
6.4.3 | DP-PD Technical Proposal - Submit for Internal Review | 0 days | Mon 3/26/18 |  | Mon 3/26/18 |  | 0%

## HV
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
7 | HV System Consortium | 325 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
7.1 | Field Cage R&D | 205 days | Mon 2/19/18 |  | Fri 11/30/18 |  | 0%
7.1.1 | Additional studies of SP field cage design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.1.3 | Additional studies of DP field cage design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.2 | Cathode Panel Assembly R&D | 205 days | Mon 2/19/18 |  | Fri 11/30/18 |  | 0%
7.2.1 | Additional studies of SP cathode design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.2.3 | Additional studies of DP cathode design | 92 days | Mon 2/19/18 |  | Tue 6/26/18 |  | 0%
7.3 | HV Feedthrough R&D | 281 days | Mon 1/1/18 |  | Mon 1/28/19 |  | 0%
7.3.1 | Complete necessary R&D on Feedthrough design | 281 days | Mon 1/1/18 |  | Mon 1/28/19 |  | 0%
7.5 | TP/TDR | 265 days | Mon 3/26/18 |  | Fri 3/29/19 |  | 0%
7.5.1 | HV Technical Proposal - Submit for Internal Review | 0 days | Mon 3/26/18 |  | Mon 3/26/18 |  | 0%

## SP-Cold Elec
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
8 | Single Phase Cold Electronics Consortium | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
8.2 | FE ASIC | 53 days | Mon 1/1/18 |  | Thu 3/15/18 |  | 0%
8.2.1 | Design and Layout of revision 8 FE ASIC | 43 days | Mon 1/1/18 |  | Wed 2/28/18 |  | 0%
8.2.2 | Review design and layout of revision 8 FE ASIC | 10 days | Thu 3/1/18 |  | Wed 3/14/18 |  | 0%
8.2.3 | Submission of revision 8 FE ASIC (address issues with baseline) | 0 days | Thu 3/15/18 |  | Thu 3/15/18 |  | 0%
8.3 | SLAC CRYO ASIC | 86 days | Wed 2/28/18 |  | Wed 6/27/18 |  | 0%
8.3.1 | Submission of DUNE specific of SLAC CRYO ASIC | 0 days | Wed 2/28/18 |  | Wed 2/28/18 |  | 0%
8.3.2 | Production run of SLAC cryo ASIC | 44 days | Wed 2/28/18 |  | Mon 4/30/18 |  | 0%
8.4 | Alternative Options | 30 days | Mon 4/2/18 |  | Mon 5/14/18 |  | 0%
8.4.2 | Finish SBND studies of commercial ADC chips | 0 days | Mon 4/2/18 |  | Mon 4/2/18 |  | 0%
8.5 | BNL-FNAL-LBNL ADC ASIC | 205 days | Mon 1/1/18 |  | Fri 10/12/18 |  | 0%
8.5.1 | Design and Layout of BNL-FNAL-LBNL ADC ASIC | 109 days | Mon 1/1/18 |  | Thu 5/31/18 |  | 0%
8.6 | COLDATA ASIC | 205 days | Mon 1/1/18 |  | Fri 10/12/18 |  | 0%
8.6.1 | Design and Layout of COLDATA ASIC | 109 days | Mon 1/1/18 |  | Thu 5/31/18 |  | 0%
8.8 | TP/TDR | 320 days | Mon 1/1/18 |  | Fri 3/22/19 |  | 0%
8.8.1 | Define requirements for Single Phase TPC Cold Electronics | 36 days | Mon 1/1/18 |  | Mon 2/19/18 |  | 0%
8.8.2 | Finalize APA interfaces | 60 days | Mon 1/1/18 |  | Fri 3/23/18 |  | 0%
8.8.3 | SP-Elec Technical Proposal - Submit for Internal Review | 0 days | Fri 3/23/18 |  | Fri 3/23/18 |  | 0%
8.8.4 | Define testing criteria for longevity / reliability of cold ASICs | 86 days | Mon 1/1/18 |  | Mon 4/30/18 |  | 0%

## SP-PD
WBS | Task Name | Duration | Start | Updated Start | Finish | Updated Finish | % Complete | Updated % Complete
9 | Single Phase Photon Detector | 325 days | Mon 1/1/18 |  | Fri 3/29/19 |  | 0%
9.1 | Physics/Simulation | 298 days | Tue 1/2/18 |  | Thu 2/21/19 |  | 0%
9.1.1 | Preliminary assessment of Physics requirements for Photon Detection system | 59 days | Tue 1/2/18 |  | Fri 3/23/18 |  | 0%
9.1.3 | Run simulations studies to better quantify physics requirements for Photon Detection | 195 days | Mon 3/26/18 |  | Fri 12/21/18 |  | 0%
9.2 | Light Collectors | 299 days | Mon 1/1/18 |  | Thu 2/21/19 |  | 0%
9.2.1 | Development of next generation ARAPUCA technology | 237 days | Mon 1/1/18 |  | Tue 11/27/18 |  | 0%
9.2.2 | Testing of next generation ARAPUCA design | 245 days | Mon 2/26/18 |  | Fri 2/1/19 |  | 0%
9.2.3 | Analysis of next generation ARAPUCA test data | 219 days | Mon 4/23/18 |  | Thu 2/21/19 |  | 0%
9.3 | Photosensors | 257 days | Thu 3/1/18 |  | Fri 2/22/19 |  | 0%
9.3.1 | Sample-lots of candidate photosensors in hand, along with testing facilities | 133 days | Thu 3/1/18 |  | Mon 9/3/18 |  | 0%
9.3.2 | Testing of candidate photosensors and photosensor ganging | 222 days | Thu 3/29/18 |  | Fri 2/1/19 |  | 0%
9.4 | Electronics/Cabling | 300 days | Mon 1/1/18 |  | Fri 2/22/19 |  | 0%
9.4.1 | Development of optimized electronics readout and cabling design | 237 days | Mon 1/1/18 |  | Tue 11/27/18 |  | 0%
9.4.2 | Prototyping and testing of optimized electronics readout and cabling | 245 days | Mon 2/26/18 |  | Fri 2/1/19 |  | 0%
9.4.3 | Analysis of optimized electronics test data | 220 days | Mon 4/23/18 |  | Fri 2/22/19 |  | 0%
9.5 | TP/TDR | 324 days | Tue 1/2/18 |  | Fri 3/29/19 |  | 0%
9.5.1 | Establish preliminary criteria for PD technology down-select (included in TP) | 59 days | Tue 1/2/18 |  | Fri 3/23/18 |  | 0%
9.5.2 | SP-Photon Detector Technical Proposal - Submit for Internal Review | 0 days | Fri 3/23/18 |  | Fri 3/23/18 |  | 0%