## Slide 1
Steve Dixon
Project Management Group
18 April 2018
Conventional Facilities Status

## Slide 2: Outline:
Schedule
Procurements
GPP Candidates

## Slide 3: Schedule
Wetland Determination
(August 2018)
A/E Re-compete Complete
(September 2018)
EA Determination Complete
(October 2018)
CD-2/3a
(March 2019)

## Slide 4: Procurements
Site Prep Design
  Purchase Order 644172 Issued on 28MAR18;
  Kick Off Meeting Planned for week of April 30th
A/E Re-compete
  Acquisition Plan Under Review;
  Estimated to Require 6 months to complete;
Cryo Plant Building Preliminary Work
  Preliminary design is required to support Site Prep Design;
  Request for Proposal issued, due in early May 2018;

## Slide 5: GPP Candidates
Cryo Plant Building – Not a Likely Candidate
R. Ortgiesen Email, dated 06APR18

## Slide 6: GPP Candidates
MSS Electric Feed to MR
CUB Expansion
KRSS Electric Feed to MR
MR Pond Improvements
ICW to MR Area
Chilled Water Corridor
Booster LCW Upgrade
IB-4 SRF Upgrade
R. Ortgiesen Email, dated 06APR18
Next Steps:
Work with Randy Wielgos (FESS GPP Project Manager) to understand the scope and impact to PIP-II.

## Slide 7: END