## Slide 1
Cons Gattuso
Summer Shutdown Status
4/6/18

## Slide 2: Shutdown Window
Shutdown duration
  10 Weeks of tunnel work * (Switchyard Beam 12 weeks)
    July 9th – Sept 10th
  1 Week of contingency
    September 17th – September 21th
  1 Week of startup back to physics program (back to normal intensities) *
    September 24th – September 28th
* Both start time and duration are tentatively set
  Dependent on which jobs get done
  Readiness of major jobs
Sept 24th –Sept28

## Slide 3: Planning Stages
We will meet Once every two weeks
  Between January - May
We will meet weekly
  Between May - July
Planning Milestones
  Kick off meeting (Jan19th) Done
  Set Major Jobs (end of Feb.) Done
  Set Maintenance tasks (end of May) 90% Done
  Set Service Building Outages (end May/early June)
  Resource leveled schedule
    Primary (mid April) Done
    Working -In progress
    Final (Mid/end May)
    Trades still needs to be looked at….

## Slide 4: Current Working List of Major Jobs
Linac
  Marx Modulator installation
    Station 4 and 5
  Tank 3 quad replacement
Booster
  2nd harmonic RF cavity
BNB
  Tritium mitigation
    Berm Cover
NuMI
  Raw system upgrades
  Pretarget window replacement
MI/RR
  Sextupole Stand and 1/3 Harmonic correction elem. installation
  8 GeV line 4 multi wire installation
  Remove/repair/reinstall Q102
  Replacement/repair of the MI Lambertson at 402-3

## Slide 5
F-Sector
  P3 line vacuum modification.
  Fix bus leak - F44
  Fix bus leak - F29
Switchyard/Transfer Hall
  Removal/Replacement of F48-1 Quad
  Removal/Replacement of H201-12
Muon Campus
  M4 line installation
    Vacuum system from 906-927
    Cable pulls for 927-936
      vacuum/power
  TLM system
    Rings and Transfer line

## Slide 6: The schedule
Assumption made
  8 hour days 5 days per week
    6 hours of work in the 8 hour day
  Rolling crew support

## Slide 7: What Remains To Be Scheduled
Power Outage/Feeder Maintenance (End of May/June)
  Substation outages on and off site have been set
  Working on individual buildings/feeder
Support Group Needs/Outstanding items
  All alignment request need to be in by the end of May
  Request to EE support to disconnect elements (Monday of next week)
  T&M request need to be in by the end of next week
    Add the Phrase “Summer Shutdown” to the Job Title
    Currently unknown how long it will take to get a job through the system once submitted…
      We are working closely with Procurement office on this.
      Please tell me when you submit a T&M request

## Slide 8: Scope of T&M Work Requested (Approx. Labor Only Cost)

## Slide 9: Misc
Shutdown Work List
  A Shutdown work list has been opened
    We have started adding jobs to the work list
    Please add somewhere in the title or description the words Summer Shutdown
      It makes the searching for task easier
Meetings with MSD Crew leaders and Engineers will occur next week.
  Work planning at ALL levels
    HA/ALARA/Global Work flow