## Slide 1: ProtoDUNE-SP Commissioning Planning
Gina Rameika
Detector Activation Preparatory Meeting
24 May 2018

## Slide 2: Detector Commissioning Planning
Defined Planning Periods
  Prior to manholes closed : June
  Cryostat gas purge begins : July
  Cryostat/TPC cool down begins : July
  Cryostat filling begins : ~ early August
  Cryostat filled with LAr : ~ mid-late August
  Beam arrives : end of August
  Beam Running

## Slide 3: Detector Commissioning Documents
Detailed Documentation and Procedures: DocDB#8288*
  Well defined sequence of steps
  Prerequisites, condition of other systems
  WHEN
  Who (expert, non-expert, expert + helper)
  How much time is needed
Bird’s Eye View of the full picture
  Google doc
  Ones that we have in hand (Posted for LBNC meeting)
  Can/should be replaced/maintained by the groups themselves.

## Slide 4
Detector Commissioning teams defined for :
  High Voltage
  APA Wire Bias
  Cold and Warm electronics
  Photon Detectors
  Data Acquisition
  Detector Controls System
  Temperature Monitoring
  Purity Monitoring
  Gas Analyzers
  Cameras
  Beam Plug
  Grounding and shielding
Requested :
Contact person
Expert list
Tasks and procedures
Responses have started
DocDB#8288

## Slide 5: Google Doc Spreadsheet
Created a Google doc spreadsheet into which each system team can enter tasks and plans so that we can allocate time and resources for installation and commissioning tasks for each system.
System contact person has edit permission
Anyone with the link can view; will send to the mailing list for this meeting