## Slide 1
Cons Gattuso
Summer Shutdown Planning
5/25/18

## Slide 2: Shutdown Planning
  Duration
    10 weeks for accelerator complex
    12-13 weeks for Transfer Hall and beyond
  July 7th Saturday (we are 31 working days way)
    00:01 - Beam Off
      Machines transitioning to shutdown mode
  July 7th -8th Saturday/Sunday
    0700 – Completion: Rad Safety
      Radiation Surveys
        Linac, Booster, MI8 Line, Main Injector/Recycler, F-Sector, MC-1
      Enclosures re-cored to shutdown access keys
        Booster, Main Injector/Recycler, F-Sector, MI65
        After Rad Survey: FESS may continue re-lamping under supervised access
  July 9th Monday(in the tunnel) (we are 31 working days way)
    0600- 0800: Fire Techs testing in MI tunnel
    0800 – Keys available. RWPs will be set up in the Huddle.
    Machine Shutdown Coordinators
    Please submit long term key request to Mary Kohler

## Slide 3: Crew Briefings
Mechanical Crew Briefings will be occurring next week ……
  Meet with crew leaders
    Discuss work that each crew will be doing
      Installation Drawings
      Crew makeup
      Work strategy
    Discus the work flow
      Alternative paths to our final goal
    Equipment needs
    Paper work to acquire Trades should be in this point time
      Iron workers
      Pipe Fitter
      Electrician

## Slide 4: What Remains to be Scheduled
Power outages
  Global and local
  We should have a plan in place by the end May
MI tunnel
  MI 52 Lambertson Bake
    Concerns about hydrofluorocarbon contamination
  MI 52 Septa changeout
    Concerns about hydrofluorocarbon contamination
Safety system testing
  Across all machines
General Maintenance Schedule

## Slide 5: T&M
We have ~$650K in various T&M trade requests for this shutdown
  Bulk of the request are for electricians ~$350K
  Of the known jobs only ~40-45% have been submitted
  We have P.O.’s for ~20% of our tasks
  And releases for about 8% of our tasks
  The average length of time it took to get a release 2 weeks ago was 3-4 weeks
  Now we believe we have gotten the process down to 2-3 weeks
  Several of our T&M request have been denied ( determined that they should be fixed priced)

## Slide 6: Working Planning
Shut down job submissions
  Please enter your jobs in the electronic work list
    Use SUMMER SHUTDOWN 2018 in the title or description to help us find the jobs
We are at the point that adding additional jobs to the shutdown without impacting the length has passed. The pattern is full…..
  Rescheduling jobs within the shutdown can still done to a limited level….
    AS SOON AS YOU KNOW we may a problem let me know so we can shuffle resources accordingly …
We will also be hearing from our Division Head and ESH&Q
  Division Pre shutdown All Hands meeting

## Slide 7
Thank you

## Slide 9: Proton Source Shutdown Work list
RIL
Source maintenance
Einzel Lens maintenance
RFQ maintenance
General maintience
Linac
LRF 3 Quad drift tube replacement
Marx modulator project
  Planning to install 2, LRF4 and 5 stations
    Duration ~6-7 Weeks for the removal of old and installation of new
LE tasks (performed by Linac techs)
  Modulator/driver maintenance
  Inductrol maintenance
  Water skid maintenance
HE tasks (performed by Linac techs)
  CS & PFN maintenance
  PFN cap bank maintenance
  QPS PM
  Water skid maintenance
  Heat exchanger maintenance
Booster
BRF18 Tuner repairs
Perpendicular RF cavity installation
General Maintenance
  Power supplies
  Cooling Systems
  Vacuum

## Slide 10: Main Injector/Recycler
MI
  8 Gev line
    Ion pump Maintenance
      ~1-2 weeks
    Vacuum leak check
      ~1-2 Weeks
    Multi wire replacement (4)
      ~2 Week
  General maintience for MI/RR
    ~2-3 weeks
      Tunnel and service building
  Abort line
    MI40-3 Lambertson water leak repair/magnet change out
    Replace abort line beam pipe
  Q102 magnet removal/reinstallation
    Water leak repair
  MI 52 (not yet scheduled)
    Lambertson Bake
    Septa replacement
RR
  Recycler Sextupole/Skew Quad stand change out
    ~5 weeks
  Abort line Cable pulls
    Gap clearing kicker
    PMT system
    Abort line high voltage cable for loss monitors
  Higher order Sextupoles correction magnets
    Stands
    Magnets
    Cable pulls
    Power supply system

## Slide 11: External Beam line
P3 rough vacuum
  F2 House IP to Turbo Station upgrade (~2 weeks)
    Run 4" vacuum pipe from service buildings down stairwells to tunnel
    Install Roots blower stations in service buildings, one per house.
    Switch controls over to Tevatron CIA crates, rename parameters
    Remove and cap ion pumps.
F48-1 3Q120 replacement
  Magnet being swopped out to give the MI a viable spare.
    ~1 week to replace
Enclosure C
  H201-12 EPB magnet
    Has a water leak that can’t be fixed in the tunnel and the magnet will be changed out.
F-Sector Heat exchanger Cleaning
  F1/2/3/4
Repair water leaks on magnets and buss
  F44 and F29
MS2 LCW system Cooling tower repairs

## Slide 12: External Beam line (continued)
NuMI (~10-12 weeks)
  Target replacement
  General maintience
    Dehumidifiers
    Replace Filter and water in the Absorber and Decay pipe cooling system
    Drain tile cleaning
    Ext.
  MI-65 RAW system upgrades for 1MW operations
    Old ejector pump and associated piping must be upgraded
    The old 10 hp pumps must be replaced with new 15 hp pumps. Piping must be modified to make room for the bigger pumps, an additional pressure controlling by-pass loop must be installed on the piping.

## Slide 13: Muon Campus Work
  Mu2e work
    M4 line installation ( first half to shielding wall)
      Vacuum system and cable pulls installation (6-7 weeks)
    TLM system
      Delivery ring
      Transport
      Extraction line
      Abort line
    Collimator installation
      M2/3 Line
    Wedge momentum collimator in M5 line
    Delivery ring general vacuum maintenance
    Instrumentation Repair M4/5 Shared line
      PWC and IP’s ~ 1 week

## Slide 14
More to come next week…..