## Slide 1
Status & Plans
Eric James
Far Detector Technical Board Meeting
June 28, 2018

## Slide 2: Path to TDR
Nine months remaining to produce TDRs by April 1, 2019
Next big step is to have a full WBS including initial cost estimates (with hopefully a much more complete indication of assigned institutional responsibilities) by the next Resources Review Board (RRB) meeting on September13-14

## Slide 3: Initial Goal
Initial goal was for each consortia to produce an initial cost estimate for their sub-system in spreadsheet format by the end of this month (status reports at this meeting)
The plan is to go through a period of review and iteration with the goal of having finalized estimates by mid-to-late July
Will work to arrange another round of phone calls with consortia leadership teams

## Slide 4: Final Step
Once the overall cost estimates for each sub-system are signed off on, the final step will be to transfer cost information into the lowest-level WBS items
May require some further iteration of WBS structure to ensure reasonable granularity (no single item should have assigned costs greater than a few hundred thousand dollars)
Note that consortia should continue to iterate on WBS format with Steve in preparation

## Slide 5: End Game
Would like to have a first pass of WBS with assigned costs by Thursday, July 26th.
Allows for a couple of weeks of additional review/iteration prior to these being passed to NCG in mid-August

## Slide 6: Requirements
(From LBNC) The collaboration is advised that it should maintain a single, centralized, official set of requirements, whose content is owned by the EB.”
Our goal is to produce a set of requirements that can be approved by the EB in late July prior to the next LBNC meeting (Aug 1-3)

## Slide 7: Process
Steve and I are working to put something together based on requirements information contained within the Technical Proposal (Interim Design Report) and the material provided by the consortia back in February
We will need to iterate on this with the consortia leadership teams over the next few weeks (want to pass to EB in advance of proposed July 26th meeting)

## Slide 8: Food for Thought
We need to present a plan for future ProtoDUNE operation (beyond this year) to CERN SPSC at its upcoming October meeting
It has been suggested that we might want to conduct integration testing of Module 0 (first production) components in the ProtoDUNE cryostats in 2020-2021
How would this fit into consortia plans?