## Slide 1: LBNC Report to the PAC
David MacFarlane,
LBNC Chair
Jul 16, 2018

## Slide 2: Current membership
Members
Consultants for IDR
Chair, David MacFarlane (SLAC)
Sampa Bhadra (York)
David Charlton (Birmingham)
Amber Boehnlein (JLab)
Joel Fuerst (ANL)
Cristiano Galbiati (Princeton)
Beate Heinemann (DESY)
Patrick Huber (Virginia Tech)
Bob Laxdal (TRIUMF)
Ted Lui (FNAL)
Naba Mondal (TIFR)
Jocelyn Monroe (Royal Holloway)
Marco Pallavicini (Genova)
Tom Peterson (SLAC)
Kevin Pitts (UIUC)
Jimmy Proudfoot (ANL)
Kem Robinson (LBNL)
Bob Tschirhart (FNAL)
Red = new
Tom Shutt (SLAC)
Eric Dahl (Northwestern)
Adam Para (FNAL)
Alan Bross (FNAL)
Hugh Lippincott (FNAL)
Transitioning to Hugh Montgomery as the next LBNC chair, overlapping during the next two LBNC meetings

## Slide 3: Intended outcomes for RRB
Provide credible validation of TDR and monitoring of project for RRB and sponsoring agencies
  Gateway for international agencies to move forward with their funding decisions with confidence that the whole project has a valid and credible plan: all partners have assurance that they are contributing to what will be a successful scientific outcome & the other partners will deliver on their parts as well
  Neutrino Cost Group (NCG) an integral component for cost/risk/schedule as part this gateway process
  Important that there be a trust relationship between LBNC and RRB: confidence that insightful and accurate assessment is being provided

## Slide 4: Continuous oversight: face-to-face reviews and ongoing contacts
Typically plan for 3-4 face-to-face meetings per year:
  June 22-24 (CERN) and Oct 26-28, 2017 (SURF)
  Feb 19-21, 2018 at Fermilab: Progress towards TP
  May 22-24, 2018 at Fermilab: First look at TP
  Aug 1-3, 2018 at Fermilab: Final report on TP
Between meetings, referee subgroups keep up-to-date through regular contact with LBNF/DUNE POCs
  Develop and sustain a high level of referee familiarity and understanding of the assigned systems(s)
  Provide follow-up and/or progress reports on intermediate time scales for issues identified during regular LBNC reviews
  Facilitate preparation for regular LBNC reviews, such as advance discussion of draft documents and development of agendas and focal topics

## Slide 5: Context and DUNE Strategy
DUNE embarked on production of a “Technical Proposal (TP)” (now called Interim Design Report (IDR)) in summary 2018 as a stepping stone to a full blown Technical Design Report in summer 2019
  Substantial organizational and collaborative effort by the detector consortia
  Opportunity for LBNC to provide early assessment and feedback towards any course correction
Scope: goal is Far Detector TDR by summer 2019, conceptual design only for the Near Detector (TDR a year later)
Challenge: Dual Phase organization not yet mature and technical foundation not as well established
  LBNC suggested a separate timeline for DP (precedent from LHC upgrades), but this was not adopted by the DUNE collaboration

## Slide 6: Intended approach to TP and TDR reviews
Dec 2017: Establish guidelines for TP, TDR, cost and risk documentation
Mar 2018: Review progress on TP on intermediate timescale: are the consortia working with demonstrated leadership
May-Aug 2018: Pair of face-to-face meetings to review written TP, allow for Q&A, and production of synthesized compact report together with NCG
  Reorganized referee subgroups maintain close contact with and focus on relevant technical subsystems before & after TP
  Overlap in membership between NCG & LBNC, to ensure close coordination of review sessions and technical analysis
Similar process, displaced by a year, for TDR review, with now a year of practice for DUNE and LBNC members

## Slide 7: Subgroup organization for TP review
Number | Topic | Subtopics & Consortia
1 | DUNE-SP | APA
 |  | DAQ
 |  | ElectronicsSP
 |  | HV
 |  | PhotonSP
 |  | Slow Controls and Cryo Instumentation
 |  | Calibration & Monitoring
 |  | protoDUNE-SP CE & TPC
 |  | protoDUNE-SP DAQ
 |  | DUNE-SP schedule & planning
 |  | protoDUNE-SP TPC systems, schedule & planning
Number | Topic | Subtopics & Consortia
2 | DUNE-DP | CRP & TPC systems
 |  | DAQ
 |  | ElectronicsDP
 |  | HV
 |  | PhotonDP
 |  | Slow Controls and Cryo Instumentation
 |  | Calibration & Monitoring
 |  | protoDUNE-DP technical, schedule and planning
Number | Topic
3 | DUNE physics, simulation & reconstruction
4 | DUNE Computing
5 | LBNF/DUNE cryogenics
6 | LBNF management, schedule and planning
7 | LBNF/DUNE interfaces
8 | DUNE management, schedule and planning
9 | Beamline design and optimization
10 | DUNE Near Detector
May need to draw on external experts as needed

## Slide 8: Detailed guidelines provided to DUNE for TP, TDR and review process
Laid out a multi-phase approval process:
  Step 1: Technical Proposal: overall scope, preliminary design and cost for the DUNE Far Detector program defined and documented by DUNE, with the possibility of detector options.
    Consortia should be clearly defined in terms of the scope and organization at the time of the TP
  Step 2: Technical Design Report phase: detailed expectations laid our for the content, expect only conceptual design for ND at the time of the FD TDR
  Step 3: Final design and construction readiness of the major detector components will be prepared for review, likely on different timelines for different systems, by the LBNC and NCG
  Step 4: Operational Readiness Review: Evaluate the capability of the completed detectors to provide the expected performance and mark the end of the construction phase.

## Slide 9: Charge for May review: IDR related questions
Are the technical requirements for system clearly stated?
Do the technical requirements connect well to the physics requirements of DUNE?
Is the system accurately and clearly described, keeping in mind the criteria that a science agency specialist should understand the introductory section and a professional member of the HEP community should be able to follow the body of the text?
Has the system been demonstrated to meet its technical requirements, and if not, what are the deficiencies?
Is the level of detail appropriate? Are any key elements missing? Are any components described in too much detail for this phase of the experiment?
Agenda link

## Slide 10: Charge for May review
Are project related activities—management structure, facilities, interfaces, safety, quality assurance, integration/installation, and high level schedule—described well enough in the TP to show that the complete delineation of these activities needed for the TDR is on-track?
Is there a clear decision pathway laid out to address options and unknowns between now and the TDR? Are decision criteria understood and can the required information or process realistically be executed on the proposed timeline?
Are risks to the subsystem project identified and are mitigation strategies plausible?
Are there aspects of the subsystem design that will not be informed by previous experience or prototypes and therefore present risks to the project design and/or execution?

## Slide 11: Charge to May review: other areas
DUNE-SP
  Status and schedule of the 3 ASIC front-end design.
  Describe the plans for the protoDUNE Testbeam measurements and plans beyond the testbeam.
DUNE-DP
  Update on identifying HV issues with the 1x1x3
  Update on design and testing for protoDUNE-DP CRPs
  Update on schedule and planning for protoDUNE-DP
DUNE Physics, Simulation & Reconstruction
  Describe the status of the physics studies needed to define the system requirements adopted by each of the consortia, the resulting list of requirements, and how the physics-driven requirements are transmitted to, and used by, the consortia.

## Slide 12: Charge to May review: other areas
  Describe the physics studies guiding the Near Detector design decisions and the ND technology decision process.
DUNE Computing
  Outline of the factors that will impact the computing model;
  Outline the lessons learned from the experience of other LAr TPC experiments wrt software and computing;
  Outline the state of readiness for ProtoDUNE data collection? What are the plans to use ProtoDUNE data to influence the computing model?
LBNF/DUNE Cryogenics
  Detailed commissioning plan for protoDUNE cyostats and cryogenic systems
  Update on equivalence approach in lieu of cryostat pressure testing

## Slide 13: Charge to May review: other areas
LBNF Management, Schedule & Planning
  Provide an overview of LBNF progress and planning, with particular attention to aspects of the project that could impact the DUNE project and schedule
  Provide an update on risks, with particular attention to those risks that could impact the DUNE project and schedule
LBNF/DUNE Interfaces
  Discuss protoDUNE lessons-learned implications for definition and control of interfaces for DUNE interfaces and project office management
  Discuss status of internal and LBNF-DUNE interfaces at the time of the TP and plans for maturing these definitions and plans by the time of the TDR

## Slide 14: Charge to May review: other areas
DUNE Management, Schedule & Planning
  Update on implementation of new management structure, including new Executive Board;
  Review plans for, and scope of, the international project office;
  Review document covering construction and installation lessons from protoDUNE and earlier prototypes;
  Report on progress and status of the ND conceptual design development;
  Update on collaboration membership and development plans for funding matrix

## Slide 15: Charge to May review: other areas
  Discuss lessons learned from the assembly and commissioning of protoDUNE-SP for planning of the FD design and development effort
Beamline design and optimization
  Discuss revised plans for restarting beamline design work on a timescale commensurate with the fall 2019 CD 2/3b review
  Discuss risks and buildability issues raised by the beamline optimized solution proposed by DUNE
DUNE Near Detector
  see #3

## Slide 16: Format of May meeting
700-page IDR was delivered to the LBNC on the Friday before the review: little or not chance to read in advance
Review agenda provided for a complete set of plenary presentations from consortium leadership as an overview of the IDR
Instructions provided to speakers to guide content
Full breakouts held with FD-SP consortia; DP delayed until a later date (now planning face-to-face breakout at CERN, Aug 27-28)
Preliminary responses to charge questions provided in interim report
Committee asked to read IDR by end of June and develop a set of follow-up questions for August review (currently being collected)

## Slide 17: Instructions to plenary speakers
Give an executive summary of the content of the relevant part(s) of the IDR, including a high-level overview of the main physics drivers for the system design and the corresponding critical design parameters;
Identify the main unresolved design or construction issues and uncertainties, risks to the design or project execution and gaps in planning as they exist now at the time of the IDR;
Identify the decision pathway, decision criteria and timeline to resolve these issues by the time of the TDR;
Identify the state of interface (internal or external) definitions and plans for defining these by the time of the TDR;

## Slide 18: Instructions to plenary speakers
Describe the additional tasks that need to be executed by the time of the TDR, and the associated plans for taking these steps;
Provide an overview of the project execution plan and main organizational partners in the plan.

## Slide 19: Feedback and highlights from recent reviews:
May 22-24 meeting at Fermilab
  Produced a 50-page written closeout report
  Organized around IDR subgroups (not all up able to report) with findings, comments, recommendations, and status of previous recommendations
  Executive summary provides a broad overview and highlights main comments and recommendations

## Slide 20: Context: fast paced effort that has come very far in 2 years!
Established of a new, vigorous and truly international science collaboration DUNE
Further strengthened and defined the LBNF organization
Developed suitable management structures, interfaces and oversight for LBNF and DUNE
Developed science strategy satisfying P5 requirements and achieved CD-1R approval for LBNF/DUNE project
Completed preliminary design work & planning for LBNF far site construction & passed DOE CD-3a review in Dec 2015 with flying colors
  Gateway to DOE committing substantial multi-year ($300M) construction funding for far site development
Establish protoDUNE organization and planning to validate DUNE engineering design

## Slide 21: Overarching impressions from May
Overall the LBNC is impressed by the progress being made by the DUNE Collaboration
  Mounting an ambitious project to construct protoDUNE-SP and (soon to come) protoDUNE-DP
    Represent critical engineering tests at 1/25th scale of the designs for DUNE far detectors, as well as invaluable opportunities to calibrate the response of the far detector TPCs with particle beams.
    CERN has continued to provide enormous support for these projects, particularly the cryostat technology development and the cryogenics systems for these devices, and the larger development of the Neutrino platform.
  Assembling an ambitious Technical Proposal for the DUNE far detectors, as the first major deliverable from the recently formed detector consortia.

## Slide 22: Overarching issues and recommendations for the next step of preparing a full Technical Design Report
Unclear mechanisms for identifying, studying and resolving cross-cutting topics that transcend individual consortia, or which lie at the interface between hardware design and physics requirements;
Concern about the strength of the central integration and technical coordination team and its ability to develop and implement standards across a relatively new collaboration with diverse international experience and little in the way of established standards;
The lack of a comprehensive and well-documented connection between physics requirements and their connection to technical system requirements, an obvious example of an area requiring strong coordination between detector and physics teams; and

## Slide 23: Overarching issues and recommendations for the next step of preparing a full Technical Design Report
Concern that obtaining maximal benefit from the protoDUNE exercise requires a clear and tight focus on planning for and obtaining key engineering and scientific validation of the designs, while operating in what is essentially a full time commissioning mode, where operational conditions may be constantly changing without the benefit of significant prior experience.

## Slide 24: Cross-cutting topics
The organizational connections between the physics activity and the data collection and processing coming imminently from ProtoDUNE should be stronger. The current separation of these activities does not appear to be optimal.
Tighter coupling between physics and software activity and the detector consortia would facilitate a broader understanding of the connections between key detector performance parameters and physics goals.
Mechanisms to review specification and/or significant design changes need to be developed, especially changes which may impact overall performance and physics capabilities. Changes to the Photon Detector System may provide an early test case for this.

## Slide 25: Cross-cutting topics
DUNE management is encouraged to develop further the organization of cross-cutting horizontal activities such as performance, software, computing, calibration, alignment, eventual data quality monitoring and so on, bringing together expertise from across the consortia and collaboration. Linkages are not as developed as they need to be, and a different organization may facilitate this.
Examples:
  Light collection system design and supernova physics impact
  TPC calibration systems and feasibility of implementation: perhaps the most difficult of the cross cutting topics the Collaboration must face

## Slide 26: Technical Coordination
DUNE technical coordination is responsible for project engineering, installation planning and execution, operation of the far detector integration test facility, and common infrastructure.
Post TDR, the organization includes project support, integration, infrastructure, integration and test facility, and installation groups.
Overall the LBNC is concerned that the path to resourcing and filling out the technical coordination team is lengthy and uncertain.
  We note that the bulk of the organization will not be in place until after the TDR and it is not clear to us that the team is sized appropriately, e.g. on the basis of benchmarking from other large-scale international detector projects.

## Slide 27: Technical Coordination
  The plan is for the Technical Coordination team to be resourced from a combination of host lab and common collaboration resources.
  The common collaboration resource component may take some time to realize.
  We expect that a strong technical coordination team will be needed during the preparation of the TDR itself.
DOE has now invited a proposal from DUNE/Fermilab to grow a technical coordination team near-term

## Slide 28: Connecting physics and technical requirements
LBNC strongly encourages the Collaboration to develop a clear connection between the physics goals of the experiment and the technical design requirements.
  Many of the plenary speakers who summarized the technical systems described in the TP could not provide a crisply articulated argument about physics drivers and were generally unable to identify such drivers during questioning.
  The Collaboration should maintain a single, centralized, official set of requirements, whose content is owned by the EB. This content should be augmented with the expected impact on the project of validation tests of the specific requirements using ProtoDUNE and a “Motivation/Consideration” field should contain summary arguments leading to the planned performance requirement (reference to documentation).

## Slide 29: Benchmark from Dave Schmitz’ talk

## Slide 30: Connecting physics and technical requirements
Arguments in favor of developing such a clear and simple explanation of technical requirements as a best practice:
  (1) requirements very often become schedule and cost drivers, with implications for curtailing the overall cost of the experiment and demonstrated maximal effectiveness of limited funding on scientific output;
  (2) guiding value engineering, which will only come into play once the project passes from the present conceptual phase to a fully engineered design; and
  (3) allowing sound technical priorities and plans when confronted by decisions during the design and development phase, or later in the project when project execution encounters difficult budget, schedule or technical problems.

## Slide 31: Connecting physics and technical requirements
The LBNC will expect clear statements of the flow down from physics sensitivity to technical requirements at the time of the TDR and sensitivity analysis for key parameters, identified with some judgement by the Technical Coordination team.
Recommendation: Report to the next LBNC meeting a summary of the main performance drivers, as for example listed in this meeting in the talk “DUNE-SP Overview, Schedule & Planning”, with explicit couplings to the primary DUNE physics goals. Summarize which of these performance indicators will be established or explored by ProtoDUNE, and which will remain untested.

## Slide 32: protoDUNE experience and implications for engineering design
A detailed presentation on the ProtoDUNE-SP commissioning, operation and data analysis plan was made by Flavio Cavanna. An internal ProtoDUNE-SP Data Exploitation Readiness Review was also conducted by DUNE and Fermilab SCD on May 10-11. The report from the review panel was made available to the LBNC in draft form.
The LBNC concurs with recommendations made there concerning establishing a schedule for remaining work on the DAQ system, which is considerable.
  From the long list of measurements and results expected from protoDUNE-SP would benefit from establishing priorities based on high-level strategic goals for protoDUNE-SP, particularly since operations will probably be closer to a full time commissioning mode without the benefit of routine operational experience. l

## Slide 33: protoDUNE experience and implications for engineering design
  This will make it challenging to address the full list of measurements and studies, since some may be quite exploratory in nature and therefore uncertain in duration.
  Finally, we are concerned by the establishment of a whole new organization (the Data Reconstruction and Analysis (DRA) group) with uncertain connections to the existing physics and computing organizations or the hardware consortia, which does not appear to be optimal
Examples:
  Validation of CFD calculations in the light of protoDUNE cryostat measurements
  Validation of TPC engineering design and TPC performance

## Slide 34: SBN issues (2 excellent talks provided at May LBNC meeting: recommended to the PAC)
Findings:
  A common software framework, LArSoft, is used by the three SBN experiments, SBND, MicroBooNE and ICARUS, facilitating code and algorithm sharing.
  Frequent and regular joint reconstruction and analysis meetings, and longer workshops, are held between all three SBN experiments.
  Common meetings are also held regularly between experiments on various common hardware and operations aspects, such as DAQ, slow controls, and so on.
  The SBN program is providing hands-on training to technicians, engineers and physicists in the realities of LArTPC commissioning, operations and software.

## Slide 35: SBN issues (2 excellent talks provided at May LBNC meeting: recommended to the PAC)
Findings:
  MicroBooNE, as the experiment currently with data, has made most progress on reconstruction and analysis tools – these are being made available to the other experiments in the LArSoft framework.
Comments:
  The linkages and interactions between the SBN experiments, as presented, are impressive and well exercised so far.
  The committee believes such strong connections should continue also through the operation and analysis phases of all the experiments.

## Slide 36: SBN issues (2 excellent talks provided at May LBNC meeting: recommended to the PAC)
  The natural exchange – indeed overlap - of individuals between experiments is also a strongly positive feature that the panel supports. This also is important between the SBN experiments and DUNE.
  The engagement of SBN experiment experts in reviewing the protoDUNE program is a very positive step.
  The LBNC encourages the SBN experiments also to flag areas of concern, as well as successes, in future interactions with the committee.
No recommendations
  Previously heard about plans for joint coordination between the three collaborations

## Slide 37: Issues for discussion with PAC
Two possible roles for PAC:
  Review and comment on process by which the LBNC is executing its scope and charter
  Comment on and (potentially) reinforce recommendations and comments from LBNC
  Role with regard to the SBN program (concern about double jeopardy)
Issues from the perspective of current LBNC chair
  Recent move to limit review and scope with regard to LBNF
    Argument: LBNC reports to RRB, which is responsible for DUNE (not LBNF); limiting scope helps focus LBNC effort
    Chair believes that, under any circumstance, the LBNC needs to maintain visibility into LBNF to the extent that it potentially impacts DUNE (both known interfaces and unknown threats)
    Concern: membership no longer supports insightful review of LBNF

## Slide 38: Issues for discussion with PAC
    Fermilab should maintain technical oversight of LBNF by some means (could be a separate group), in order to avoid surprises (SPAC is not technical, primarily management)
    Lack of clarity here is confusing to LBNC, LBNF, and DOE
  Some evidence that LBNC members are saturated and not providing as insightful advice as they could
    Worried that this will get worse as the NCG becomes active, since some overlap of service will be needed
    Risk is the primary driver for cost uncertainty, but risk is primarily a technical judgement by the LBNC who then need visibility into mitigation strategies (interface with NCG)
  DUNE collaboration:
    Still evolving organization structures for decisions; general concern about communication between physics and detector groups
    Still concerned about disjoint FD consortia, with no overarching structure

## Slide 39: Issues for discussion with PAC
    Who owns monitoring of international milestones and pays attention to risks in maintaining them?
    Some cases where DUNE management may not be as supportive of recommendations (physics flow down) as they could be
    Formation of consortia possibly a missed opportunity: new groups are not strongly encouraged as they might have been, no real leadership change, not clear guidance and expectations given to consortia leadership in terms of developing a “collaborative spirit”
    Similarly EB may only be effective to the extent it is used effectively: requires preparation, planning, and clear establishment of expectations for EB members
    US part of DUNE is not being as coherently organized as it might be and this may be a problem for DOE
    Have so far taken an accommodating attitude towards the dual phase part of the IDR: how long should this continue? Collaboration management want space to work problem

## Slide 40: Summary
LBNC is in the midst of a detailed review of the TP and has provided from initial feedback pending further review in August
  Guidelines provided to DUNE for both TP, TDR and cost/WBS/risk information for NCG
In addition to a number of specific concerns about physics justifications and challenges in addressing cross-cutting issues, there are a number of concerns related to LBNC scope, interaction with the PAC, and organizational questions about DUNE that remain and PAC advice would be helpful