## Slide 1: PIP-II Risk Analysis: The View From India
S. C. Joshi, RRCAT
Srinivas Krishnagopal, BARC
IIFC Technical Coordinators from DAE, India
13 July, 2018

## Slide 2: General Observations on International Collaborations
International collaborations are characterized by plurality:
  Of countries, interests and cultures
  Of processes, practices and perspectives
In this subjective sea there is one objective island we should aim for:
  Deliverables
To get there, we need good communication and enlightened mutual interest.

## Slide 3: The IIFC Collaboration
India is interested in High Intensity Superconducting Proton Accelerators (HISPA) for building a Spallation Neutron Source (SNS) and an Accelerator Driven System (ADS). To this end the Indian Institutions and Fermilab Collaboration (IIFC) was formulated with the following goals:
“The HISPA design, technology and supporting infrastructure knowledge transfers from DOE to DAE are the planned in-kind contributions from the United States.”
“The engineering resources, design, manufacturing, and supply of HISPA accelerator hardware from the DAE to DOE, amounting to a maximum total of $200 million (direct cost in US accounting in terms of 2012 US dollars), are the planned in-kind contribution from India over the years 2013-2022.”
(This includes the PIP-II R&D as well as construction phases)
IIFC will enable us to get proven HISPA technology, train our scientists and engineers, and actually develop essentially all individual components of a HISPA system (even if for a lower intensity than we need).

## Slide 4: General Risks
Export control
There are many areas in which components for hardware being developed in India (under IIFC), are being denied because of export-control issues in the US. [Eg.: RF amplifiers, LLRF] This can lead to delays, short or long, in deliverables, and in the worst case to cessation.
[Some solution has been discussed between DAE and DoE. Need to see the implementation.]
Third-party IPR
HISPA technology transfer to India is restricted because much of the development is done in private industry in the US and there are issues of third-party IPR. As a result, DAE labs would be required to spend additional resources, which would result in delays in the schedule of DAE deliverables to DoE.
Unsatisfactory conclusion of PIP-II R&D phase
If the Government of India is dissatisfied with the outcome of the R&D phase, it will not give approval for the construction phase.

## Slide 5: Technical Risks: External
Three main categories:
Delays in receiving specifications (FRS, TRS) from Fermilab. [Eg.: LLRF, RFPI]
Delays in receiving designs from Fermilab, which are needed to commence fabrication. [Eg.: Couplers, SSR1 tuners]
Delays in receiving other information or materials from Fermilab, that are essential for proceeding on design or fabrication. [Eg.: SSR2 cryomodule, SSR2 cavity]

## Slide 6: Technical Risks: Internal - 1
Dressing of cavity with the new type of infrastructure being developed at RRCAT
System integration and commissioning of HTS at RRCAT
Establishing processing methodology for achieving the required Accelerating and Quality factor for five-cell 650 MHz cavity
Consistency in procurement of Niobium material for series production

## Slide 7: Technical Risks: Internal - 2
Delays in getting prototypes fabricated to TRS
[Note: Important that TRS are well formulated.]
Delays in imports that are not denied
Delays in identifying industrial partners and getting them up to speed

## Slide 8: Summary
IIFC is proceeding well
Successful completion of the R&D phase is crucial
The major risks remain export control and third-party IPR, which cannot be addressed by scientists and engineers
Transparent and quick communication is essential for addressing the external risks
We will work on mitigating the internal risks as much as possible