## Slide 1: Workshop Organization, Roles and Responsibilities PIP-II Risk Management Workshop July 12-13, 2018

## Slide 2: Overview
Workshop Organization, Roles and Responsibilities
Risk Identification Process
Risk Assessment Exercise

## Slide 3: Workshop Format
Opening Session
Risk Identification and Assessment Sessions
  Conventional Facilities
  Accelerator Systems, Installation & Upgrades
  SRF and Cryo Systems
  Project Management Systems
Risk Management Summary and Wrap-up

## Slide 4: Keys to a Successful Workshop
This is a Workshop
  Participative/open/active
Your input is the key
  Subject Matter Experts (fresh eyes)
  PIP-II Technical Team (deep knowledge)
What we are asking of you is HARD!

## Slide 5: Risk Management Process
In a Nutshell
Formal and structured process
Anticipating and planning for potential problems and opportunities
Better understand and control project outcomes
Risk is an uncertain event that, if it occurs, has a negative effect on a project objective

## Slide 6: Risk Management Process
Risk Management Planning
Risk Identification
Qualitative Risk Analysis
Quantitative Risk Analysis
Risk Response Planning
Risk Monitoring and Control
Source: PMI PMBOK
Risk Management Process

## Slide 7: DOE Risk Management Process
INITIATION
DEFINITION
EXECUTION
CLOSEOUT
CD-0
CD-1
CD-2
CD-3
CD-4
Risk Planning
Qualitative Risk Identification and Analysis Process
Risk Response Planning, Monitoring and Control
Quantitative Risk Analysis
Risk Documentation and Communication
Lessons Learned

## Slide 8: Risk Identification
In a nutshell
Identification, categorization and documentation of a comprehensive, non-overlapping set of “risks” (potential problems)
Events that, if they occur, have a negative effect on a project objective (cost, schedule, technical)
Note that this is different from uncertainty that might also change project cost or schedule, but is not attributed to an event

## Slide 9: Risk Identification
Risk Statements
Consist of a defined event and its impact
Represent one risk event
Enhance the next step of analyzing likelihood and impact

## Slide 10: Risk Identification
Risk Statements
  “If <RISK EVENT> happens, then <CONSEQUENCE> will <IMPACT> <PROJECT OBJECTIVE>.”

## Slide 11: Risk Assessment
One-of-a-kind projects rely on subjective risk assessments for modeling
To make good assessments we must be aware of our biases
  Availability
  Representativeness

## Slide 12: Risk Assessment
Availability
Human judgment tends to over-estimate rare events that are more available or memorable
  e.g., deaths from airplane crashes – 1 in 1.6 million
and under-estimate rare events that are less available or memorable
  e.g., deaths following total knee replacement – 1 in 4,000

## Slide 13: Risk Assessment
Availability

## Slide 14: Risk Assessment
Availability – another example
How many seven letter words in the English language contain an “n” in the sixth position?
_ _ _ _ _ n _
How many words ______

## Slide 15: Risk Assessment
Availability – another example
How many seven letter words in the English language contain an “n” in the sixth position?
_ _ _ _ i n g
How many words ______

## Slide 16: Risk Assessment
Representativeness
True or False
“People with a Ph.D. are more likely to read the New York Times than persons with only a high school education”

## Slide 17: Risk Assessment
Representativeness
There is a woman sitting next to you in the cafe who is reading the New York Times…
Which is likely true:
She has a Ph.D.
She doesn’t have a college degree
Base Case Frequency

## Slide 18: Keys to a Successful Workshop
Biases and Heuristics
  Availability
    _ _ _ _ ing
  Representativeness
    Ignoring base case frequencies

## Slide 19: Keys to a Successful Workshop
This is a Workshop
  Participative/open/active
Your input is the key
  Subject Matter Experts (fresh eyes)
  PIP-II Technical Team (deep knowledge)
What we are asking of you is HARD!