## Slide 1
Lucas Taylor
Fermilab Risk Manager
Associate Project Manager, CMS HL-LHC Upgrades
Deputy Project Manager, CMS Phase 1 Upgrades
PIP-II Risk Workshop, 12-13th July 2018
Risk Process and PIP-II Risk Register

## Slide 2: Overview
Fermilab risk management process
PIP-II risk register – guidance for the workshop
A few subjective comments

## Slide 3: Fermilab Risk Management Procedure
Communicate and Improve
https://go.usa.gov/xUTJS
Plan Risk
Management
Identify
Risks
Develop mitigation
and response plans
Monitor and
Control risks
Analyze
Risks

## Slide 4: Fermilab Risk Register
Many views of risks
  https://go.usa.gov/x9sCm
Login: your-Fermilab-services-account
(ask Lucas.Taylor@cern.ch to get access)
Add new risk
PIP-II specific view
(we can easily tailor this)

## Slide 5: PIP-II Risk Register
https://go.usa.gov/xXRrr
Probability and Impacts
Warnings
This text = ADMIN COMMENT field concatenated with all warnings that are auto-generated generated by the system (like a software compiler).
You should aim for no warnings.
Open / close WBS
Add new risk
https://go.usa.gov/xXRrr
Edit risk

## Slide 6: Risk Register: (1) General description & metadata
Risk ID = Rx-nnn-i-jjj
x = “T” (threat) or “O” (opportunity)
nnn = P6 project ID (121 for PIP-II)
i is the L2 P6 ID (= 1,2,3,4)
jjj is risk number (001, 002, etc.)

## Slide 7: Risk Register: (1) General description & metadata
Risk title describes a risk event
rather than a consequence of a risk
It should make sense standalone
Examples:
Not good: “Delivery damage”
Better: “FPIX – Disk is damaged during shipping to CERN”
Not good: “Cost increases”
Better: “Niobium price increases faster than assumed escalation rate”

## Slide 8: Risk Register: (1) General description & metadata

## Slide 9: Risk Register: (1) General description & metadata
Risk “grammar” captures risk causes and effects, and hence points towards mitigation actions
If <RISK EVENT> occurs then
IMPACTS to technical scope, or
IMPACTS to cost, or
IMPACTS to schedule
would jeopardize the Project’s
Technical OBJECTIVES (e.g. KPP)
Cost OBJECTIVES (e.g. TPC)
Schedule OBJECTIVES (e.g. CD-4)
( If it does not jeopardize a project
objective, is it really a risk? )

## Slide 10: Risk Register: (1) General description & metadata
Risk Breakdown Structure
(common areas of risk)

## Slide 12: Risk Register: (1) General description & metadata
Personnel DB lookup
(includes external people with Fermi services account)
PIP-II

## Slide 13: Risk Register: (1) General description & metadata
Approval status:
Used in planning phase (e.g. risk workshop) to tag progress
Enter proposed risks freely – use this field to tag approval (or not)
Risk Status:
Used in project execution phase to track if risk is still a concern

## Slide 14: Risk Register: (2) dates, probability, tech. impact
Probability that risk occurs
This is critical input to the choice of risk mitigation strategy, and the contingency and float MC analysis
It does not need to be very precise! (by its very nature, risk is imprecise)
Used in risk ranking. Impact levels are project-specific.
Entering dates is optional They can be used for risk reports (e.g. “6-month look-ahead”) and to track risks to closure

## Slide 15: Risk Register: (3) cost impact
Impact (assessed after mitigations in the baseline were done) includes
  Cost of risk if it happens (e.g. higher cost of a backup vendor)
  Cost of response plans (e.g. rework or repair of damage)
  Burn rate costs from delays (standing army and increased escalation)

## Slide 16: Risk Register: (3) cost impact – single value
10
20
Impact
(k$)
Probability, P
0
30
P = 80%
(risk does
not occur)
P= 20%
(risk occurs)
1-point estimate (single value) for impact
  If risk occurs, impact is always exactly 20k$
Most likely value

## Slide 17: Risk Register: (3) cost impact – range
10
20
Impact
(k$)
Probability, P
0
30
P = 80%
(risk does
not occur)
P= 20%
(risk occurs)
2-point estimate (flat range) for impact
  If risk occurs, impact is in range 15k$ – 25k$ (all equally likely)
  Most likely impact = 20k$; Mean impact = 20k$
Minimum value
Maximum value

## Slide 18: Risk Register: (3) cost impact – 3-point estimate
3-point estimate (triangle distribution) for impact
  If risk occurs, impact in range 15k$ – 30k$ (extremes less likely)
  Most likely impact = 20k$; Mean impact* = 21.7k$
10
20
Impact
(k$)
Probability, P
0
30
P = 80%
(risk does
not occur)
P= 20%
(risk occurs)
* Mean x of triangular probability distribution function = (minimum x + most likely x + maximum x) / 3
Most likely value
Minimum value
Maximum value

## Slide 19: Risk Register: (4) schedule impact
1-, 2-, 3-point schedule impacts (in months)
(similar to cost impacts)
For now, just say in a few words what work is delayed

## Slide 20: Risk Register: (5) explanation & quality of estimate
Tag your level of confidence in the estimates so you know what might need follow-up analysis
Brief explanation of how the risk probability and impacts were estimated
See “Link to more details” field below, to add a URL

## Slide 21: Risk Register: (6) mitigation and response plans
Risks responses
Proposed Actions
Risk mitigations
 next slides

## Slide 22: Risk Mitigations
Inherent Risks
Mitigations
Current
(Residual) Risks
Mitigations – actions taken before a risk occurs, to reduce risk probability / impacts
  Mitigations are often part of standard operating procedures and controls
  Funds for mitigations must be in base plans
  Examples: build and test prototypes, work with multiple vendors, manufacture spares, safety training, financial controls, IT security…

## Slide 23: Risk Responses
Risk responses – actions only taken after a risk occurs, to reduce the impacts
  They are contingency (not baseline) plans
  Risk responses use contingency funds
  Examples: rework non-compliant items, replace failed hardware, respond to a fire, restore a hacked IT system…
Inherent Risks
Mitigations
Current
(Residual) Risks
Risk
Event
Consequences
and
Responses

## Slide 24: Probability and Impacts
Inherent Risks
Mitigations
Current
(Residual) Risks
Risk
Event
Consequences
and
Responses
Probability (%)
For ops risk: chance that risk happens in a 1 year period
Cost impact (k$)
(including cost of response plans)
Schedule impact
(including delays due to responses)
  Probability and Impacts are estimated post-mitigation
  Impacts cover the risk event itself and the response plans
Technical impact

## Slide 25: Risk Mitigations vs. Proposed Actions
Inherent Risks
Mitigations
Current
(Residual) Risks
IF mitigation IS in the base plan THEN
  Describe in Risk Mitigation field (including mitigation cost if known)
ELSE
  Describe in Proposed Actions field
  Fill in Proposed Actions Cost (k$)
Workshop (and after) will need to decide whether to incorporate new, proposed actions into baseline mitigation plans

## Slide 26: Risk Register: (7) more information
Only used if risk occurs and requires a Baseline Change Request
Optional: link to more information
(can be left blank)
Optional: any other comments (e.g. next steps to assess risk)
Optional: tags for creating custom filters or views
Obligatory: keeps track of what was changed and why

## Slide 27: Risk Register: (8) version history
Displays the change log
Be sure to save your changes
Optional: text entered here is pre-pended to the Warnings field (shown in “list of all risks” view)

## Slide 28: Risk Ranking
Risks are ranked according to the values of the Probability and Impacts (technical, cost, schedule). The register tool does the ranking automatically.

## Slide 29: Risk Ranking – implications
High Rank  PM + Lab / DOE
  May jeopardize the Project’s KPPs
  May lead to failure to complete major deliverables within cost or schedule
  Need mitigation or response plans
Medium Rank  L2 manager + PM
  Not expected to jeopardize KPPs
  Significant inability to deliver all scope in a timely & cost-effective manner
  Need mitigation or response plans
Low Rank  L3 manager + L2
  Will not jeopardize KPPs
  Modest impacts
  Mitigation or response plan not required

## Slide 30: Risk Monte Carlo Modeling – Contingency Analysis
Cost and schedule drivers
Costs of risks and contingency
Completion dates and float (e.g. to CD-4)
Results of Risk Modeling
Evaluate effectiveness of risk mitigations
Identify cost and schedule risk drivers
Determine cost and schedule contingency to finish on time, within budget (at 90% C.L.)
After the workshop
P6
DB
Full
Schedule
Summary Schedule
MC Risk Model
(Primavera Risk Analysis - PRA)
Risk
DB
Risk Register
(Web tool)
DocDB
More Details
(documents)
Implements Risk Events as probabilistic activities in the P6 schedule
All activities to deliver the project, logically linked.
Can be the full schedule or a summary schedule.

## Slide 31: Risk Monte Carlo Modeling – Contingency Analysis
(3) Choose cost and schedule impacts from distributions
(5) Repeat steps (2) – (4) thousands of times to study the statistical behavior of many scenarios
(1) Placeholder risk (hook) events are inserted into schedule with zero cost and zero duration
(2) Throw dice – if risk happens, risk activity is assigned risk impacts (cost and duration)
(4) Update entire schedule to generate one complete project outcome (scenario)
Primavera Risk Analysis (PRA) MC framework
After the workshop

## Slide 32: PIP-II risk register – some observations
Do ranks (H/M/L)
map well to oversight
level (PM/L2/L3)?
Total likely risk cost:
Sum (P * Cost Impact) =$17M
90% CL contingency will
be ~$(30-40)M
Sum (P * Schedule Impact)
= 11.4 years
Risks aren’t all in series on critical path
but total is still worryingly high
Include burn rate
costs for delays
(standing army
and escalation)
AccU:
only 3 risks but
all High rank
Many risks – obscures big picture
(1) Merge similar risks & (2) tune
ranking matrix to move risks to
“negligible” (= watch list)
Most High rank
risks have P=50%.
~Half will happen!
 review

## Slide 33: More information
Fermilab Risk Management  https://go.usa.gov/x9sCU
Project Risk Management  https://go.usa.gov/x9sCm
Risk Management Board  https://go.usa.gov/xXcyM
Operations Risk Management  https://go.usa.gov/x9sCp
Enterprise Risk Management  https://go.usa.gov/x9sCv
PIP-II Risk Summary  https://go.usa.gov/xXRrr
Any questions: Lucas.Taylor@cern.ch