## Slide 1
Paul Derwent
Risk Workshop
12,13-Jul-2018
PIP-II WBS 121.3 Accelerator Systems Risk Overview

## Slide 2: Outline
Scope Overview
Critical Technology Elements
Interfaces
Cost and Schedule
Risk categories
PIP-II Risk Register is at:
https://fermipoint.fnal.gov/organization/ocoo/ippm/Lists/Risk%20Register/PIP-II-Project-Risks.aspx

## Slide 3
Scope Overview

## Slide 4: WBS 121.3
Accelerator Systems:
“This WBS entry covers the labor, materials, travel, and costs associated with the design, procurement, fabrication, installation, and commissioning of accelerator systems (Accelerator Physics, High Power RF, Low Level RF, Magnets and Power Supplies, Vacuum, Controls, Safety Systems, and Beam Instrumentation) for PIP2IT, Test Infrastructure facilities, the Linac, and the transfer line to Booster.”

## Slide 5
Critical Technology Elements

## Slide 6: WBS 121.3 Critical Technology Elements (CTEs)
Critical Technology Element (CTE)
A technology element is “critical” if this technology is either new or poses major risk
  Does the component/technology directly impact a functional requirement of the system?
  Does the component/technology achieve a performance beyond existing state-of-the art?
  Are there uncertainties in the definition of the requirements for this component/technology?
  Do the limitations in the understanding of the technology/component non-performance result in a potential:
    cost overrun (> $500k)
    schedule delay (> 4 months)
  Is the component/technology expected to operate under new conditions?

## Slide 7: WBS 121.3 Critical Technology Elements (CTEs)
Resonance Control
  Beyond state of the art in the Pulsed RF case
  5 cavity and CM types
Laser Profile Monitor
  Beyond state of the art in low power modulated version
Machine Protection System
  Definition of requirements
Electronic systems
  Software, firmware, platforms, communications
  Definition of requirements perspective
Linac-Booster Energy match
  Phase stability, power supply stability
  Cost & schedule perspective, Definitions of requirements perspective

## Slide 8
Cost and Schedule

## Slide 9: WBS 121.3 Cost and Schedule
Costs from the CD1 Cost Book – to set the scale
L3 | Labor (hours) | Direct M&S (k$) | Fully Loaded + Escalation (k$)
PM & Coordination | 15,468 | $40 | $3,532
Accelerator Physics | 20,332 | $30 | $4,601
HPRF | 14,366 | $9,464 | $13,871
LLRF | 67,366 | $2,506 | $13,320
Magnets & PS | 37,989 | $10,707 | $18,831
Vacuum | 20,044 | $2,301 | $6,009
Controls | 92,893 | $3,932 | $20,023
Safety Systems | 9,493 | $568 | $2,176
Instrumentation | 31,980 | $3,288 | $9,423
Total | 309,901 | $32,836 | $91,785
Full Project | 1,415,458 | $306,103 | $687,781

## Slide 10
Interfaces

## Slide 11: WBS 121.3 Interface
Content of Interface slide(s): Describe any pertinent interfaces, whether internal to or external to your L2, and of any type - physical, energy/mass/information flow, software, managerial, organizational…
Have risks both internal to L3 systems and external to other L2

## Slide 12: WBS 121.3 External Interfaces: On the large scale
Cables & Racks
  Civil – penetrations
  Installation - layout
Controls
  Interface to everything!
  Key for schedule understanding
    Civil (for networks)
  Machine Protection
RF (both HL and LL)
  Cryomodules
  Civil (cables and RF distribution)
  Installation
Accelerator Physics
  Struggled defining interfaces here but they exist
  Civil / Installation
Vacuum
  Cryomodules
  Transfer Line
  Installation
Safety Systems
  Civil
  Cryogenics
  Installation
Magnets & PS
  Cryomodules
  Transfer Line
  Installation
Instrumentation
  Cryomodules
  Transfer LIne
  Installation

## Slide 13
Risks

## Slide 14: WBS 121.3 Risks : Identified Categories
High Power RF
  Performance, delivery, modifications to IIFC deliverables
LLRF
  Resonance Control, Interlocks
Machine Protection
  Instrumentation, Interlocks, Losses
Electronics (Controls, Instrumentation, LLRF, MPS)
  Software, firmware, platforms