## Slide 1
S. Dixon
Risk Workshop
12,13-Jul-2018
PIP-II WB 121.06 - Summary

## Slide 2: Conventional Facilities – Summary
General
  More Interfaces with other L3 than anticipated
  Many Technical Requirements not yet stable
Action Items
  Complete FESS MOU by September 2018 (RT-121-05-002)
  Reconsider Estimate Uncertainty versus Risk (eg: Linac Complex)
  Consolidate Similar Risks by area/type
  Review/Update Risk Register with Design Team

## Slide 3: Conventional Facilities – Risks
Revisit Risks:
  Construction Escalation (RT-121-05-001)
  Delineation between construction packages (RT-121-05-01-004)
  Extreme Weather (RT-121-05-008)
  Unknown Subsurface Conditions (RT-121-05-02-002)
New Risks:
  Penetrations Between Linac Tunnel and Linac Gallery
  CDS Tunnel Between Cryo Plant Building and Linac Tunnel
  Changing Regulations/Orders Impacts Construction
  Public Reaction Delays Construction
  Endangered/Threatened Species Identified

## Slide 4: END