## SRF CRYO only
RISK Level | RI-ID | Title | Owner | Probability | Cost Impact | Schedule Impact | Risk Status | Approval Status | Warnings | Item Type | Path | Impact (k$) - Function | Impact (k$) | Impact (k$) - Min | Impact (k$) - Max | Impact (months) - Function | Impact (months) | Impact (months) - Min | Impact (months) - Max | ADMIN COMMENT | Warning01 | Warning13 | Warning15 | Warning16 | Warning19 | Warning11 | Warning08
| RT-121-03-05-004 | Q0 performance of installed cavities | Allan M Rowe | 15% | 0 -- 1000 -- 2000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-12-001 | Resonance control and field regulation | Brian E Chase | 40% | 500 -- 3000 k$ | 6 -- 24 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-12-004 | IIFC LLRF/RFPI hardware/software does not meet acceptance criteria | Brian E Chase | 50% | 100 -- 1500 k$ | 3 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-11-005 | Technical Issues with RF Power Amps | James M Steimel | 50% | 100 -- 250 -- 500 k$ | 6 -- 12 -- 18 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-15-003 | Quench calculations indicate inadaquate QPM system | Bruce M Hanna | 50% | 40 k$ | 2 -- 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-11-010 | Failure of High Power Circulator | James M Steimel | 50% | 10 -- 50 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-17-001 | Machine Protection System Fails (Allows Beam Event) | James M Steimel | 25% | 30 -- 2000 k$ | 0.5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-12-005 | Incompatability in high performance electronic systems | James M Steimel | 25% | 100 -- 1500 k$ | 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-18-002 | Choice of laser profiling technology | Victor E Scarpine | 25% | 0 -- 100 -- 500 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-18-003 | Integration of instrumentation into MPS | Victor E Scarpine | 25% | 0 -- 200 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-11-001 | 162.5 MHz, 7 kW RF amplifier procurement delayed | David W Peterson | 25% | 65 -- 75 -- 85 k$ | 5 -- 6 -- 7 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-14-004 | Magnetic measurement system or test stand unavailable |  | 10% | 90 -- 100 -- 110 k$ | 5 -- 6 -- 7 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-12-003 | RF interlocks fail to protect SSA-Coupler-Cavity | Peter S Prieto | 10% | 90 -- 250 -- 340 k$ | 2 -- 5 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-17-002 | Machine Protection System Not Allowing Operation | James M Steimel | 25% | 10 -- 150 k$ | 1 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-19-002 | Controls interface to existing complex | James F Patrick | 10% | 0 -- 50 k$ | 0 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-15-004 | Quench analysis shows SSR1 protection is insufficient | Bruce M Hanna | 10% | 20 k$ | 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-15-001 | Cold magnet power supply procurement delay | Bruce M Hanna | 20% | 1 -- 5 k$ | 0 -- 2 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-19-003 | Internal interfaces to control system | James F Patrick | 10% | 0 k$ | 0 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
|  | HB650 amplifiers do not perform as expected | James M Steimel |  | k$ | months | Proposed | 1 - draft | Enter a unique risk ID. Enter Probability. Enter cost impact. Enter schedule impact. Specify Quality of Estimate. Specify earliest Start Date (of mitigations or risk event). | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-05-005 | Need to order PAs for "50 Ohm" kicker option | Lionel R Prost | 50% | 500 -- 700 -- 900 k$ | 0 months | Proposed | 1 - draft |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-24-005 | Machine performance problems during commissioning | Curtis M. Baffes | 25% | 100 -- 1000 -- 3000 k$ | 1 -- 4 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-04-002 | Unable to maintain proper vacuum between MEBT absorber and SRF | Lionel R Prost | 25% | 100 -- 200 -- 1000 k$ | 1 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Component
| RT-121-03-05-001 | Niobium quality assurance | Allan M Rowe | 20% | 0 -- 500 -- 1000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-11-002 | SRF Pre-Production Input Coupler Failure | Sergey Kazakov | 50% | 60 -- 500 k$ | 0.5 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
|  | Cavities Fail Qualification Test (non-recoverable) |  | 30% | 1000 -- 6000 k$ | 3 -- 12 months | Proposed | 1 - draft
Tuners (stepper, piezo) Fail Acceptance test
Current Leads Fail Acceptance Test
Solenoids Fail Acceptance Tests
Major cryomodule Components (Vacuum vessel, strong back, Support Post) Fail Acceptance Test
| RT-121-03-05-002 | Insufficient cavity production delivery rate (US/International) | Allan M Rowe | 25% | 400 -- 500 -- 600 k$ | 6 -- 9 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-01-02-002 | Failure of SRF cavity processing equipment | Allan M Rowe | 10% | 25 -- 280 -- 300 k$ | 0.5 -- 5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Cryomodule
Insufficient Engineering Resource
| RT-121-03-07-001 | SSR1 Cryomodule design modifications identified late in design cycle | Allan M Rowe | 20% | 250 -- 500 -- 2500 k$ | 4 -- 8 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-05-003 | Cryomodule production rate at Fermilab is too slow (US/International) | Allan M Rowe | 50% | 0 -- 0 -- 0 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Inadequate Procedure During Assembly
Tooling Failure During Assembly
| RT-121-03-10-001 | HB650 Cryomodule assembly and integration | Allan M Rowe | 10% | 0 -- 500 -- 1000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Excessive Field Emission During Acceptance Test
Cavity Gradient Below Spec During Acceptance Test
Excessive Heat Load During Acceptance Test
Cavity Frequency Out of Spec During Acceptance Test
Excessive Cavity Microphonics
Poor Thermal Strap Attachment
Alignment Below Spec During Acceptance Test
Excessive Residual Magnetic Field During Acceptance Test
Current Leads Failure in HWR Cryomodule
Current Leads Failure in SSR Cryomodule
| RT-121-03-09-006 | LB650 Cryomodule damage during transportation | Allan M Rowe | 10% | 0 -- 250 -- 500 k$ | 0 -- 3 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Transportation Damage for HB650 Cryomodules
| RT-121-01-02-003 | SRF Test Infrastructure Cryogenic Plant Failure | Stephen D Holmes | 15% | -- -- k$ | 1 -- 6 -- 9 months | Open | 4 - approved | Enter cost impact. | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-11-011 | Failure of 650 MHz IOT Amplifiers | James M Steimel | 50% | 10 -- 50 k$ | 2 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
SSA RF Station Failure During Acceptance Tests
| RT-121-03-06-001 | HWR Cryomodule does not meet technical performance requirements | Allan M Rowe | 20% | 250 -- 1000 -- 2000 k$ | 6 -- 12 -- 18 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-07-002 | SSR1 CM (1) Performance at PIP2IT does not meet technical requirements | Donato Passarelli | 40% | 250 -- 1000 -- 2000 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-10-002 | HB650 CM (1) Performance at CMTF does not meet technical requirements | Allan M Rowe | 40% | 250 -- 750 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-08-001 | SSR2 CM (1) Performance at PIP2IT does not meet technical requirements | Donato Passarelli | 40% | 250 -- 750 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-07-003 | SSR1 CM (2) Performance at PIP2IT CMTS does not meet technical requirements | Donato Passarelli | 20% | 250 -- 1000 -- 2000 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-09-001 | LB650 CMs (1-11) Performance at CMTS does not meet technical requirements | Allan M Rowe | 25% | 250 -- 500 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-08-002 | SSR2 Production CMs (2-7) do not meet technical performance requirements at PIP2IT | Donato Passarelli | 25% | 250 -- 500 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-10-003 | HB650 Production CMs (2-4) do not achieve technical performance requirements at CMTS. | Allan M Rowe | 20% | 250 -- 1000 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Commisioning
| RT-121-03-13-003 | Insufficient Cryogenic system vendor manufacturing capacity and priority | Arkadiy L Klebaner | 50% | 900 -- 1000 -- 1100 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-03-09-011 | Pulsed and CW cryomodule operating modes cause cryogenic or mechanical instabilities | Allan M Rowe | 50% | 125 -- 1000 -- 3000 k$ | 2 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Excessive Field Emission During Linac Commissioning
Cavity Gradient Below Spec During Linac Commissioning
Excessive Heat Load During Linac Commissioning
Excessive Cavity Microphonics During Linac Commissioning
Alignment Below Spec During Linac Commissioning
Excessive Residual Magnetic Field During Linac Commissioning
Cryoplant Pressure Instability
| RT-121-03-13-002 | Cryogenic system specification changes | Arkadiy L Klebaner | 1% | 0 -- 3000 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
Non Technical
SSR2 Cavity Late Delivery
LB650 Cryomodule Late Delivery
HB650 Cryomodule Late Delivery
Cryomodule Assembly Facility Availability
Cryomodule Test Facility Availability
Insufficient Assembly Staff
Insufficient Engineering Staff
| RT-121-01-02-001 | Delay in access to SRF testing and fabrication infrastructure | Stephen D Holmes | 50% | 0 -- 400 -- 500 k$ | 0 -- 5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| RT-121-02-03-001 | Cryoplant delivery delay | Arkadiy L Klebaner | 10% | 0 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register

## owssvr (downloaded)
RI-ID | Title | Owner | Probability | Cost Impact | Schedule Impact | Risk Status | Approval Status | Warnings | Item Type | Path | Impact (k$) - Function | Impact (k$) | Impact (k$) - Min | Impact (k$) - Max | Impact (months) - Function | Impact (months) | Impact (months) - Min | Impact (months) - Max | ADMIN COMMENT | Warning01 | Warning13 | Warning15 | Warning16 | Warning19 | Warning11 | Warning08
RT-121-02-01-002 | Technical Issues with International Deliverables | Allan M Rowe | 25% | 3000 -- 10000 -- 17500 k$ | 3 -- 9 -- 18 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-01-001 | Project Assumption of Operating fund with laboratory not implemented | Stephen D Holmes | 50% | 1000 -- 2000 -- 3000 k$ | 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-05-002 | NEPA approval is delayed | Stephen D Holmes | 50% | 90 -- 100 -- 110 k$ | 5 -- 6 -- 7 months | Open | 4 - approved | Add burn rate (standing army and escalation) costs. | Item | organization/ocoo/ippm/Lists/Risk Register
RU-121-02-04-001 | Currency Fluctuation | Stephen D Holmes | 50% | -5000 -- 0 -- 5000 k$ | months | Open | 4 - approved | IT IS AN UNCERTAINTY SO P SHOULD BE 100%. | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-01-004 | Effect of US Continuing Resolution | Stephen D Holmes | 50% | 0 k$ | 0 -- 4 -- 8 months | Open | 4 - approved | Add burn rate (standing army and escalation) costs. | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-05-001 | Non-jurisdictional Wetlands application denied | Stephen D Holmes | 30% | 2300 -- 4600 k$ | 2.5 -- 3 -- 3.5 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-02-002 | Insufficient Scientific, engineering and technical human resources including Contractor | Stephen D Holmes | 25% | 2000 -- 3000 -- 4000 k$ | 6 -- 11 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-04-001 | Inflation exceeds assumptions | Stephen D Holmes | 15% | 0 -- 5000 -- 10000 k$ | 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-01-005 | Effect of US Funding delay of "In-Kind" Design effort | Stephen D Holmes | 25% | 0 -- 500 -- 1000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-05-003 | Machine accident during installation / commissioning | Stephen D Holmes | 5% | 10 -- 100 -- 3000 k$ | 1 -- 3 -- 24 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-05-005 | Significant hydrofluoric acid spill or personnel exposure during SRF cavity processing | Allan M Rowe | 10% | 100 -- 250 -- 500 k$ | 1 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-01-003 | Assumed R&D funding profile not achieved | Stephen D Holmes | 15% | 0 k$ | 3 -- 9 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-02-001 | Inability to assign qualified individuals to key Project positions | Stephen D Holmes | 15% | 0 k$ | 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-01-001 | Failure to reach agreement on international in-kind contributions | Stephen D Holmes | 15% | 0 k$ | 12 -- 18 -- 24 months | Under review | 2 - see Comments |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-01-002 | Delay in formalizing international in-kind contributions | Stephen D Holmes | 25% | 0 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-01-004 | Assumed construction (post-CD-2) funding profile not achieved | Stephen D Holmes | 10% | k$ | 0 -- 24 months | Proposed | 2 - see Comments | Enter cost impact. | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-01-006 | Delay in international deliverables | Allan M Rowe | 25% | 0 k$ | 3 -- 6 -- 9 months | Open | 4 - approved | Is it already covered by RT-121-02-01-002? | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-03-002 | Insufficient International Deliverable Documentation | James M Steimel | 25% | 25 -- 50 -- 100 k$ | 0 -- 2 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-05-004 | Significant Injury/Fatality During Construction | Steven J Dixon | 1% | 1000 k$ | 0 -- 3 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-01-005 | Major Accident/Incident on Fermilab Site (PHA-1,3-6,8-15) | Stephen D Holmes | 10% | 0 k$ | 0 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-04-003 | Increase in Laboratory Overhead Rate - Large Procurements | Stephen D Holmes | 100% | 0 k$ | 0 months | Open | 4 - approved | Estimate cost impact (currently says 0k$) | Item | organization/ocoo/ippm/Lists/Risk Register
| Discovery of protected/endangered/threatened species |  |  | k$ | months | Proposed | 1 - draft | Enter a unique risk ID. Enter Probability. Enter cost impact. Enter schedule impact. Specify Quality of Estimate. Specify earliest Start Date (of mitigations or risk event). | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-09-011 | Pulsed and CW cryomodule operating modes cause cryogenic or mechanical instabilities | Allan M Rowe | 50% | 125 -- 1000 -- 3000 k$ | 2 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-13-003 | Insufficient Cryogenic system vendor manufacturing capacity and priority | Arkadiy L Klebaner | 50% | 900 -- 1000 -- 1100 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-07-002 | SSR1 CM (1) Performance at PIP2IT does not meet technical requirements | Donato Passarelli | 40% | 250 -- 1000 -- 2000 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-10-002 | HB650 CM (1) Performance at CMTF does not meet technical requirements | Allan M Rowe | 40% | 250 -- 750 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-08-001 | SSR2 CM (1) Performance at PIP2IT does not meet technical requirements | Donato Passarelli | 40% | 250 -- 750 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-002 | SRF Pre-Production Input Coupler Failure | Sergey Kazakov | 50% | 60 -- 500 k$ | 0.5 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-011 | Failure of 650 MHz IOT Amplifiers | James M Steimel | 50% | 10 -- 50 k$ | 2 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-05-003 | Cryomodule production rate at Fermilab is too slow (US/International) | Allan M Rowe | 50% | 0 -- 0 -- 0 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-07-001 | SSR1 Cryomodule design modifications identified late in design cycle | Allan M Rowe | 20% | 250 -- 500 -- 2500 k$ | 4 -- 8 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-06-001 | HWR Cryomodule does not meet technical performance requirements | Allan M Rowe | 20% | 250 -- 1000 -- 2000 k$ | 6 -- 12 -- 18 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-07-003 | SSR1 CM (2) Performance at PIP2IT CMTS does not meet technical requirements | Donato Passarelli | 20% | 250 -- 1000 -- 2000 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-09-001 | LB650 CMs (1-11) Performance at CMTS does not meet technical requirements | Allan M Rowe | 25% | 250 -- 500 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-08-002 | SSR2 Production CMs (2-7) do not meet technical performance requirements at PIP2IT | Donato Passarelli | 25% | 250 -- 500 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-10-003 | HB650 Production CMs (2-4) do not achieve technical performance requirements at CMTS. | Allan M Rowe | 20% | 250 -- 1000 -- 1500 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-02-001 | Delay in access to SRF testing and fabrication infrastructure | Stephen D Holmes | 50% | 0 -- 400 -- 500 k$ | 0 -- 5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-05-004 | Q0 performance of installed cavities | Allan M Rowe | 15% | 0 -- 1000 -- 2000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-05-002 | Insufficient cavity production delivery rate (US/International) | Allan M Rowe | 25% | 400 -- 500 -- 600 k$ | 6 -- 9 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-05-001 | Niobium quality assurance | Allan M Rowe | 20% | 0 -- 500 -- 1000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-10-001 | HB650 Cryomodule assembly and integration | Allan M Rowe | 10% | 0 -- 500 -- 1000 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-02-002 | Failure of SRF cavity processing equipment | Allan M Rowe | 10% | 25 -- 280 -- 300 k$ | 0.5 -- 5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-02-03-001 | Cryoplant delivery delay | Arkadiy L Klebaner | 10% | 0 k$ | 3 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-01-02-003 | SRF Test Infrastructure Cryogenic Plant Failure | Stephen D Holmes | 15% | -- -- k$ | 1 -- 6 -- 9 months | Open | 4 - approved | Enter cost impact. | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-09-006 | LB650 Cryomodule damage during transportation | Allan M Rowe | 10% | 0 -- 250 -- 500 k$ | 0 -- 3 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-13-002 | Cryogenic system specification changes | Arkadiy L Klebaner | 1% | 0 -- 3000 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-12-001 | Resonance control and field regulation | Brian E Chase | 40% | 500 -- 3000 k$ | 6 -- 24 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-12-004 | IIFC LLRF/RFPI hardware/software does not meet acceptance criteria | Brian E Chase | 50% | 100 -- 1500 k$ | 3 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-005 | Technical Issues with RF Power Amps | James M Steimel | 50% | 100 -- 250 -- 500 k$ | 6 -- 12 -- 18 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-15-003 | Quench calculations indicate inadaquate QPM system | Bruce M Hanna | 50% | 40 k$ | 2 -- 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-010 | Failure of High Power Circulator | James M Steimel | 50% | 10 -- 50 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-17-001 | Machine Protection System Fails (Allows Beam Event) | James M Steimel | 25% | 30 -- 2000 k$ | 0.5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-12-005 | Incompatability in high performance electronic systems | James M Steimel | 25% | 100 -- 1500 k$ | 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-18-002 | Choice of laser profiling technology | Victor E Scarpine | 25% | 0 -- 100 -- 500 k$ | 0 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-18-003 | Integration of instrumentation into MPS | Victor E Scarpine | 25% | 0 -- 200 k$ | 0 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-001 | 162.5 MHz, 7 kW RF amplifier procurement delayed | David W Peterson | 25% | 65 -- 75 -- 85 k$ | 5 -- 6 -- 7 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-14-004 | Magnetic measurement system or test stand unavailable |  | 10% | 90 -- 100 -- 110 k$ | 5 -- 6 -- 7 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-12-003 | RF interlocks fail to protect SSA-Coupler-Cavity | Peter S Prieto | 10% | 90 -- 250 -- 340 k$ | 2 -- 5 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-17-002 | Machine Protection System Not Allowing Operation | James M Steimel | 25% | 10 -- 150 k$ | 1 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-19-002 | Controls interface to existing complex | James F Patrick | 10% | 0 -- 50 k$ | 0 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-15-004 | Quench analysis shows SSR1 protection is insufficient | Bruce M Hanna | 10% | 20 k$ | 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-15-001 | Cold magnet power supply procurement delay | Bruce M Hanna | 20% | 1 -- 5 k$ | 0 -- 2 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-19-003 | Internal interfaces to control system | James F Patrick | 10% | 0 k$ | 0 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| HB650 amplifiers do not perform as expected | James M Steimel |  | k$ | months | Proposed | 1 - draft | Enter a unique risk ID. Enter Probability. Enter cost impact. Enter schedule impact. Specify Quality of Estimate. Specify earliest Start Date (of mitigations or risk event). | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-05-005 | Need to order PAs for "50 Ohm" kicker option | Lionel R Prost | 50% | 500 -- 700 -- 900 k$ | 0 months | Proposed | 1 - draft |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-24-005 | Machine performance problems during commissioning | Curtis M. Baffes | 25% | 100 -- 1000 -- 3000 k$ | 1 -- 4 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-04-001 | MEBT kickers performance is unsatisfactory | Lionel R Prost | 25% | 500 -- 1000 k$ | 4 -- 8 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-04-002 | Unable to maintain proper vacuum between MEBT absorber and SRF | Lionel R Prost | 25% | 100 -- 200 -- 1000 k$ | 1 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-05-006 | Use a subset of the PIP2IT MEBT bunching cavities at PIP-II | Lionel R Prost | 50% | 80 -- 160 -- 240 k$ | 0 months | Proposed | 1 - draft |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-04-004 | MEBT scrapers unable to absorb amount of beam loss | Lionel R Prost | 25% | 100 -- 500 k$ | 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-01-001 | PIP2IT does not meet overall requirement at CD-3 | Lionel R Prost | 10% | 100 -- 1000 k$ | 2 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-24-001 | Late subsystem delivery makes installation less efficient | Curtis M. Baffes | 50% | 20 -- 200 k$ | 2 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-21-002 | Requirements or interface definition for LCW LTA | Curtis M. Baffes | 50% | 10 -- 200 k$ | 2 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-04-003 | MEBT Absorber does not meet performance requirement | Lionel R Prost | 10% | 100 -- 800 k$ | 8 -- 12 -- 16 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-21-003 | LCW system does not achieve temperature stability requirements | Curtis M. Baffes | 10% | 100 -- 500 k$ | 1 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-02-003 | Ion source performance does not allow efficient transmission through HWR | Lionel R Prost | 12.5% | 100 -- 250 k$ | 12 -- 24 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-008 | Insufficient Space for SSR2 Amplifiers at PIP2IT | James M Steimel | 50% | 25 k$ | 0 -- 1 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-24-003 | Subsystem or component problem discovered after installation | Curtis M. Baffes | 10% | 50 -- 100 k$ | 1 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-03-02-001 | Re-design ion source vacuum chamber | Lionel R Prost | 25% | 15 k$ | 2 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-11-009 | Insufficient Space for LB650 Amplifiers at CMTS | James M Steimel | 10% | 25 k$ | 0 -- 1 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-14-002 | Damage to magnets/frame during shipping and handling | Stoyan Emilov Stoynev | 5% | 15 k$ | 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-24-002 | Mismatch between sybsystem delivery and installation schedule creates need for storage | Curtis M. Baffes | 25% | 50 k$ | 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-03-001 | RFQ resonant frequency does not meet specifications | Lionel R Prost | 5% | 10 k$ | 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-04-01-001 | MI RF System Upgrade | Ioanis Kourbanis | 25% | 5500 -- 6000 -- 6500 k$ | 1.5 -- 2 -- 2.5 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-12-007 | Transfer Energy Matching Fails | James M Steimel | 50% | 20 -- 150 k$ | 2 -- 8 months | Proposed | 2 - see Comments |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-03-10-006 | Synchronous Bucket Transfer Fails | James M Steimel | 50% | 75 k$ | 5 months | Proposed | 2 - see Comments |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-09-001 | Accelerator Shutdown Changes | Steven J Dixon | 50% | 0 -- 250 -- 1500 k$ | 0.5 -- 1 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-002 | Inadequate Fermilab CF Engineering Support | Steven J Dixon | 50% | 100 -- 300 k$ | 3 -- 8 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-07-001 | Increased Support Space in Linac Gallery |  | 25% | 500 -- 1250 -- 2000 k$ | 0 -- 5 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-01-002 | Subproject Changes Impact Conventional Facilities | Steven J Dixon | 30% | 250 -- 600 -- 2000 k$ | 2 -- 6 -- 12 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-013 | Construction Bids Exceed Estimates | Steven J Dixon | 15% | 100 -- 500 -- 750 k$ | 0 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-06-001 | Increased Linac Enclosure Width | Steven J Dixon | 20% | 100 -- 250 -- 600 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-07-001 | RF LCW Temperature Delta Too Low | Steven J Dixon | 20% | 150 -- 300 -- 500 k$ | 2 -- 4 -- 8 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-03-001 | Cryoplant Design Requirements | Steven J Dixon | 25% | 10 -- 150 -- 500 k$ | 0 -- 3 -- 8 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-03-004 | Cryoplant Cooling Water | Steven J Dixon | 50% | 0 -- 75 -- 250 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-003 | Radiation Shielding Inadequate | Steven J Dixon | 15% | 0 -- 250 -- 750 k$ | 0 -- 1 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-03-002 | Cryoplant Cooling Water | Steven J Dixon | 10% | 150 -- 500 -- 750 k$ | 0 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-01-001 | Design Complexity | Steven J Dixon | 15% | 0 -- 250 -- 600 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-09-005 | Poor Interface Definition | Steven J Dixon | 25% | 25 -- 150 -- 300 k$ | 1 -- 6 -- 9 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-004 | Schedule Slippage for Long Lead Time Equipment | Steven J Dixon | 10% | 10 -- 50 -- 100 k$ | 1 -- 6 -- 8 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-005 | Full Funding for Conventional Facilities | Steven J Dixon | 0.1% | -100 -- -500 -- -750 k$ | -6 -- -10 -- -20 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-001 | Value Management Opportunities | Steven J Dixon | 50% | 0 -- -100 -- -300 k$ | 0 -- -1 -- -3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-07-002 | Increase in RF Heat Load in Pulsed Mode Requires Additional Cooling | Steven J Dixon | 30% | 200 -- 300 -- 400 k$ | 0 -- 2 -- 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-01-004 | Unclear/Incomplete Delineation Between Construction Packages | Steven J Dixon | 25% | 0 -- 200 -- 500 k$ | 0 -- 1 -- 3 months | Open | 4 - approved | Revisit risk impacts | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-015 | Quality Deficiencies Result in Decreased Performance | Steven J Dixon | 5% | 0 -- 500 -- 1500 k$ | 0 -- 1 -- 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-08-001 | Inadequate Sheilding at Beam Absorber Location | Steven J Dixon | 15% | 50 -- 125 -- 400 k$ | 0 -- 3 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-011 | Improper Maintanence After Beneficial Occupancy | Steven J Dixon | 25% | 0 -- 50 -- 200 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-04-001 | CUB Chilled Water Inadequate | Steven J Dixon | 5% | 200 -- 300 -- 400 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-002 | Renewable Energy Opportunities | Steven J Dixon | 5% | 100 -- 250 -- 500 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-01-003 | Errors/Omissions in Construction Documents | Steven J Dixon | 5% | 0 -- 200 -- 600 k$ | 0 -- 0.5 -- 1 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-008 | Extreme Weather Delays Construction | Steven J Dixon | 10% | 0 -- 100 -- 250 k$ | 0.5 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-07-003 | Humidity Requirements in Linac Gallery | Steven J Dixon | 10% | 50 -- 100 -- 200 k$ | 0 -- 2 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-010 | Poor Performance by Construction Subcontractor | Steven J Dixon | 15% | 0 -- 50 -- 150 k$ | 1 -- 3 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-09-002 | Damage to Existing Booster Equipment During Construction | Steven J Dixon | 15% | 10 -- 35 -- 125 k$ | 0 -- 1 -- 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-007 | Unavailability of Construction Workforce | Steven J Dixon | 5% | 0 -- 250 -- 300 k$ | 0 -- 2 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-006 | Substantial Claim by Subcontractor | Steven J Dixon | 5% | 100 -- 150 -- 200 k$ | 0 -- 2 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-02-002 | Unknown Subsurface Conditions | Steven J Dixon | 10% | 0 -- 50 -- 150 k$ | 0.5 -- 1 -- 2 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-001 | Construction Escalation Greater Than Predicted | Steven J Dixon | 10% | -100 -- 100 -- 200 k$ | 0 -- 0 -- 0 months | Open | 4 - approved | Revisit risk | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-09-003 | Differing Conditions at Booster | Steven J Dixon | 10% | 10 -- 60 -- 100 k$ | 0 -- 1 -- 3 months | Open | 4 - approved | Consolidate related risks to excavations | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-06-003 | Equipment Induced Vibrations Impact Accelerator Operations | Steven J Dixon | 10% | 25 -- 50 -- 100 k$ | 0 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-08-003 | Damage to Main Ring Beamline Equipment During Construction | Steven J Dixon | 15% | 0 -- 25 -- 75 k$ | 0 -- 1 -- 2 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-014 | A/E Proposals Exceed Budget | Steven J Dixon | 5% | 0 -- 100 -- 200 k$ | 0 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-08-002 | Impact to Muon Campus Operations Due to Cryo Line Damage | Steven J Dixon | 10% | 10 -- 30 -- 75 k$ | 0 -- 0.5 -- 1 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-06-001 | Sump Pump Failure | Steven J Dixon | 5% | 10 -- 80 -- 150 k$ | 0 -- 1 -- 3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-02-003 | Unknown Soil Contaminants | Steven J Dixon | 5% | 25 -- 50 -- 75 k$ | 0 -- 1 -- 4 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-012 | Poor Performance by A/E Team | Steven J Dixon | 5% | 0 -- 50 -- 100 k$ | 1 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-009 | Labor Action Delays Construction | Steven J Dixon | 5% | 10 -- 15 -- 50 k$ | 0 -- 0.5 -- 1 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-02-001 | Permitting Delay | Steven J Dixon | 5% | 0 -- 10 -- 20 k$ | 0.5 -- 2 -- 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-03-003 | Cryogenic plant building BO delayed |  | 10% | 0 k$ | 6 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-08-001 | Main Ring Enclosure Not Needed | Steven J Dixon | 5% | -10 -- -50 -- -150 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-004 | Construction Bids Below Estimate | Steven J Dixon | 10% | -100 -- -250 -- -500 k$ | 0 -- -1 -- -3 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
RT-121-05-09-006 | Booster Ventilation Inadequate | Steven J Dixon | 30% | 10 -- 30 -- 100 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register
| Penetrations between gallery and tunnel |  |  | k$ | months | Proposed | 1 - draft | Enter a unique risk ID. Enter Probability. Enter cost impact. Enter schedule impact. Specify Quality of Estimate. Specify earliest Start Date (of mitigations or risk event). | Item | organization/ocoo/ippm/Lists/Risk Register
| Uncertainty of trench location & size between Cryo Plant and Linac Tunnel |  |  | k$ | months | Proposed | 1 - draft | revisit and define Enter a unique risk ID. Enter Probability. Enter cost impact. Enter schedule impact. Specify Quality of Estimate. Specify earliest Start Date (of mitigations or risk event). | Item | organization/ocoo/ippm/Lists/Risk Register
RO-121-05-003 | Radiation Shielding Opportunities | Steven J Dixon | 10% | 0 -- -25 -- -50 k$ | 0 -- 0 -- 0 months | Open | 4 - approved |  | Item | organization/ocoo/ippm/Lists/Risk Register