## Slide 1
M. Anerella
August 1, 2018
Vertical Test Stand at BNL
Cost and Schedule
For
Operations During Production

## Slide 2: Outline
Responding to Charge 3. Equipment and Design Documentation
f. Is the cost and schedule estimate for the deployment of the Vertical Magnet Test system credible?
Responding to Charge 5. OPERATIONS
e. Is the cost and schedule estimate for operations of the Vertical Magnet Test system during production credible?
        Schedule
        Cost
        Summary

## Slide 3: Prototype Schedule, Resources
2 quenches / day, 12 hr. days
Needs BCR to add incoming electrical tests
Schedule subject to changes in Run Plan

## Slide 4: Production Schedule, Resources
3 quenches / day, 16 hr. days
25 quenches per G.A / R.C.
Needs BCR to add incoming electrical tests

## Slide 5: BOE’s for Magnet Test during Operation (3)
1
2
3

## Slide 6: BOE 302-4-01-1030 Magnet Test Preparation
Reference: US-HiLumi-doc-126
1
no M&S – need BCR for rigging

## Slide 7: BOE 302-4-01-1040 Magnet Test p.1
Reference: US-HiLumi-doc-126
2

## Slide 8: BOE 302-4-01-1040 Magnet Test p.2
Reference: US-HiLumi-doc-126
2

## Slide 9: BOE 302-4-01-1040 Magnet Test p.3
Reference: US-HiLumi-doc-126
2

## Slide 10: BOE 302-4-01-1050 Magnet Test Breakdown & Shipment to FNAL
Reference: US-HiLumi-doc-126
3
$7,100 M&S per magnet for shipping freight only – need BCR for rigging

## Slide 11: BOE for Magnet Test Deployment

## Slide 12: BOE 302-4-01.1020 Cryo Facility, Rate and Reliability p.1

## Slide 13: BOE 302-4-01.1020 Cryo Facility, Rate and Reliability p.3

## Slide 14: BOE 302-4-01.1020 Cryo Facility, Rate and Reliability p.2
Many large $ items are based on quotes or actuals
$195,723 (FY19)
$365,704 (FY18)

## Slide 15: Summary
Cost and Schedule are well understood
  Based on previous experience with test facility during Mirror magnet test and MQXFA-01 test
  Based largely on actual purchase orders for cryogenic materials and actual daily electric power usage & BNL rates, and previous experience with regard to reliability / rate items
  Based on directed scope of work for prototypes and production magnets

## Slide 16: Backup slides

## Slide 17
Testing Day Durations, Usage
17.9KA Ultimate Current Quenches, 25% Energy Extraction – 3 QUENCHES/DAY, PRODUCTION; 16 hour cryo |  |  | 
Task Name | Duration (hr) | Helium Usage (gal) | Helium Usage (L)
refill 4.5K liquid | 1.5 | 250 | 946
pump down to 1.9K | 3 | 150 | 568
ramp #1 (17.9KA @20A/s) | 0.5 |  | 
refill 4.5K liquid after 4.0 MJ | 2 | 300 | 1136
pump down to 1.9K | 3 | 150 | 568
ramp #2 (17.9KA @20A/s) | 0.5 |  | 
refill 4.5K liquid after 4.0 MJ | 2 | 300 | 1136
pump down to 1.9K | 3 | 150 | 568
ramp #3 (17.9KA @20A/s) | 0.5 |  | 
partial refill 4.5K liquid after 4.0 MJ | 1 | 200 | 757
total cryo tech (CT) * | 17 | 1105 | 4183
total test tech (TT) | 11.5 |  | 
total helium |  | 2605 | 9861
17.9KA Ultimate Current Quenches, 25% Energy Extraction – 2 QUENCHES/DAY, PROTOTYPE; no 16 hour days |  |  | 
Task Name | Duration (hr) | Helium Usage (gal) | Helium Usage (L)
refill 4.5K liquid | 1.5 | 250 | 946
pump down to 1.9K | 3 | 150 | 568
ramp #1 (17.9KA @20A/s) | 0.5 |  | 
refill 4.5K liquid after 4.0 MJ | 2 | 300 | 1136
pump down to 1.9K | 3 | 150 | 568
ramp #2 (17.9KA @20A/s) | 0.5 |  | 
partial refill 4.5K liquid after 4.0 MJ | 1 | 200 | 757
total cryo tech (CT) * | 11.5 | 747.5 | 2830
total test tech (TT) | 6 |  | 
total helium |  | 1798 | 6804
* boil-off of 250 L/hr. is calculated based on cryo tech time for full day

## Slide 18
Testing Performance
Days in red denote testing does not occur; liquefaction only to rebuild inventory
Prototype testing based on 1/10/17 Functional Test Requirement US-HiLumi Document 137-v3
of 50 quenches
Production testing analysis based on G. Ap’s request for 30 quenches in 10 working days –
AGREED by R. Carcagno that Functional Test Requirements to be updated to 25 quenches (5 to be added to Risk Registry)
Prototype: 2 quenches-12hrs/day defensible due to marginal improvement at 16hrs/day with present liquefaction capability

## Slide 19: BOE 302-4-01-1010 L3 Management of Vertical Test LOE