## Slide 1: Project Monitor and Control: Estimate at Completion
Presenter’s Name: Mohammed Elrafih, Project Controls Specialist
Meeting Title : EVMS Training – Monitor & Control: Estimate at Completion and Change Control
1 March 2019

## Slide 2: Obtain a Fermi Services Account
To request a Fermi account:
Go to - https://fermi.service-now.com/new_acct_request.do
Select your affiliation under “Collaborations” using the Pull-down menu
Fill out the rest of the information.
After submitting the form, it should come to the Project PM/Director for approval
Once approved it should be easy to get the Fermi account.
The training courses and the Fermi Workday system set up take a little time

## Slide 3: Fermi Systems Access
Once you obtain your Fermi Services account PM/Director can (as appropriate):
Inform Risk Manager to authorize you to access the Fermilab web-based risk register.
Authorize access to DocDB or FermiPoint where all Project documents reside including
  P6 PDFs
  Status reports
  Other CAM reports
Inform OPSS for Access to:
  P6 can be granted if desired.
    Cost to Project ~$400 per year
    Read only for project files
    Read/Write for “Sandbox”
  Baseline Change Request (BCR) Tool – Needed for next week
  CAM eToolbox – Needed for next week

## Slide 4: CAMs Address Deviations from Plan
“How do you let your PM know there will be an increase (or decrease) in cost or schedule?”
“When do you let your PM know there will be an increase (or decrease) in cost or schedule?”
Why do you notify PM?
How Would You Answer?

## Slide 5: FNAL EVMS process is found in procedures
  CAMs need to:
  Know
  Use
  Reference
EVMS Procedures Answer:
  Who
  Why
  When
  How

## Slide 6: FNAL EVMS Procedures (4/9)
Project WBS, OBS, RAM
Control Accounts, Work Packages, Planning Packages
Work Authorization
Project Scheduling
Cost Estimating
Monthly Status Reporting
Change Control
EVMS Surveillance & Maintenance
EVMS Description

## Slide 7
Getting to Procedures & Guidelines – Policies & Procedures
https://web.fnal.gov/organization/OPSS/Pages/EVMS-Documentation.aspx

## Slide 8
FNAL Procedure 12.PM-005 Cost Estimating

## Slide 9
FNAL Procedure 12.PM-005 Cost Estimating
  EAC = Estimate At Completion
  ETC = Estimate To Completion

## Slide 10
FNAL Procedure 12.PM-005 Cost Estimating

## Slide 11
FNAL Procedure 12.PM-006 Monthly Status Reporting

## Slide 12
FNAL Procedure 12.PM-006 Monthly Status Reporting

## Slide 13
FNAL Procedure 12.PM-006 Monthly Status Reporting

## Slide 14
Fermilab Earned Value Management System Description

## Slide 15
Fermilab EVMS Description – Continued 5.2.6

## Slide 16: Deviations from Plan are Answered by EVMS Procedures
Who
  CAM
  PM
Why
  Required – OK but
  Manage
  Inform
When
  Annually
  When Requested
  Monthly Process
  When Known

## Slide 17
FNAL Deviation Communication Tool
What Formal Tool(s) does FNAL use to Communicate Cost and Schedule Deviations?

## Slide 18
FNAL Deviation Communication Tool (Cont.)
What Formal Tool(s) does FNAL use to Communicate Forecast Cost Deviations (under/over)?

## Slide 19: Cobra Reports – VAR: Forecast Communication Tool
At Complete
  BAC (Budget At Completion)
  EAC (Estimate At Completion)
  VAC (Variance At Completion)
2
3
1

## Slide 20: Variance Analysis Thresholds (Default)
FRA Management
Project Requirements
FRA Management
Project Requirements
  Risk
  Budget
  Reflected in PMP
Changed by Exception

## Slide 21: VAR – Narration (Four Key Elements)
Explanation of Variance
Impact
Corrective Action
Summary

## Slide 22: VAR – Narration (First Two Elements)
Explanation of Variance
Current
Cumulative
  Cost
  Schedule
    What
    Why
  At Completion
Impact
Schedule
Cost
CA
Think Successors
Project

## Slide 23: VAR – Narration (Last Elements)
Corrective Action
Plan to Return to PMB
Time-frame to Correction
Track Actions to Completion
VAC – Usually None
Summary
Accomplishments
Technical Challenges
Look Ahead
  Over and Under Runs
Ensure your VAR is Approved (Project Manager)

## Slide 24: Scenario #1
What if you know a Contract/M&S has cost more (or less) than Planned?
Actions
Communicate via VAR
  Explanation of Variance (VAC)
  Impact: CA increase EAC
  No Corrective Action (Unless warrants BCP on Future work)
Project Change in ETC if Appropriate

## Slide 25: Scenario #2
What if you know a Future Contract/M&S will cost more (or less) than Planned?
Actions
Attempt to Mitigate
Project change in ETC
Communicate via VAR
  Cost Variance Explanation (VAC)
  Impact: CA increase EAC
  Corrective Action: Attempt Mitigation or BCR

## Slide 26: Scenario #3
What if you know Rates (Labor/M&S) have Changed from Planned?
Actions: ETC
Project change in ETC
Communicate via VAR
  Cost Variance Explanation (VAC)
  No Corrective Action
Actions: BCP
Communicate via Change Control
VAR with new BAC
Decision of ETC vs BCP is PM’s

## Slide 27: Scenario #4
What if you know a Field Change has been Initiated (Added Scope) or BCR will be implemented, but has not been yet?
Actions: ETC
Project change in ETC
Communicate via VAR
  Cost Variance Explanation (VAC)
  Corrective Action – Future BCR
Prepare Change Control Documentation
Identify in Summary (Look ahead)
Decision BCP approval is PM’s - Communicate

## Slide 28: Scenario #4 (Cont.)
What if you know a Field Change has been Initiated (Added Scope) or BCR will be implemented, but has not been yet? Communicated to PM but PM will not allow BCR
Actions: ETC
Project change in ETC
Communicate via VAR
Identify in Summary (Look ahead)
Decision BCP approval is PM’s - Communicate

## Slide 29: How to Calculate ETC
Calculations
EAC = ACWPCTD + ETC
ETC = EAC - ACWPCTD
ETC = BAC – BCWPCTD
VAC = BAC - EAC
Information Needed to Start
BAC = Budget at Completion
BCWSCTD = Cumulative BCWS
BCWPCTD = Cumulative BCWP
ACWPCTD = Cumulative ACWP

## Slide 30: How to Calculate ETC
Calculations
EAC = ACWPCTD + ETC
ETC = EAC - ACWPCTD
ETC = BAC – BCWPCTD
VAC = BAC – EAC
SPI, CPI & CV
Information Needed to Start
BAC = Budget at Completion
BCWSCTD = Cumulative BCWS
BCWPCTD = Cumulative BCWP
ACWPCTD = Cumulative ACWP

## Slide 31: How to Calculate ETC (Cont.)
EAC = ACWPCTD + ETC
ETC = EAC - ACWPCTD
ETC = BAC – BCWPCTD
VAC = BAC - EAC
What is Missing?

## Slide 32: How to Calculate ETC (Cont.)
EAC = ACWPCTD + ETC
ETC = EAC - ACWPCTD
ETC = BAC – BCWPCTD
VAC = BAC - EAC
Understand:
Assumes Plan is Perfect
  Does not Account for Good/Bad Performance
No Future Adjustments
No Cost of Schedule Slip

## Slide 33: How to Calculate ETC (Cont.)
EAC = ACWPCTD + ETC
ETC = EAC - ACWPCTD
ETC = BAC – BCWPCTD
VAC = BAC - EAC
+ Known Future Deviations
EVMS is:
Management Tool
Communication Tool
EVMS is:
Management Tool
Communication Tool

## Slide 34: How to Calculate ETC using P6
P6 update included forecast dates and resource remaining units

## Slide 35: How to Calculate ETC using P6 (cont.)
P6 Forecast dates and remaining units integrated into Cobra

## Slide 36: Reporting Tools – Understand ETC
Time-Phased ACWP (Actuals), BCWS (Budget) & ETC in Hours
Estimate To Completion i.e. cost of future work

## Slide 37: Reporting Tools – Understand ETC
Time-Phased ACWP, BCWS & ETC in Dollars

## Slide 38: Reporting Tools – Understand ETC
Time-Phased BCWS (Budget) & ETC

## Slide 39: CAMs Address Deviations from Plan
“How do you let your PM know there will be an increase (or decrease) in cost or schedule?”
“When do you let your PM know there will be an increase (or decrease) in cost or schedule?”
Why do you notify PM?
Now How Would You Answer?

## Slide 40
FNAL Procedure 12.PM-007 Change Control
Baseline Change Request

## Slide 41
FNAL Procedure 12.PM-007 Change Control

## Slide 42
Fermilab Earned Value Management System Description

## Slide 43: Project Life Cycle – Models Review
Initiation
Planning
Execution
Close-out
Begin then Implement Change Control

## Slide 44: Project Life Cycle – Monitor & Control Review
Initia…
Monitor/Control
…tion
Plan…
Monitor/Control
…ning
Exacu…
Monitor/Control
…tion
Close…
Monitor/Control
…Out
Monitor & Control Cycle
Measure
Evaluate
Correct

## Slide 45: Why We Monitor/Control and Initiate Change Control
During Baseline All agreed, Scope, Schedule, and Cost are reasonable
Deviations need to be Agreed to
Demonstrate We Manage not being Managed

## Slide 46
Change Management – Primary Goal is Manage/Control
  Control Deviations from Original Plan
  Work
    Defined Scope
    Performed Scope
  Cost
    Budget
    Actual
  Schedule
    Baseline
    Actual
Work
Schedule
Cost

## Slide 47
Types of Change
Scope/Schedule/Cost
  Internal Re-planning & Changes
    Changed Conditions
    Better Mouse Trap
    Missed Scope (requires FPD Approval)
    Realized Risks
  External/Directed (Added Scope)
  Authorized Unpriced Work (Field Changes)
Administrative
  Coding
  Typographical
  Description Clarification

## Slide 48
Where to Find Change Thresholds
Appendix C of Change Control Procedure (Guidance)
PEP –
Project Specific

## Slide 49: Questions about Change - CCB
What is a Change Control Board (CCB)?
“The CCB ensures technical performance, scope, cost, schedule, and associated risk impacts are understood and documented. CCB membership typically consists of key members of the project management team, including level 2 managers, the ES&H officer, the QA manager, the Project Controls Manager/Lead, and others as appropriate. The Project Controls Manager/Lead will ensure that all changes are consistent with the EVMS processes. The Project Technical Board or the Project Management Group may also serve as the Change Control Board provided that these groups include the necessary membership. The composition, duties, and responsibilities of the CCB will be included in the Project Management Plan template.”

## Slide 50: Questions about Change – Contingency, UB, MR
I hear about Contingency, Undistributed Budget, and Management Reserve.
What are they?
Why should I Care?
Contingency = Created by a Combination of Estimate Uncertainty (Bottom-up) & Risk Mitigation (Top-Down) allowances.
Undistributed Budget (UB) = Money Approved but Temporarily not Allocated to Discrete WBS/Activities. Addressed in CA’s EAC.
Management Reserve (MR) = Tool for tracking Cumulative total of Contingency transferred to active budget via Change Control. Note: The portion of contingency retained by PM and is equal to PM’s approval threshold

## Slide 51: More Questions about Change
Who Owns Contingency?
  CAM
  PM
  Funding Agency
Why Do I need to Think About Change Control?
  Responsibility
  Manage
  Inform
How Long Does it Take to Process a Change?

## Slide 52
Change Flowchart

## Slide 53
Questions regarding Change – Initiating BCR
Who Can Initiate A BCR?
  Anyone on Project
  Client
When Can I Initiate BCR?
  Approved Prior to Work Start
    Future = Managing Scope
    Past = Reaction Managed
  Field Changes (Construction Only)

## Slide 54
FNAL Procedure 12.PM-007 Change Control - Clarification
What does this mean?
Response to Who can Initiate
Addresses CAM’s
  Ability to Manage
  Approve Means
    Preliminary
    Continues through Process
    PM/CCB ultimate approval/disapproval
Change Request

## Slide 55
Questions regarding Change – Action Steps
What Actions Do I take when Change is Identified?
  Start Documentation Process
  Iterative Process With PCS
  Communicate
    Alternatives
    Impacts
    Urgency
    Consequence of Not Approving
  Submit BCR
  Wait for Approval

## Slide 56: Change Control Process
Steps to Change Control:
  1. Prepare supporting documentation [CAM]
  2. Fill out and submit Baseline Change Request (BCR) Form in BCR Tool [CAM]
  3. Enter routing data into BCR database [Config Mgr]
  4. Obtain approvals – depends on BCR Level [Config Mgr]
  5. Update cost & schedule information in P6 & Cobra, and finalize BCR database entries [PCS]  details Beyond Scope of this Training
  6. Then actually process
    the changes…

## Slide 57
Questions regarding Change – Gate Keeper
I have Some Changes to Make, but my PCS won’t Process them Now - Why?

## Slide 58
Change Control – PCS Limitations
Can Take Days or Weeks to Process
PM – Prioritizes / Approves
EVMS Guidelines
  Can NOT Change History
  Future ONLY with Four Exceptions
Rate Changes
Obvious Errors
Establishing PMB
Contract Changes

## Slide 59
Identified Change
  How
  When
  Type
When Work can Start
  Work Authorization & BCR Approval
  Demonstrate Management
  Demonstrates Control
Impacts of Change
  Cost
  Schedule
  Scope
  Risks
    Quality
    Safety
Authority / Responsibility for Approvals
Change Control System – Formal Documented Process
Baseline Change Request

## Slide 60: Baseline Change Request Tool
BCR Tool database is used to Manage Changes.
Data Input source is BCR form
Approval Workflow and Routing controlled by Change Manager in Tool
Tracks approval status
Records cost impact (both Preliminary and Final amounts) by type (M&S or Labor) and by Labor resource
Also records schedule impacts (Reflected in P6 Schedule)
Prints detailed report for each BCR
Database maintained by OPSS

## Slide 61: Change Request Form – Generated by BCR Tool

## Slide 62: Change Request Form – Generated by BCR Tool (Cont.)
Title: Very Brief Summary
WBS Number: Single Lowest common WBS Element that encompasses all work.
Example 1: Work affects the following WBS elements 123.01.02, 123.01.04, 123.01.06 then Lowest common WBS Element would be 123.01
Example 2: Work affects the following WBS elements 1234.01.02, 123.01.04, 123.02.01 then Lowest common WBS Element would be 123

## Slide 63: Change Request Form – Generated by BCR Tool (Cont.)
Describe all details of the change such as why it is needed, How need was discovered, Basic BOE information – what is the Basis for the Change (remember the BCR is used instead of BOE and should contain equivalent back-up. Can use Attachments later but at least brief description and note that will bring reviewers to attachment)
Include Consequences of NOT approving this Change. Also, specify and Risk, ESH, Interface, and Scientific impacts.

## Slide 64: Change Request Form – Generated by BCR Tool (Cont.)
Filled out by Change Manager and Read Only for CAM after Request is Submitted.
Who will be Notified. Edited out by Change Manager and Read Only for CAM after Request is Submitted.

## Slide 65: Example: Change Request Detail Report
This printable form is produced by Access for each BCR.
Stored as PDF in DocDB
Contains signature box for approvals
Lists cost, schedule impacts, supporting documents, change type and level, affected L2 subprojects, WBS, justification, technical & risk impacts…

## Slide 66: Example: Change Request Log (Summary)
Summary record of all changes
Tracks contingency and mgmt reserve used

## Slide 67: BCR Control Account Log (Control Account)

## Slide 68: Work Authorization Document (WAD)

## Slide 69
WAD Attachments Examples: Schedule & CAP
Procedure outlines required fields for these reports
WAD information is incomplete without these attachments

## Slide 70: WAD Attachments: Schedule Reports (By CA)

## Slide 71: WAD Attachments: Control Account Plan

## Slide 72: BCR Documentation: Schedule Reports – Three Required
Schedule Impacts Critical Path
Milestone

## Slide 73: BCR Documentation: Validation Reports (CA Impact i.e. Before & After)
Data Subtotaled

## Slide 74: BCR Documentation: Validation Reports (History Unchanged)

## Slide 75: Other Documents Possibly needing Update with BCR
Manage the documents is detailed in the project’s Configuration Management Plan
WBS
WBS Dictionary
Milestone Dict.
PEP
PMP