## Slide 1
Next Steps Toward Production of TDRs
Eric James
Far Detector Technical Board Meeting
August 16, 2018

## Slide 2: Path to TDR
Less than seven months remaining to produce TDRs by April 1, 2019
Completion of initial detector cost estimates on desired time frame (mid-August) was a big step forward
  Thanks to everyone for their efforts to provide this information
Neutrino Cost Group (NGC) will now review the cost information that we have provided

## Slide 3: Cost Estimates
The information provided has been uploaded into the following DUNE DocDB entries:
Please do not modify the contents of these entries while the NCG review is in progress
WBS | Description | DocDB
1.0 | Project Office | 9450
2.1 | SP-TC | 9453
2.2 | SP-APA | 9456
2.3 | SP-ELE | 9459
2.4 | SP-PD | 9462
2.8 | SP-HV | 9465
2.9 | SP-DAQ | 9468
2.10 | SP-CISC | 9471
3.1 | DP-TC | 9474
3.5 | DP-CRP | 9477
3.6 | DP-ELE | 9480
3.7 | DP-PD | 9483
3.8 | DP-HV | 9486
3.9 | DP-DAQ | 9489
3.10 | DP-CISC | 9492

## Slide 4: Cost Estimates – Next Steps
NGC will provide feedback to us and report to the RRB on the time scale of one month
Ami Dave is working to combine the received input into a coherent WBS cost book
  Goal is to see if we can format this in a manner that will be easier to update and maintain
Expect the next NCG review of the cost book to take place in about six months

## Slide 5: TDR Preparation
Next major step is to get the writing of the document underway
LBNC has asked that
  We attempt to minimize the length of the TDR volumes as much as possible
  We provide initial drafts that the committee can begin to study several months prior to the submission of the final documents

## Slide 6: TDR Schedule (Preliminary thoughts)
September 1 - editors appointed
October 1 - outlines due
November 1 – first drafts due
December 1 – second drafts due
February 1 – input from independent reviews of second drafts
March 1 – final drafts due
April 1 – independent reviews of second drafts complete
April 15 – submit final drafts to LBNC

## Slide 7: Next LBNC Review
Next LBNC review is tentatively being planned for December 13-15 at CERN
  Focus on ProtoDUNE results and a more in-depth discussion of DP not possible at last review
LBNC would like access to second drafts of TDR volumes to begin digesting contents, although with understanding that the review itself would be based on the final versions

## Slide 8: TDR Themes
LBNC has continued to hammer on a number of themes which will need to be addressed in the TDRs
  Detector requirements and how these are derived from the physics goals of the experiment
  Identification of risks and strategies for mitigating and/or dealing with these should they be realized
  Plans for additional R&D and how decisions between various design choices will be made
  Definition of interfaces (both between detector sub-systems and with the supporting infrastructure)

## Slide 9: Decision on ProtoDUNEs
On the topic of plans for future integration testing, we will need to decide in the very near future whether to incorporate additional ProtoDUNE running into our planning
CERN SPSC expects us to submit a proposal for future running at its October meeting
Spokespersons have requested input from the consortia on how additional ProtoDUNE running would fit within their current plans

## Slide 10: Other Deliverables Required for TDRs
Finalized Cost Workbook
Final assignments of institutional responsibilities for detector deliverables (funding matrices)
Finalized construction and installation schedule
Complete set of interface documents

## Slide 11: Funding Matrices
Need to update the RRB in September on the status of funding matrices associated with each detector sub-system
Will need to set up another round of phone calls with the consortia leadership teams to review recent developments in advance of meeting
  Target holding these in late August/early September

## Slide 12: Construction Schedule
With initial cost estimate in place, need to focus on further refining construction and installation schedule
Initial inputs received from consortia earlier in the year did not join simply to form a coherent schedule across all sub-systems
I have been working with Mohammed a top-down approach for connecting the individual consortia schedules in a coherent way

## Slide 13: Construction Schedule (cont.)
Once this is finalized, I will need to interact with the consortia leadership teams to more fully develop the schedules associated with their sub-systems
The decision on whether to have a second ProtoDUNE run with production components has a potentially big impact on the schedule
We need to try to have a complete first pass of the schedule on the time scale of the next few months

## Slide 14: Interface Documents
A lot of progress has been made on interface documents over the past few months in conjunction with assembling cost estimates
Have started the process of placing these documents under signature control – need to continue pushing this forward
Have started to place a bit more emphasis on software interfaces – working to identify an Online Computing Coordinator

## Slide 15: Design Reviews
Need to schedule 30% design reviews for SP-DSS, Installation, ITF, SP-PD, and DAQ before the end of this calendar year
  60% Design reviews for all sub-systems would nominally need to be scheduled for the first three months of 2019
Tentative Schedule :
  SP-DSS Review – Next week at CERN
  Installation Review – First week of October at CERN
  ITF Review – Last week of October at SURF
  SP-PD – Late November/Early December at FNAL
  DAQ – Third week of December at CERN