## Slide 1: Cryomodule Lessons Learned
A. Klebaner, G. Wu
International Workshop on Cryomodule Design and Standardization
September 7, 2018

## Slide 2: Outline
  Introduction
  Lessons Learned during Cavity Production
  Lessons Learned during String Assembly
  Lessons Learned during Cryomodule Testing
  Lessons Learned from Cryomodule Transportation (skipped, see Peterson presentation)
  Summary
2018-09-07
International Workshop on Cryomodule Design and Standardization
Major Lessons Only

## Slide 3: Outline
  Introduction
  Lessons Learned during Cavity Production
  Lessons Learned during String Assembly
  Lessons Learned during Cryomodule Testing
  Lessons Learned from Cryomodule Transportation (skipped, see Peterson presentation)
  Summary
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 4: LCLS-II Cryogenic Systems overview:
Cryoplant:
2 x 4 kW@2.0K
3.7 kW nom. load
35 Cryomodules
(+2 3.9GHz CM)
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 5: Some Changes during the Production
Added 5 additional 1.3 GHz CMs
  1 spare + 4 production extras
Added 1 spare 3.9 GHz CM
  Goal to select best 35 of 40 – 1.3 GHz and 2 of 3 3.9 GHz CMs for linac
  Maintain extras for field replacement as necessary
Ordered additional cavities to account for production yield
Installation of fluxgate magnetometers in all CMs
Optimized cavity processing recipes for cavity production
Added cryomodule test cycles for cooldown optimization
Increased vendor oversight for cavity production
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 6: Cryomodule Progress
  1.3 GHz CM Production
    29 of 35 1.3 GHz CMs are in production or complete
    Six broken for various reasons
  1.3 GHz CM Testing
    11+10 CM tests complete
    Average Q0 > 2.7e10
    Average Gradient > 16 MV/m
6
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 7: Cryomodule Production at Fermilab
Courtesy of Sam Posen
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 8: Key Technical Challenges
CM Assembly
  Tight Schedule
  Design changes
  String leaks outside of the cleanroom
CM Testing
  Maintaining high Q0 in the CM
  Field emission
  Microphonics mitigation
  HOM tuning / end group heating
  Cooldown optimization
  String leak after warm-up
  Transportation
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 9: Outline
  Introduction
  Lessons Learned during Cavity Production
  Lessons Learned during String Assembly
  Lessons Learned during Cryomodule Testing
  Lessons Learned from Cryomodule Transportation (skipped, see Peterson presentation)
  Summary
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 10: Nitrogen Doped Cavity Challenges
Cavity production issues:
  Poor flux expulsion material resulted cavity performance below specification in cryomodule
Lessons learned
  Improved understanding of niobium flux expulsion
  Improved material/cavity processing recipe to recover flux expulsion capability.
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 11: RI: Q0 Results
RI has completed fabrication of original order of 133 cavities
121 cavities have been tested so far at JLab and Fermilab
TD Cavities 900/200 preparation consistently exceed LCLS-II spec
Slide by Dan Gonnella of SLAC
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 12: RI: Q0 Results
RI has completed fabrication of original order of 133 cavities
121 cavities have been tested so far at JLab and Fermilab
TD Cavities 900/200 preparation consistently exceed LCLS-II spec
NX Cavities at 900oC have middling results
Slide by Dan Gonnella of SLAC
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 13: RI: Q0 Results
RI has completed fabrication of original order of 133 cavities
121 cavities have been tested so far at JLab and Fermilab
TD Cavities 900/200 preparation consistently exceed LCLS-II spec
NX Cavities at 900oC have middling results
950 and 975oC have further improved upon the NX cavities’ performance
Slide by Dan Gonnella of SLAC
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 14: Outline
  Introduction
  Lessons Learned during Cavity Production
  Lessons Learned during String Assembly
  Lessons Learned during Cryomodule Testing
  Lessons Learned from Cryomodule Transportation (skipped, see Peterson presentation)
  Summary
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 15: J1.3-06 Status
J1.3-6
Accidentally vented during preparation for leak check of 2 phase circuit
  GHRP cap slipped and impacted right angle valve
  String fast bled up to just under 100 torr.
J1.3-06
Cavity and couplers will require reprocessing
Courtesy of Bob Legg of JLAB
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 16: J1.3-06 Lessons Learned
New assembly procedure and tooling for GHRP cap installation at WS3 and WS5.
J1.3-06
Portable lift used to both lift GHRP cap and protect the Right Angle Valve; Safer for both employees and equipment.
Looking into a plug with o-ring to replace GHRP cap for vacuum leak checks. Lighter, safer.
Metal bellows covers put in place to prevent accidental venting during prep for testing.
Courtesy of Bob Legg of JLAB
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 17: F1.3-03 HOM Feedthrough Thermal Strap Loose
F1.3-03
CAV3 quenched prematurely at 11 MV/m.
  HOM end group heating.
  One bolt thread damaged and provided false torque number.
Washer loose
Thermal braid head completely loose
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 18: F1.3-03 Lessons Learned
F1.3-03
Improved procedure to double check the integrity of the HOM thermal Straps
Improved procedure to inspect bolts quality
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 19: F1.3-03 Cold Leak Developed
F1.3-03
Cold Leak Discovered during Cryomodule Warm up
BPM Feedthrough flanges leaked
  Three out of four seals leaked
  Leak rate was ~8.5e-5 mbar.L/sec
    Leak was considered too big for clean beam line.
    Decision was made to dis-assemble
Grade 2 Titanium bolts did not provide sufficient sealing force.
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 20: F1.3-03 Lessons Learned
F1.3-03
Replaced Grade 2 titanium bolts with Gr5 titanium studs.
Increase the torque strength from 12 to 16 N.m
Measure seal crush to ensure sufficient sealing cross section
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 21: F1.3-06 Fasteners Loosened
Washers not installed and one bolts dis-lodged and one completely loosened.
2018-09-07
International Workshop on Cryomodule Design and Standardization
Courtesy of A. Burrill of SLAC
Several other fasteners loosened
in upper cold mass assembly

## Slide 22: F.13-06 Fastener Lessons Learned
In addition to lessons learned as in F1.3-03:
Added QC step in traveler to inspect all fasteners and their torques both in component level, as well as completed string assembly.
Established a comprehensive fastener torque table and included into all the relevant travelers.
Improved fastener design with lock washers or loc-tite application.
Increased vendor oversight.
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 23: J1.3-09 and J1.3-11 Helium Vessel Bellows Damaged
J1.3-09 Bellows was found damaged on 5 July,
  Visual inspection of all bellows on in process cryomodules (J1.3-09-11-12-13) followed
  We found one additional bellows damaged on J1.3-11
  Completed cryomodules (J1.3-02 – J1.3-07) will be inspected during subsequent work
  JL1.3-08 and JL1.3-10, were in the process of acceptance testing, no leaks found
J1.3-09
J1.3-11
J1.3-09 damage was found after a failed leak check and disassembly of the cryomodule
J1.3-11 was in an earlier stage of assembly and the damage was found during a visual inspection
2018-09-07
International Workshop on Cryomodule Design and Standardization
Courtesy of E. Daly of JLAB

## Slide 24: J1.3-09 and J1.3-11 Lessons Learned
The JLab team has extended the risk matrix to all bellows in the cryomodule
  Continuous improvement extends this to the cryomodule as a whole
  FNAL will be included
Apply lessons learned to other cryomodule production activities
  CEBAF cryomodule production and rework
  Cryomodules for other projects (SNS PPU, LCLS-II HE)
Training matrix developed as part of the improved work controls identifies individual’s qualifications
Matrix is now the basis for staff development plans and will be a continuing part of the cryomodule production at JLab
  Every supervisor has the matrix and only assigns work to qualified technicians
  Every technician and supervisor has their own qualification matrix
  Each individual is expected to know their qualifications and work only those activities they are qualified for
2018-09-07
International Workshop on Cryomodule Design and Standardization
Courtesy of E. Daly of JLAB

## Slide 25: Outline
  Introduction
  Lessons Learned during Cavity Production
  Lessons Learned during String Assembly
  Lessons Learned during Cryomodule Testing
  Lessons Learned from Cryomodule Transportation (skipped, see Peterson presentation)
  Summary
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 26: Microphonics Sources and Mitigations
Cryogenic Valve Plumbing
  Thermal Acoustic Oscillations in the Valve Stems
  Helium Leakage into Cooldown Circuit
Cavity 1 Mechanical Support
  Modification and Retrofit Options
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 27: Cryogenic Valve Plumbing – Improved Valve Stems
TAOs are a pressure/temperature oscillation in cryogenic lines (in this case, valve stems)
  During testing, wipers were added to close space in valve stem, acting as a damping term for the TAOs
  Significant improvement in heat load and microphonics levels and stability for both F1.3-01 and J1.3-01
  Optimized valve stems with wipers were used during F1.3-02 testing, and will be used going forward for both labs
    4-5 wipers, positioned to keep temperature ratio <4 as recommended by literature
    Radiation hard material (PEEK)
DN10
DN6
Before
After
Optimized wiper placement going forward
Slide by Jeremiah Holzbauer
2018-09-07
International Workshop on Cryomodule Design and Standardization
27

## Slide 28: Cryogenic Valve Plumbing – Reverse Flow Path
  Test results show valve reversal (lower press in stem) significantly reduces/eliminate TAOs there
    F1.3-01 configuration has valve stem at supply pressure (~3 bar)
    Reversing flow will lower this pressure to sub-atmospheric, requiring guard gas to prevent contamination
    All cryomodules will have guard gas, reversed valves
  Additional effort to mitigate TAOs in cryogenic distribution system should improve inlet temperature at test stand
Reversed Flow Pattern (CM2)
3 bar Supply
~23 Torr
pCM Flow Pattern
~23 Torr
3 bar Supply
Slide by Jeremiah Holzbauer
2018-09-07
International Workshop on Cryomodule Design and Standardization
28

## Slide 29: Valve Modification Improvement
Comparing performance of the standard cryogenics configuration, the microphonics environment in the F1.3-02/03/04 is a factor of ~10 improved
Significant improvements in stability of the system, leading to a far more predictable detuning environment
pCM As Cooled Down
F1.3-03
After Improvements
Slide by Jeremiah Holzbauer
2018-09-07
International Workshop on Cryomodule Design and Standardization
29

## Slide 30: Cryogenic Valve Plumbing – Cooldown Valve Leakage
Thermalized Detuning
Post CD Stem Swap
F1.3-04 presented with higher than expected microphonics, worsening as the cryomodule thermalized
Noise was narrowband and showed complex spatial and spectral distribution in cryomodule
Testing showed strong correlation with cooldown circuit, eventually proven to be coherent bubbling due to cooldown valve leakage
Swapping valve stem returned expected performance, although testing schedule prevented detailed studies
Tails seen in ‘post-swap’ data are likely due to continued thermalization of cryomodule after cooldown
Additional QA check step now included to prevent valve leakage in the future
Slide by Jeremiah Holzbauer
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 31: Cavity 1 Mechanical Connections – Mitigation Beamline Gate Valve Bellows
Replacing spool piece between cavity 1 and gate valve with a bellows is non-trivial
Corrective fix includes extending tuner arms with fixture to connect to gate valve
  When replacing spool piece with bellows, fixture fully supports gate valve
  Current supports are long arms connected to the 300 mm pipe with needle bearing for the longitudinal motion
With gate valve is supported by frame/helium vessel, the spool piece can be replaced with a bellows to separate mass from cavity/tuner system
First cryomodule with bellows to be tested will be F1.3-06 (on deck at FNAL)
Extended Tuner Arms
Fixture with Bellows
Slide by Jeremiah Holzbauer
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 32: Outline
  Introduction
  Lessons Learned during Cavity Production
  Lessons Learned during String Assembly
  Lessons Learned during Cryomodule Testing
  Lessons Learned from Cryomodule Transportation (skipped, see Peterson presentation)
  Summary
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 33: F1.3-05 and F1.3-06 Coupler Bellows Cracked during Transportation
Failed bellows examined after sectioning them:
SLAC (Chris Pearson) Report on Cavity 4 Bellows: “This is an example of high stress low cycle fatigue. That is, the material at the fracture location experienced multiple bending stress cycles at or above the yield strength, work hardening locally and eventually failing in a brittle manner.”
SGS report on Cavity 5 Bellows: “Fatigue fracture initiated on the outside surface at multiple locations at grain boundaries that were infiltrated with braze metal. Uni-directional bending stresses initiated and propagated the multiple fatigue cracks completely through the bellows.”
Cavity 4
Cavity 5
2018-09-07
International Workshop on Cryomodule Design and Standardization
Courtesy of C. Adolphsen of SLAC

## Slide 34: F1.3-05 and F1.3-06 Lessons Learned
See Tom Peterson’s slides.
2018-09-07
International Workshop on Cryomodule Design and Standardization

## Slide 35: Summary
A few significant cryomodule incidents have occurred during LCLS-II Cryomodule production.
Incidents have been addressed.
Lessons learned greatly benefit future projects such as PIP-II.
2018-09-07
International Workshop on Cryomodule Design and Standardization