## Slide 1: MI/RR Shutdown Status
Denton Morris
0900 Meeting
September 7, 2018

## Slide 2: 2018 Shutdown
  “I wouldn’t want to be you.”
  -Almost everyone

## Slide 3: 2018 Shutdown
  Tunnel work:
  Recycler sextupole and skew quad stand upgrade
  Alignment completed MI-10 sector stands
  Four new sextupoles and stands installed (ready to connect)
  Four to go

## Slide 4: 2018 Shutdown
  Tunnel work:
  8 GeV Multiwires
  Installing four multiwires: 826, 827, 829, 836
  All four multiwires and stands are in place
  Vacuum pipe welded
  Flanges connected
  Performing rough leak check today
  Monday alignment
  Final leak check
  Leak check continues through RF section
  RF maintenance continues

## Slide 5: 2018 Shutdown
  LCW maintenance
  Repaired leaking valves and repaired a leak on dipole bus

## Slide 6: 2018 Shutdown
  MI-60 Upper Dipole Bus choke water LCW leak
  Repaired in place
  Pending work:
  MI-40 abort vacuum
  Septa RGA stand installation
  MI-10 SEY sample change (Monday)
  Absorber room detector installation
  Miscellaneous ion pump maintenance

## Slide 7: 2018 Shutdown
  MI-8 GeV, MI-10 and MI 20-62 enclosures will be re-keyed to operational keys for Tuesday morning access.
  Monday clear LOTO locks from MI-10 lock box.