## Slide 1: Cryo Assembly, Cold Mass
A. Vouris
Cryo Assy Meeting
September 10th, 2018

## Slide 2: Cold Mass Tooling & Design Status
Empty Shell
  Vouris - Shells back at MK Mfg for re-work – this week, looking to set up shop visit this afternoon
  SS End ring modified for MQXFS1e and returned to IB-1
Cold Mass Shell Design
  Vouris - Workflow steps in process
Lifting Beam Procurement
  Charles Orozco – to review and revise purchase spec
CM Weld Tooling
  Justin Carmichael analysis looks good, write up started (passed on to summer help – Colin).
  Charles Orozco – to do formal analysis on rolling clamp and start write up
Alignment Tooling
  Bill Robotham - reviewing and commenting on magnet alignment fixtures – modifications in progress
  Bill Robotham/Vouris – End Cover alignment tooling model completed by Design Drafting and emai forwarded for comments.

## Slide 3: BUS and Interconnect Status
  Most work last week focused on the bus bar validation test, or the “Bus Demonstrator”. This is a bus, including housing and “attachment clips” identical in cross section to the production design. It will be installed into MQXFS1. The magnet will be retested as MQXFS1e, to demonstrate the viability of the bus, bus insulation, and housing design. Also during testing, spot heaters and voltage taps will be placed onto each side of the bus to induce quenches and measure time of travel. Work during the past week:
Bus Bar Validation test on MQXFS1e
Demonstrator bus configuration has been finalized.
A practice demonstrator bus has been successfully fabricated using standard (unreacted Nb3Sn) cable.
Fabrication of the final demonstrator busses that will be installed into MQXFS1e has begun.
Spot heater and voltage tap configuration and wiring have been established and installed on the practice bus.
A test section of the practice bus with housing and “clips” has been successfully installed into the bus port of MQXFS1.
An opening to accept the bus has been machined into the instrumentation ring on the return end.

## Slide 4: BUS and Interconnect Status
Other Work on Bus and Interconnection last week
Rework on mockup to re-model the expansion loop with the actual bus (current mockup uses unreacted Nb3Sn cable drop-offs from coil fabrication) will begin as soon as more NbTi bus is available. The reworked mockup will include the adjusted space for expansion loops between the splice box and the dome.
2nd (final) iteration bus wrapping device parts have all arrived and the device is being assembled.
Controller for the long bus soldering fixture will be ready this week. The fixture is complete and will be tested as soon as the controller is ready.
Drawings of the bus insulation and routing from the magnet to the interconnection are in process.
Drawings of the splice soldering fixture were released and fixture is ordered.
Design work on expansion loop hold down mechanisms (on the face of the Q1/Q3) has begun.