## Slide 1: Muon Campus Status
Jerry Annala
Shutdown week 10
September 14, 2018

## Slide 2: Week 10
Water leak on H748 (Injection line bend magnet)
  Most likely will require winding a new coil
  5 weeks for repair and return to tunnel
  There are options to get on the air sooner for g-2 if necessary
V003 is in the tunnel ready for installation
M4 line construction continues
  Downstream under vacuum
  Alignment is complete
  Beam pipe welding continues
M5 line work still to complete
  Cooling wedges to be installed next week

## Slide 3: This weekend
Delivery Ring and Extraction enclosure will host a tour on Saturday September 15. Tunnel cleaning
  Radiation survey and de-posting takes place today