## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly Reports
Guram Chlachidze
Sep. 14th, 2018

## Slide 2: Cryo-mechanical upgrades
Adapter box & Interconnect design work in progress
  More requests placed for D&D: Detailing thermal shield bridges between the Feed box and Adapter box.
  Detailing End box vacuum shell modifications
  Need to review existing bus support drawings
Vacuum adapter design work in progress
  Adapter box to cryo-assembly: preliminary drawings are ready for review
Resolving recommendations from the Process design review
  Some design revision is required
Stand 4 process controls (Off-project)
  Cryo-sector takes responsibility for the upgrade.
  Most of the equipment already purchased, should arrive in October.
  PLC Logic specifications will be defined next

## Slide 3: Other On-Project upgrades
25 T crane upgrade
Prints are under final review (FESS, IB1)
Delivery date is Oct. 26, 2018
Magnetic measurement Systems
Procuring parts for the DSA and SSW measurement systems
Requisitions will be placed for the probe motion system
Cable spooler mock-up assembly in progress (Off-project). Proof-of-concept tests are expected soon.

## Slide 4: More Off-Project upgrades
QPM
Interface document developed for communication between the AQD and DQD controllers
DQD controller design still in progress
AQD and DQD integrations test are expected in Nov. 2018
First components for the stand 4 AQD and DQD systems arrived
Remaining requisitions will be issued after the integration tests are successfully completed for mu2e