## Slide 1: A new layout (proposal) 14-09-2018

## Slide 2: Some new requirement
Avoid any dependence on filling and cooling between det#1 and det#2
Test complete double APA (+electronics and PD) or CRP just before inserting it into the cryostat
Det #1 in cavern 1
Det #2 in cavern 2
Cold tests in dedicated cold boxes in the cavern clean room
Cold boxes for double APA
or
Cold boxes for individual CRPs

## Slide 3
Det#1
Det#2
Det#3
Det#4

## Slide 4: Two caverns implications
Cavern 2 beneficial occupancy after the warm vessel det #1 is assembled (t0+9m). This means cavern 2 beneficial occupancy 8-12 months after cavern 1 has been released.
Cavern 2 equipped with general services (HVAC, electricity, light, …). This means adding ~4-5M$ to the initial investments by CF
Advantages:
Det#1 cooling independent from det#2 status/progress. This will have important implication on the overall schedule
Might allow parallel activities and schedule independency
For the first two detectors more space available for storage and assembly work organization
More quality controls before last step of installation
This might liberate resources from the ITF facility
Problems:
Number of people underground
Schedule of the second cavern

## Slide 5
beneficial occupancy cavern 1
STEP#0
excavation cavern 2
T=T0

## Slide 6
Det#1 warm vessel assembled
STEP#1
excavation cavern 2
steel material
people : 40
people : 20?
T=T0+9m
total people : 60

## Slide 7
Det#1 warm vessel assembled
STEP#2
people : 5
people : 20?
beneficial occupancy cavern 2
T=T0+9m+3m
total people : 25

## Slide 8
Det#1 cold vessel assembled + cryo mezzanine
STEP#3
people : 35
people : 40
material / boxes
Det#2 warm vessel assembly
steel material
T=T0+9m+12m
total people : 75

## Slide 9
Det#1 installation
STEP#4
people : 34
people : 35
material
Det#2 cold vessel assembly + cryo mezzanine
material / boxes
T=T0+9m+12m+12m
total people : 69

## Slide 10
Det#1 cooling
STEP#5
people : 10
people : 34
Det#2 installation
material
T=T0+9m+12m+12m+12m
total people : 44

## Slide 11
Det#1 commissioning/operation start
STEP#6
people : 15
people : 10
Det#2 cooling
T1=T0+45m T0=Jan-2023 ->T1=Sep 2026
total people :20

## Slide 12
Det#1 in operation
STEP#6
people : 15
people : 15
Det#2 cooled and start commissioning
T2=T0+57m T0=Jan-2023 ->T2=Sep 2027
total people : 30

## Slide 13
3 cold boxes : ~14m high, N2 gas cooling
Integration of the photon detectors bars
Final integration of the electronics
Final cabling of the 2 APAs
Test with final DAQ
Integration of the FC/cathode
Use bridge crane for manipulations
Local storage
Material SAS
Clean room
to be optimized
total people max in any period : ~ 70p/cavern

## Slide 14: Detector 3 and 4
Probably different technology
Lesson learned, will make it easier
Yes, more difficult because of less space