## Slide 1: What happens at the ITF and at SURF for Cold Electronics
Marco Verzocchi - Fermilab
Integration Test Facility and Installation Workshop @ SURF
29-31 October 2018

## Slide 2: What would we do at the ITF ?
Reception test (warm) for the Front End Motherboards
  Would still like to have a CTS (cryogenic test system) to spot check a few FEMBs and check FEMBs that may fail testing in the cold box at SURF (just need to be able to refill LN dewar)
  To be done in the “CE+CISC” laboratory
Install the FEMBs on the APAs and perform quick test
  Expect rate 1 day per APA
  In current plan for first detector APAs arrive at ITF before the FEMBs
Repackage all other components for transport to SURF
Prepare cold cable bundles on spools (this should be done in a clean room)

## Slide 3: What would we need at the ITF ?
If we do not do cold testing at the ITF we can relax some requirements
  We may do the testing with a portable DAQ / power system (i.e. 1 FEMB at at time), instead of testing 20 FEMBs at once (which requires a full WIEC / rack)
  We will not need a full CISC / Detector Safety System at the ITF

## Slide 4: What would we do at SURF (i) ?
Need to set up racks for power/control/readout of APAs in 3 cold boxes and commission readout of the cold boxes
  Are these racks on the detector mezzanine or closer to the cold boxes ? Are these additional racks on top of the ones used for the readout of the installed APAs ? (will come back to this in slide 7)
As soon as we have occupancy of the detector mezzanine we should start populating the racks in the mezzanine with all the CE, PD, CISC, DAQ components and put in place all the fibers between the CUC and the detector, plus all the fibers/cables between the racks and the cryostat penetrations
Ideally we have the cryostat penetrations for a row of APAs ready on top of the cryostat ~2 weeks before the installation of the corresponding row of APAs

## Slide 5: What would we do at SURF (ii) ?
Once the APA and cables are in the clean room:
  Route the cables through the APA frames and connect them to the FEMBs, arrange the cables in the trays
  Perform a quick test (warm) on a FEMB by FEMB basis before moving the APA pair in the cold box
  Cold box testing: need a patch panel and extension cables to avoid routing the cables through the cryostat penetration every time
    This needs to be demonstrated, may need active patch panel with signal repeaters (receivers / transmitters)
    Cold Electronics needs to do this test in 2019, need to find (design ?) the appropriate ASICs
  After the cold box testing the APA pair is moved into the cryostat and put in its final position

## Slide 6: What would we do at SURF (iii) ?
Once the APA is its final position:
  Route the cables through the cryostat penetrations and connect them to the flanges, attach the WIEC, perform final readout test
  Install next APA in same column only after test completed
    This included a bias voltage test in the original plan, including providing bias to electron diverters and field cage termination electrodes, which cannot be performed if CPA is not installed / deployed (perform partial test with temporary load, repeat test when CPA deployed)
Keep on monitoring CE while the installation of following rows of APAs continues
  This means that installation of the corresponding DAQ backend precedes the installation of a row of APAs

## Slide 7: What would we need at SURF ?
One slice of racks / DAQ backend needs to be available for the commissioning of the cold boxes
  If the cold boxes are on detector 1 this could be part of the readout of detector 1, except that we will continue needing it also for the second single phase detector. This may need to be an extra DAQ slice and an extra rack
Slow control and safety system for detector (SS4D) for the cold boxes
Mini-racks for PD electronics need to be in place (and connected to DAQ backend / controls) before we route cables through the cryostat penetrations