## Detailed Schedule Summary
|  | # | 2020 |  |  | 2021 |  |  |  | 2022 |  |  |  | 2023 |  |  |  | 2024 |  |  |  | 2025 |  |  |  | 2026 |  |  |  | 2027 |  |  |  | 2028 |  |  |  | 2029
Task | Group | Month | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Excavation Cavern #1 | CF | 31 | 2020 Q2: Cavern#1 (North) Cavern 2 (CUC)
Excavation Cavern #3 | CF | 20 | 2023 Q2: Cavern#3
N2 piping in the shaft | SURF | 12 | 2023 Q4: N2 Piping
CUC Infrastruc and DAQ | DUNE | 12 | 2023 Q2: CUC Infra; 2024 Q1: DAQ
Install Warm Dec #1 | CERN | 9 | 2023 Q2: Warm 1
Install Cold Dec #1 | GTT | 12 | 2024 Q1: Cold Struct. #1
Infrastructure Det #1 | DUNE | 6 | 2024 Q3: Infra
Assembly SP Dec #1 | DUNE | 12 | 2025 Q1: Detector #1 SP
TCO Closing | CERN | 3 | 2026 Q1: TCO
Purge/Fill Dec #1 | CERN | 15 | 2026 Q2: Pur; 2026 Q3: Fill Dec #1
Install Warm Dec #2 | CERN | 9 | 2024 Q2: Warm 2
Install Cold Dec #2 | GTT | 12 | 2025 Q1: Cold Struct. #2
Infrastructure Det #2 | DUNE | 6 | 2025 Q3: Infra & DAQ
Assembly Dec DP #2 | DUNE | 12 | 2026 Q1: Detector #2 DP
TCO Closing | CERN | 3 | 2027 Q1: TCO
Purge/Fill Dec #2 | CERN | 15 | 2027 Q2: Pur; 2027 Q3: Fill Dec #2
Install Cryo Equipment | CERN | 12 | 2024 Q3: Cryo #1; 2025 Q2: Cryo #2
Install Warm Dec #3 | CERN | 9 | 2022 Q3: B.O. Cavern #1 Apr 2023; 2027 Q4: Warm 3
Install Cold Dec #3 | GTT | 12 | 2028 Q3: Cold Struct. #3
Assembly Dec #3 | DUNE | 18 | 2023 Q3: B.O. Cavern #3 Apr 2024; 2029 Q1: Infra; 2029 Q3: Det #3
Install Warm Dec#4 | CERN | 9 | 2029 Q1: Warm 4
Install Dec#4 | GTT | 12
Assembly Dec#4 | DUNE | 18
Estimated Number if FTEs Underground per shift-Assume 2 shifts per day
CF-Day |  |  | 2020 Q2: 25; 2020 Q3: 25; 2020 Q4: 25; 2021 Q1: 25; 2021 Q2: 25; 2021 Q3: 25; 2021 Q4: 25; 2022 Q1: 25; 2022 Q2: 25; 2022 Q3: 25; 2022 Q4: 25; 2023 Q1: 25; 2023 Q2: 25; 2023 Q3: 25; 2023 Q4: 25; 2024 Q1: 25
CF-Night |  |  | 2020 Q2: 15; 2020 Q3: 15; 2020 Q4: 15; 2021 Q1: 15; 2021 Q2: 15; 2021 Q3: 15; 2021 Q4: 15; 2022 Q1: 15; 2022 Q2: 15; 2022 Q3: 15; 2022 Q4: 15; 2023 Q1: 15; 2023 Q2: 15; 2023 Q3: 15; 2023 Q4: 15; 2024 Q1: 15
CERN-Warm-Day |  |  | 2023 Q2: 25; 2023 Q3: 25; 2023 Q4: 25; 2024 Q1: 5; 2024 Q2: 25; 2024 Q3: 25; 2024 Q4: 25; 2025 Q1: 5; 2027 Q4: 25; 2028 Q1: 25; 2028 Q2: 25; 2028 Q3: 5; 2029 Q1: 25; 2029 Q2: 25; 2029 Q3: 25; 2029 Q4: 5
CERN-Warm-Night |  |  | 2023 Q2: 15; 2023 Q3: 15; 2023 Q4: 15; 2024 Q2: 15; 2024 Q3: 15; 2024 Q4: 15; 2027 Q4: 15; 2028 Q1: 15; 2028 Q2: 15; 2029 Q1: 15; 2029 Q2: 15; 2029 Q3: 15
GTT-Cold-Day |  |  | 2024 Q1: 15; 2024 Q2: 15; 2024 Q3: 15; 2024 Q4: 15; 2025 Q1: 15; 2025 Q2: 15; 2025 Q3: 15; 2025 Q4: 15; 2026 Q1: 5; 2027 Q1: 5; 2028 Q2: 15; 2028 Q3: 15; 2028 Q4: 15; 2029 Q1: 15; 2029 Q2: 15; 2029 Q3: 15; 2029 Q4: 15
GTT-Cold-Night |  |  | 2024 Q1: 15; 2024 Q2: 15; 2024 Q3: 15; 2024 Q4: 15; 2025 Q1: 15; 2025 Q2: 15; 2025 Q3: 15; 2025 Q4: 15; 2026 Q1: 5; 2027 Q1: 5; 2028 Q2: 15; 2028 Q3: 15; 2028 Q4: 15; 2029 Q1: 15; 2029 Q2: 15; 2029 Q3: 15; 2029 Q4: 15
CERN-Cryo |  |  | 2024 Q3: 8; 2024 Q4: 8; 2025 Q1: 8; 2025 Q2: 8; 2025 Q3: 8; 2025 Q4: 8; 2026 Q1: 8; 2026 Q2: 4; 2026 Q3: 4; 2026 Q4: 4; 2027 Q1: 4; 2027 Q2: 4; 2027 Q3: 4; 2027 Q4: 4; 2028 Q1: 4; 2028 Q2: 4; 2028 Q3: 4; 2028 Q4: 4
DUNE Infra & DAQ-Day |  |  | 2023 Q2: 5; 2023 Q3: 5; 2023 Q4: 10; 2024 Q1: 10; 2024 Q2: 10; 2024 Q3: 10; 2024 Q4: 10; 2025 Q3: 5; 2025 Q4: 5; 2026 Q1: 5; 2026 Q2: 5; 2028 Q4: 5; 2029 Q1: 5; 2029 Q2: 5; 2029 Q3: 5; 2029 Q4: 5
DUNE-Day |  |  | 2024 Q1: 5; 2024 Q2: 5; 2024 Q3: 5; 2024 Q4: 15; 2025 Q1: 32; 2025 Q2: 32; 2025 Q3: 32; 2025 Q4: 32; 2026 Q1: 32; 2026 Q2: 32; 2026 Q3: 32; 2026 Q4: 32; 2028 Q4: 5; 2029 Q1: 5; 2029 Q2: 32; 2029 Q3: 32; 2029 Q4: 32
DUNE-Night |  |  | 2024 Q1: 5; 2024 Q2: 5; 2024 Q3: 5; 2024 Q4: 15; 2025 Q1: 32; 2025 Q2: 32; 2025 Q3: 32; 2025 Q4: 32; 2026 Q1: 32; 2026 Q2: 32; 2026 Q3: 32; 2026 Q4: 32; 2028 Q4: 5; 2029 Q1: 5; 2029 Q2: 32; 2029 Q3: 32; 2029 Q4: 32
SURF-Day |  |  | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15 | 15
SURF-Night |  |  | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5 | 5
Total FTEs Carvern #1 4910 level-Day |  |  | 2023 Q2: 25; 2023 Q3: 25; 2023 Q4: 25; 2024 Q1: 25; 2024 Q2: 20; 2024 Q3: 20; 2024 Q4: 30; 2025 Q1: 32; 2025 Q2: 32; 2025 Q3: 32; 2025 Q4: 32; 2026 Q1: 5; 2027 Q4: 25; 2028 Q1: 25; 2028 Q2: 20; 2028 Q3: 15; 2028 Q4: 20; 2029 Q1: 20; 2029 Q2: 32; 2029 Q3: 32; 2029 Q4: 32
Total FTEs Carvan # 3 4910 level-Day |  |  | 2023 Q2: 25; 2023 Q3: 25; 2023 Q4: 25; 2024 Q1: 25; 2024 Q2: 25; 2024 Q3: 25; 2024 Q4: 25; 2025 Q1: 20; 2025 Q2: 15; 2025 Q3: 15; 2025 Q4: 15; 2026 Q1: 32; 2026 Q2: 32; 2026 Q3: 32; 2026 Q4: 32; 2028 Q3: 25; 2028 Q4: 25; 2029 Q1: 25; 2029 Q2: 15; 2029 Q3: 15; 2029 Q4: 15
Total FTEs Underground per Day Shift |  |  | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 40 | 70 | 70 | 75 | 95 | 70 | 78 | 88 | 75 | 70 | 75 | 75 | 65 | 56 | 51 | 51 | 24 | 19 | 19 | 44 | 44 | 59 | 39 | 44 | 65 | 92 | 92 | 72
Total FTEs Underground per Night Shift |  |  | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 20 | 35 | 35 | 35 | 40 | 40 | 40 | 50 | 52 | 52 | 52 | 52 | 42 | 37 | 37 | 37 | 10 | 5 | 5 | 20 | 20 | 35 | 20 | 25 | 40 | 67 | 67 | 52

## Detector #1 SP
2025
Detector #1 SP
Task | Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Crossing Tibes/Flanges | bar: Detector #1 SP Jan to Detector #1 SP Feb
Cryostat Internal Piping | bar: Detector #1 SP Jan to Detector #1 SP Feb
DSS | bar: Detector #1 SP Mar
First EndWall | bar: Detector #1 SP Apr
Drift Volume 1-2 | bar: Detector #1 SP May
Drift Volume 3-48 | bar: Detector #1 SP Jun to Detector #1 SP Oct
Drift Volume 49-50 | bar: Detector #1 SP Nov
Last End Wall | bar: Detector #1 SP Dec

## Single APA Path
Week 1-APA & CPA Schedule
|  |  | Day 1 |  |  |  | Day 2 |  |  |  | Day 3 |  |  |  | Day 4 |  |  |  | Day 5 |  |  |  | Day 6 |  |  |  | Day 7
| APA |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2 |  | Shift 1 |  | Shift 2
| Task | Location | 6:00 | 11:00 | 16:00 | 21:00 | 6:00 | 11:00 | 16:00 | 21:00 | 6:00 | 11:00 | 16:00 | 21:00 | 6:00 | 11:00 | 16:00 | 21:00 | 6:00 | 11:00 | 16:00 | 21:00 | 6:00 | 11:00 | 16:00 | 21:00 | 6:00 | 11:00 | 16:00 | 21:00
APA Pair #1
1 | T/B APA into Tower | SAS | 6 | 6
2 | Test PD, Join APA | SAS |  |  | 6
3 | Move APA to Work Station | SAS |  |  |  | 6
4 | Cable work/Test | WS-1 |  |  |  |  | 4 | 4 | 4 | 4
5 | Cable management/CB Cable | WS-1 | [8 empty] | 4
6 | Remove Protective panels | WS-1 | [9 empty] | 4
7 | Photogrammtry/survey | WS-1 | [10 empty] | 4 | 4
8 | Close up Cold Box/Warm test | CB-1 | [12 empty] | 2 | 2
9 | Cool Down | CB-1 | [14 empty] | 2 | 2 | 2 | 2
10 | Cold Tests | CB-1 | [18 empty] | 2 | 2 | 2 | 2
11 | Warm Up | CB-1 | [22 empty] | 2 | 2 | 2 | 2
12 | Open Cold Box -Remove | CB-1 | [26 empty] | 2 | 2
13 | Move to cryostat-Position | Cryo | 4 | 4
14 | Final Cable-Cryostat-in & out | Cryo |  |  | 4 | 4 | 4 | 4
15 | DAQ Test | Cryo | [6 empty] | 4 | 4
16 | Deploy | Cryo | [8 empty] | 4 | 4
17 | Final Test | Cryo | [10 empty] | 4 | 4
APA Pair #2
1 | T/B APA into Tower | SAS |  |  |  |  | 6 | 6
2 | Test PD, Join APA | SAS | [6 empty] | 6
3 | Move APA to Work Station | SAS | [7 empty] | 6
4 | Cable work/Test | WS-2 | [8 empty] | 4 | 4 | 4 | 4
5 | Cable management/CB Cable | WS-2 | [12 empty] | 4
6 | Remove Protective panels | WS-2 | [13 empty] | 4
7 | Photogrammtry/survey | WS-2 | [14 empty] | 4 | 4
8 | Close up Cold Box/Warm test | CB-2 | [16 empty] | 0 | 0
9 | Cool Down | CB-2 | [18 empty] | 2 | 2 | 2 | 2
10 | Cold Tests | CB-2 | [22 empty] | 2 | 2 | 2 | 2
11 | Warm Up | CB-2 | 2 | 2 | [24 empty] | 2 | 2
12 | Open Cold Box -Remove | CB-2 |  |  | 2 | 2
13 | Move to cryostat-Position | Cryo |  |  |  |  | 4 | 4
14 | Final Cable-Cryostat-in & out | Cryo | [6 empty] | 4 | 4 | 4 | 4
15 | DAQ Test | Cryo | [10 empty] | 4 | 4
16 | Deploy | Cryo | [12 empty] | 4 | 4
17 | Final Test | Cryo | [14 empty] | 4 | 4
18 | Deploy | Cryo | 4 | 4
19 | Final Test | Cryo |  |  | 4 | 4
APA Pair #3
1 | T/B APA into Tower | SAS | [8 empty] | 6 | 6
2 | Test PD, Join APA | SAS | [10 empty] | 6
3 | Move APA to Work Station | SAS | [11 empty] | 6
4 | Cable work/Test | WS-1 | [12 empty] | 4 | 4 | 4 | 4
5 | Cable management/CB Cable | WS-1 | 4
6 | Remove Protective panels | WS-1 |  | 4
7 | Photogrammtry/survey | WS-1 |  |  | 4 | 4
8 | Close up Cold Box/Warm test | CB-3 |  |  |  |  | 2 | 2
9 | Cool Down | CB-3 | [6 empty] | 2 | 2 | 2 | 2
10 | Cold Tests | CB-3 | [10 empty] | 2 | 2 | 0 | 0
11 | Warm Up | CB-3 | [14 empty] | 0 | 0 | 2 | 2
12 | Open Cold Box -Remove | CB-3 | [18 empty] | 0 | 0
13 | Move to cryostat-Position | Cryo | 4 | 4
14 | Final Cable-Cryostat-in & out | Cryo |  |  | 4 | 4 | 4 | 4
15 | DAQ Test | Cryo | [6 empty] | 4 | 4
16 | Deploy | Cryo | [12 empty] | 4 | 4
17 | Final Test | Cryo | [14 empty] | 4 | 4
CPA Pair #1
1 | Bring CPA & FC boxes in | Mat Han | 2
2 | Lift CPA1A and bolt to frame | CPA A | 4 | 4
3 | Lift CPA1b and bolt to frame | CPA A |  |  | 4 | 4
4 | Add Field Shaping at profiles | CPA A |  |  |  |  | 4
5 | Add disfuser and Top FC | CPA A | [5 empty] | 4
6 | Move completed CPA to Cryo | Cryo | [6 empty] | 0 | 0
CPA Pair #2
1 | Bring CPA & FC boxes in | Mat Han | [8 empty] | 2
2 | Lift CPA2A and bolt to frame | CPA A | [6 empty] | 4 | 4
3 | Lift CPA2b and bolt to frame | CPA A | [8 empty] | 4 | 4 | 4 | 4
4 | Add Field Shaping at profiles | CPA A | [12 empty] | 4 | 4
5 | Add disfuser and Top FC | [15 empty] | 4 | 4
6 | Move completed CPA to Cryo | Cryo | [14 empty] | 0 | 0
| Material Handling | Cavern |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 |  | 2 | 2 | 2 | 2 | 2 | 2 | 2
| SAS-Extra Manpower is needed | [13 empty] | 6 | 6 | 6 | 6
|  |  | Day |  | Night |  | Day |  | Night |  | Day |  | Night |  | Day |  | Night |  | Day |  | Night |  | Day |  | Night |  | Day |  | Night
| FTE Cryo 8 inside-4 top |  | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8
| FTE 4910-Cleanroom |  | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 8 | 12 | 12 | 12 | 12 | 12 | 12 | 12 | 12
| FTE 4910 -SAS |  | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6 | 6
| FTE-Cold Box |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| FTE Materials Handling |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| Total FTE Day-Manage-2.5 FTE |  | 32.5 | 32.5 |  |  | 32.5 | 32.5 |  |  | 32.5 | 32.5 |  |  | 32.5 | 32.5 |  |  | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4 | 4
| Total FTE Night-Manage-2.0 FTE |  |  |  | 32 | 32 |  |  | 32 | 32 |  |  | 32 | 32 |  |  | 32 | 32

## TPC Schedule-Cold Test
Week 10
TPC | Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5 |  | Day 6 |  | Day 7
Component | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2
APA#1 | SAS |  | APA Work Station-1 Cables/Test |  |  |  | CB-Close | CB1-Cooldown |  | CB1-Test |  | CB1-Warmup |  | CB-Open | Completed End of Week 10
CPA#1 | CPA#1 In Cleanroom |  |  | Cryostat | [11 empty] | CPA#1 |  |  |  | CPA#2
Deploy
APA#2 |  |  | SAS |  | APA Work Station-2 Cables/Test |  |  |  | CB-Close | CB2-Cooldown |  | CB2-Test |  | CB-War
CPA#2 |  |  |  |  | CPA#2 In Cleanroom |  |  | Cryostat
APA#3 |  |  |  |  | SAS |  | APA WS-1
Extra Day-SAS | [6 empty] | SAS
Week 11
| Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5 |  | Day 6 |  | Day 7
| Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2
APA#1 | Move | Cryo-Cable |  | DAQ
APA#2 | CB-War | CB-Open | Move | Cryo-Cable |  | DAQ | [8 empty] | Completed End of Week 11
APA#3 | APA WS-1 |  | CB-Close | CB3-Cooldown |  | CB3-Test |  | CB3-Warmup |  | CB-Open |  |  |  |  | APA#1 | CPA#1 |  | APA#2 |  | CPA#2
Deploy |  |  |  |  | Drift #1 |  | Drift #2 | Drift #3 | [6 empty] | Deployed #1 |  | Deployed #2 |  | Deployed #3
APA#4 | SAS |  | APA Work Station-2 Cables/Test |  |  |  | CB-Close | CB1-Cooldown |  | CB1-Test |  | CB1-Warmup |  | CB-Open |  | CPA#3
APA#5 |  |  | SAS |  | APA Work Station-1 Cables/Test |  |  |  | CB-Close | CB2-Cooldown |  | CB2-Test |  | CB-War
CPA#3 | CPA#3 In Cleanroom |  |  | Cryostat
CPA#4 |  |  |  |  | CPA#4 In Cleanroom
APA#6 |  |  |  |  | SAS |  | APA WS-2
Extra Day-SAS | [6 empty] | SAS
Week 12
| Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5 |  | Day 6 |  | Day 7
| Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2
APA#3 | Move | Cryo-Cable |  | DAQ | [10 empty] | Completed End of Week 12
APA#4 |  | Move | Cryo-Cable |  | DAQ | [9 empty] | APA#1 | CPA#1 |  | APA#2 |  | CPA#2 |  | APA#3
APA#5 | CB-War | CB-Open | Move | Cryo-Cable |  | DAQ | [8 empty] | Deployed #1 |  | Deployed #2 |  | Deployed #3 |  | Deployed #4
APA#6 | APA WS-2 |  | CB-Close | CB3-Cooldown |  | CB3-Test |  | CB3-Warmup |  | CB-Open |  |  |  |  | APA#4 | CPA#3 |  | APA#5 |  | CPA#4
CPA#4 | [5 empty] | Cryostat | [8 empty] | Deployed #5 |  | Deployed #6 |  | Deployed #7
Deploy |  |  |  |  | Drift #4 | Drift #5 | Drift #6 | Drift #7 | [7 empty] | CPA#5
CPA#5 |  |  |  |  | CPA#5 In Cleanroom |  |  | Cryostat
APA#7 | SAS |  | APA Work Station-1 Cables/Test |  |  |  | CB-Close | CB1-Cooldown |  | CB1-Test |  | CB1-Warmup |  | CB-Open
APA#8 |  |  | SAS |  | APA Work Station-2 Cables/Test |  |  |  | CB-Close | CB2-Cooldown |  | CB2-Test |  | CB-War
APA#9 |  |  |  |  | SAS |  | APA WS-1
Extra Day-SAS | [6 empty] | SAS
Week 13
| Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5 |  | Day 6 |  | Day 7
| Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2
APA#6 | Move | Cryo-Cable |  | DAQ | [10 empty] | Completed End of Week 13
APA#7 |  | Move | Cryo-Cable |  | DAQ | [9 empty] | APA#1 | CPA#1 |  | APA#2 |  | CPA#2 |  | APA#3
APA#8 | CB-War | CB-Open | Move | Cryo-Cable |  | DAQ | [8 empty] | Deployed #1 |  | Deployed #2 |  | Deployed #3 |  | Deployed #4
APA#9 | APA WS-1 |  | CB-Close | CB3-Cooldown |  | CB3-Test |  | CB3-Warmup |  | CB-Open |  |  |  |  | APA#4 | CPA#3 |  | APA#5 |  | CPA#4 |  | APA#6
CPA#6 | CPA#6 In Cleanroom |  |  | Cryostat | [10 empty] | Deployed #5 |  | Deployed #6 |  | Deployed #7 |  | Deployed #8
Deploy |  |  |  |  | Drift #8 | Drift #9 | Drift #10 | Drift #11 | [6 empty] | APA#7 | CPA#5 |  | APA#8 |  | CPA#6
CPA#7 |  |  |  |  | CPA#7 In Cleanroom |  |  | Cryostat | [6 empty] | Deployed #9 |  | Deployed #10 |  | Deployed #11
APA#10 | SAS |  | APA Work Station-2 Cables/Test |  |  |  | CB-Close | CB1-Cooldown |  | CB1-Test |  | CB1-Warmup |  | CB-Open |  | CPA#7
APA#11 |  |  | SAS |  | APA Work Station-1 Cables/Test |  |  |  | CB-Close | CB-Cooldown |  | CB-Test |  | CB-War
APA#12 |  |  |  |  | SAS |  | APA WS-2
Extra Day-SAS | [6 empty] | SAS
Week 14
| Day 1 |  | Day 2 |  | Day 3 |  | Day 4 |  | Day 5 |  | Day 6 |  | Day 7
| Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2 | Shift 1 | Shift 2
APA#9 | Move | Cryo-Cable |  | DAQ | [10 empty] | Completed End of Week 14
APA#10 |  | Move | Cryo-Cable |  | DAQ | [9 empty] | APA#1 | CPA#1 |  | APA#2 |  | CPA#2 |  | APA#3
APA#11 | CB-War | CB-Open | Move | Cryo-Cable |  | DAQ | [8 empty] | Deployed #1 |  | Deployed #2 |  | Deployed #3 |  | Deployed #4
APA#12 | APA WS-2 |  | CB-Close | CB3-Cooldown |  | CB3-Test |  | CB3-Warmup |  | CB-Open |  |  |  |  | APA#4 | CPA#3 |  | APA#5 |  | CPA#4 |  | APA#6
CPA#6 | CPA#8 In Cleanroom |  |  | Cryostat | [10 empty] | Deployed #5 |  | Deployed #6 |  | Deployed #7 |  | Deployed #8
Deploy |  |  |  |  | Drift #12 | Drift #13 | Drift #14 | Drift #15 | [6 empty] | APA#7 | CPA#5 |  | APA#8 |  | CPA#6 |  | APA#9
CPA#7 |  |  |  |  | CPA#9 In Cleanroom |  |  | Cryostat | [6 empty] | Deployed #9 |  | Deployed #10 |  | Deployed #11 |  | Deployed #12
APA#10 | SAS |  | APA Work Station-1 Cables/Test |  |  |  | CB-Close | CB1-Cooldown |  | CB1-Test |  | CB1-Warmup |  | CB-Open | APA#10 | CPA#7 |  | APA#11 |  | CPA#8
APA#11 |  |  | SAS |  | APA Work Station-2 Cables/Test |  |  |  | CB-Close | CB-Cooldown |  | CB-Test |  | CB-War | Deployed #13 |  | Deployed #14 |  | Deployed #15
APA#12 |  |  |  |  | SAS |  | APA WS-1 | [8 empty] | CPA#9
Extra Day-SAS | [6 empty] | SAS

## ITF-APA
| Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun | Mon | Tue | Wed | Thu | Fri | Sat | Sun
| Week 1 | [6 empty] | Week 2 | [6 empty] | Week 3 | [6 empty] | Week 4
Work Area 2 - APA pair N-1 | Mon: APA Cons; Tue: PD Cons.; Thu: Pack
Work Area 1 - APA s pair N | Mon: Arrive; Tue: APA Cons.; Thu: CE Cons.; Mon: PD Cons.; Wed: Pack
Work Area 2 - APA pair N+1 | Fri: Arrive; Mon: APA Cons.; Wed: CE Cons.; Fri: PD Cons.; Mon: PD Cons.; Tue: Pack
Work Area 1 - APA pair N+2 | Thu: Arrive; Fri: APA Cons; Mon: APA Cons; Tue: CE Cons.; Thu: PD Cons.
Work Area 2 - APA pair N+3 | Wed: Arrive; Thu: APA Cons.; Mon: CE Cons.; Wed: Pack
[25 empty] | Arrive | APA Cons
APA personnel | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 3 |  |  | 3 | 3 | 3 | 3 | 0 |  |  | 3 | 3 | 3 | 3 | 3
PD personnel | 0 | 2 | 2 | 0 | 0 |  |  | 3 | 2 | 0 | 0 | 0 |  |  | 3 | 2 | 0 | 0 | 0 |  |  | 3 | 2 | 0 | 0 | 0
CE personnel | 5 | 0 | 2 | 4 | 4 |  |  | 5 | 0 | 2 | 4 | 4 |  |  | 5 | 0 | 2 | 4 | 4 |  |  | 5 | 0 | 2 | 4 | 4
Personnel required at ITF
| WorkArea | Description of activities | [10 empty] | APA | PD | CE
Arrive | Mon: 1 day; Tue: Unpack the 2 APAs with their support frame from the shipping crate and put them in the working area; Sat: 3; Sun: 0; Mon: 0
APA Cons. | Mon: 2 days; Tue: APA consortium performs wire inspection and wire tension measurements, then mounts the CR boards; Sat: 3; Sun: 0; Mon: 0
PD Cons. | Mon: 2 days; Tue: PD consortium installs the photon detectors on the two APAs; Sat: 0; Sun: 2; Mon: 0
CE Cons. | Mon: 2 days; Tue: CE consortium installs the FEMBs on the two APAs and performs a local test; Sat: 0; Sun: 0; Mon: 2
Pack | Mon: 1 day; Tue: Move the APA pair and its frame back to the work area and prepare them for storage / shipment to SURF; Sat: 3; Sun: 0; Mon: 0