## Slide 1: PD Integration/Installation
Dave Warner
Colorado State University
10/30/18

## Slide 2: Outline
Pre-ITF integration and testing
ITF Requirements
Installation Requirements
Summary

## Slide 3: PD cabling pre-positioned inside APA frames
PD cables inside the APA frame will be pre-installed prior to wrapping the APA frames.
Cable installation will occur at APA construction sites
Cables will arrive at APA fabrication sites pre-tested.
Any post-APA installation testing (pre wire-wrapping) must use robust testing equipment, and plans for testing result data migration must be carefully thought out.
Costing for cable installation needs to be coordinated with APA group

## Slide 4: PD Module Cryogenic Testing
Cold box testing of integrated APA/CE/PD units has now been moved underground immediately prior to installation into the cryostat.
  CE cables and conduit will have been installed prior to this testing
  This will occlude removal of PD modules found to fail testing
To mitigate the implied risk, PD modules will be cryogenically tested (in LN2, in a large test dewar such as the one in the CDDF at CSU) prior to shipping to the ITF
This will constitute the final checkout of the PD modules following assembly.

## Slide 5: PD Integration at Integration Site
Following assembly and QC testing, PD modules will be shipped to the Integration/Test Facility (ITF) site in South Dakota for insertion into the APA frames.
Photon detectors will be integrated into APA frames and initial testing (warm) will occur at ITF
Following integration, modules will be stored at ITF until ready for installation into the cryostat (Up to two years storage possible)

## Slide 6: PD pre-installation testing at integration site
PD modules will arrive at integration site in shipping crates (sub-crates of 10 modules each, sub-crates gathered into larger storage crates of 5-10 sub-crates for shipping efficiency)
Immediately prior to installation into APA frames, the modules will be scanned to ensure satisfactory operation
  Two modules at a time will be scanned
  Approximately two hour per scan. Scanning is a two-person operation (two technicians)
  ½ Grad student/Postdoc level person required for data evaluation
  One scanner + one backup (two total scanners, backup scanner in storage against need)
  Approximately 1.5 days will be required to scan modules for one APA

## Slide 7: Module installation
APAs will be oriented horizontally for PD module integration
  Cable connection will occur automatically with module integration (no cable running during integration)
2 persons will be required for installation (perhaps occasional need for a third person for assistance with handling
  Approximately 45 minutes per module, 1 day per APA including testing and alignment tool handling
Immediately upon module integration, a continuity/diode check will be performed to ensure satisfactory connection
Supervision provided by grad student/postdoc?
PD installation and handling equipment required to minimize handling difficulty (single person module moving desirable!)

## Slide 8: Environmental requirements at ITF
PD modules will be shipped to ITF in light-tight sealed plastic bags to facilitate storage prior to integration
Whenever PD modules are exposed (during integration and handling) the lights must be UV-filtered and the humidity minimized
Dust contamination of PD modules is a significant concern. PD integration and storage should occur in a class 100,000 cleanroom or better. Modules should be covered in light-tight static-resistant materials whenever possible.

## Slide 9: Integration Summary
Integration will occur at a minimum rate of ~ 20 PD modules per week
  Could be accelerated significantly by parallelizing incoming scanning and module integration into APAs
Integration testing will consist of
  Pre-installation scan
  Continuity check during integration
1 “Supervisor” (Postdoc or Grad student) plus 2 techs will be needed continuously
Additional labor will be needed occasionally for special handling, incoming material receipt, etc.
Operations need to be carefully coordinated with integration site coordinators

## Slide 10: PD Installation at Sanford Lab
Sanford Lab operations are split into two classes: cabling and testing.
It is expected that approximately 6 APAs will be installed per week.
It is a general philosophy that minimal personnel should go underground.
  All testing should be automated to the extent possible to minimize PD-specific people
  Some PD experts may be required for specialized testing
In general, PD cabling operations are tied closely with CE cabling, and we should attempt to schedule operations so that the same trained technicians can do both at the same time.

## Slide 11: PD Cabling
PD cabling operation at Sanford Lab will consist of making the following connections:
  Connecting the upper to lower APA in a stack
  Cabling from the APA top to the cryostat flange
  Cabling from the flange to the FE electronics
  Cabling from the FE electronics to the DAQ
Minimal PD-specific personnel will be needed for these operations
  PD cables from the cryostat flange to the final APA position may be pre-installed, greatly facilitating PD connecting. Needs to be determined if this will interfere with CE cabling…
  Cabling outside the cryostat should probably occur on an ASAP basis, to minimize installation delays/interferences.

## Slide 12: Testing upon Unpacking
Ideally the APAs would be packaged in nearly-light-tight plastic wrapping following integration, which would allow us to do a final checkout prior to unpacking from the crate
Perhaps with an LED in the package?
All APAs would have an operational test prior to unpackaging.
  Estimated time: 15 to 30 minutes per APA pair
Remediation: TBD. Cable checks? Possible replacement of damaged PD (depends on available space, and conduit installation)

## Slide 13: Tests upon Hanging Outside Cryostat
Immediately following assembly of upper APA to lower APA, a continuity check will be performed for all 20 cables at the top of the APA stack
All assembled APA stacks would have a continuity check throughout installation
Estimated time: 10 to 15 minutes?
Remediation: Re-check cable connections. Possibly separate APA stack to access middle connectors if necessary?

## Slide 14: Cold Box Testing
Following assembly of APA stack assembly and CE cable installation, the complete APA stack will be tested in a cold box.
During the cold test, PD modules will be operated
  Dark count measurement
  LED illumination
Mitigation: As noted previously, the presence of the CE cables and conduit in the APA side tubes makes access to and replacement of defective modules difficult.
  Access to PD connectors at the head of the APA should be easy.
  Need to understand if we could reach the connectors between upper and lower APAs (If TDR measurements suggested it might be useful?)

## Slide 15: Initial Testing upon Positioning Inside Cryostat
Immediately following the APA arriving in position inside the cryostat, but prior to connecting the APA-Flange feedthrough cable, a continuity check will be performed
This checkout is envisioned early in the installation process, and may be eliminated later.
The goal of this checkout is to catch cabling issues caused by the rail installation system early enough to allow us to gain access for remediation
Estimated time: 20 minutes (?) depending on ease of access
Remediation: Move APA stack enough to allow access to cables for repair. Possible other remediation as agreed to.

## Slide 16: Full Cable Run Checkout
Following installation of APA-Flange feedthrough cable, a continuity check will be performed
This check will occur for all PDs as early as possible after installation.
Estimated time: 15 minutes
Remediation: Check cable connections. Note issues in database.

## Slide 17: Post-installation Operational Test
As soon as possible following installation and cable checkout, it would be ideal if the cryostat lights could be turned off and an operational (dark) check performed.
Ideally, this would happen on an stack-by-stack basis in the initial installation phase, then perhaps on a weekly basis as our understanding evolves?
Estimated time: 1 hour per stack (during off-installation-shift time)
Test possible involves LED illumination?
Remediation: Note module status in logbook, try to improve handling procedures to eliminate sources of failures.

## Slide 18: Tooling
A continuity check tool will need to be developed to allow for rapid testing.
  Multi-cable simultaneous connection?
  No twist lock operation?
  Automatic test result evaluation?
  Automatic data storage?
A portable operational testing station should be developed
  4 channel readout?
  Automatic test result evaluation?
  Automatic data storage?
Aim for operation by technicians, not scientists.

## Slide 19: Data Storage/Evaluation
Ideally, the data from all installation QC checks would be downloaded to the database automatically, no later than at the end of the shift where they were taken.
Data flagged as outside operational norms (TBD) would be automatically flagged for expert intervention
Weekly (?) expert examination of QC data from recently installed modules
Performance trend lines maintained (automatically?) to look for long-term changes to the system.

## Slide 20: Installation Summary:
While underground remediation is difficult, QC testing during installation is important to improve procedures and make possible repairs.
PD QC must be planned with the understanding that no module repair will be possible following the integrated cold box test.
Tooling must be developed to allow testing to de made by non-PD experts
Data must be automatically stored, and easily retrievable, to be most useful.