## Slide 1: A new layout (proposal) MNe, JF, JS, BM, DM, DMo

## Slide 2: Some new requirements have been discussed
Avoid any dependence on filling and cooling between det#1 and det#2 (accepted in the last EFIG meeting)
Test complete double APA (+electronics and PD) or CRP just before inserting it into the cryostat (still to be optimized)
Det #1 in cavern 1
Det #2 in cavern 3
Cold tests in dedicated cold boxes in the cavern clean room
Cold boxes for double APA
or
Cold boxes for individual CRPs

## Slide 3
Det#3
Det#4
Det#1
Det#2

## Slide 4: Material income (for cryostats and detector 1 and 2)

## Slide 5: Strategy
Assemble detector#1 in Cavern 1, chamber 2
Assemble detector#2 in Cavern 3, chamber 2
Chambers 1 available for material storage with direct delivery from the left drifts
During assembly of det 1 and 2, more freedom to organize space and learn from the difficulties
Large cold boxes in place in front of the TCOs (double APAs test boxes). Part of the N2 plan must be available at this moment
Keep the same level of difficulties as today for detector#3 and #4

## Slide 6: Detector TCO view
to CUC

## Slide 7: Detector roof front view
bridge crane ~12T
monorails ~20T
cable trays
to CUC
detector mezzanine

## Slide 8: New detector mezzanine
Each rack 2400-3400 Watts
(see T.Shaw presentation)

## Slide 9: Detector roof
Cable trays

## Slide 10: Detector roof

## Slide 11: Revisited cryogenics mezzanine covering the entire length of the cryostat
removable floor
more space for counting rooms/control rooms
el. isolated stairs
support rods to the cavern roof
piping and services to the CUC

## Slide 12: 3D view

## Slide 13: Cryostats and detector installation
FY28
FY27
FY26
FY25
FY23
FY22
FY21
FY20
FY19
FY18
FY29
FY30
FY24
North Cavern BO
Central Utility
South Cavern
Det1 warm str.
X
South Cavern BO
X
Det1 cold str.
Det1 install
Det1 closing.
Det1 flushing and cooling.
Det1 filling.
Det2 warm str.
Det2 cold str.
Det2 install
Det2 closing.
Det2 flushing and cooling.
Det2 filling.
End July 2027
End August 2028
Nord Cavern
9
12
12
3
4
12
9
12
12
3
4
13
52 months