## Slide 1: Thoughts on Storing Material for the SP Detector
October 29 2018
Stewart - Zhao

## Slide 2
Det#3
Det#4
Det#1
Det#2

## Slide 3: Starting Assumptions
The installation of the Cryostat, Cryogenics, and Detectors will be one coordinated effort.
Both detector caverns will be used. Detector1 East end of excavation#1 and Detector#2 in the East end of excavation#3
All 4,000 crates for the membrane installation will be in SD before starting the insulation installation.
All storage facilities must be within 1-2h drive of SURF.

## Slide 4: Additional Assumptions
Underground machine shop and storage areas will be in excavation#1 for detector 1 installation.
  CUC is not available at the start of Det1 installation
Both measure 8mx10m
Storage

## Slide 5: Installation Schedule v2
Define critical times where the need for storage is maximal. Then evaluate the space needs at that time.
Start of Cryostat#1 cold structure
Start setup of Detector#1 installation
Start Detector#1 Installation
Start cryostat cold#1
Setup detector1 installation
Install detector1

## Slide 6: Start of Cryostat#1 cold structure
Starting conditions
  CUC is available for use.
  Some storage for cryostat crates is available in the excavation outside the cryostat.
  excavation#3 is not available at the start.
Challenges
  Need to store 4,000 1.5m by 3m by 1.5m wood crates with access.
Assumptions
  Assume the machine shop and storage area are in place.

## Slide 7: Configuration
Image of the hall at the start of cryostat installation
Reserved space for cryostat crates
12m
10m
10mx8m
10mx8m
19.8m
35m
56m
8.5m

## Slide 8: Start of Detector1 Installation Setup
Starting conditions
The cold structure for cryostat1 is half complete. Need to store 2,000 1.5x3.0x1.5 crates
Cavern2 CUC is available
½ of Cavern#3 is available for storage while the warm structure is being installed in the other half.
The Detector installation setup phase is 6 months, but may be shifted some not to overlap the cryostat work as much.
  Assume 1/3 of the materials needed for the setup are available on hand at the start of the setup work. This will give a 2 month buffer with some flexibility for shuffling work.

## Slide 9: Configuration
Starting Conditions
Reserved space for cryostat crates
1/3 of parts for setup phase
Some are placed inside the carven
the others to be stored somewhere else
Equipment that needs to be stored on the surface or cavern #3

## Slide 10
20m
50m
8.5m
56m
50m x 20m space for parts that can’t fit in the carven is ample.
A one month buffer would be half this. This will fit in half Cavern#3

## Slide 11: Start Detector 1 installation
Starting conditions
The start of Det#1 corresponds to the start of Cryostat cold #2. 4,000 boxes must be in SD
The cryogenic system for detector 1 is 50% installed.
Assume 1 month buffer of APAs ready to install
Assume 100% of the end wall #1 is in SD
Assume a 1 month buffer (5 weeks) for all other components.
  20 Cathode modules
  40 FC modules

## Slide 12: Configuration
Starting Conditions
One month supplies for SP installation phase fits in the carven.

## Slide 13
One month supplies for SP installation phase fits in the carven.
Logistics center needs the ability to receive and repackage goods. A buffer of 1 week is needed to consolidate shipments and manage days when no deliveries will be possible due to high CF load.

## Slide 14: Logistics Conclusions
The underground space is sufficient for a reasonable materials buffer of 1 month.
  This estimate does not include possible storage on top of the cryostat
The logistics center does not need to serve as a short term material buffer.
The requirements should be driven by the receiving, inventory and shipping needs.
Building a coherent logistics plan needs to now include the cryostat and cryogenics.

## Slide 15: Should DUNE consider temporarily outfitting the mucking drift segment connecting excavation 1 and 3?
Det#3
Det#4
Det#1
Det#2
This would simplify moving material between excavation 1 and 3.
Would require lighting, ventilation and a 100m long concrete pad at a min.

## Slide 16: Backup