## Slide 1
Peter Winter, Jarek Kaspar (Shutdown Coordinators)
Argonne National Laboratory
Muon g-2 Shutdown Overview

## Slide 2: Physic Priorities
Top areas for FY18 shutdown
  Increased reliability / stability of pulsed injection systems
  Improved momentum distribution (needs stronger kick)
  Obtaining higher muon flux
TDR Goal
Achieved 50%

## Slide 3: Muon Flux
Have achieved 50% of design flux
Not any one problem…many compounding factors
TDR Goal
Peak Rate Achieved 50%
Factor | Cause | Fixable
0.90 | Target Yield | Hard
0.90 | Muon transport | Maybe
0.90 | Bunch width | No
0.90 | Kicker amplitude | Yes
0.85 | Kicker shape | Hard
0.90 | Quad voltage | Yes
0.83 | 12 Hz vs 10 Hz | No
Product = 0.42
Known contributing factors

## Slide 4: Path to higher flux
Gain | Upgrade | Shutdown
1.20 | Installation of momentum-collimating wedges in beamline | 2018
1.10 | Higher kicker voltages and more reliability of kicker | 2018
1.10 | More reliable operation of electrostatic quads at higher voltage | 2018
1.05 | Installation of 2 faster-switching PS in upstream beamline | 2018
1.5 | TOTAL Product for Run-2 | 2018
1.40 | Installation of new open-ended inflector | 2019
2.1 | TOTAL Product for Run-3 and beyond | 2019
Focusing on Reliability and Safety for Cryo, Kicker, Quads this year
Summer 2018 upgrades expected to yield 50% more flux
Notes: Add why are we at 50%

## Slide 5: Beamline Wedges
Wedges in region with dispersion to compactify momentum
Simulations indicate gain of ~20%
They are installed and ready for testing with beam

## Slide 6: Cryo main upgrades
Safeguards and reliability:
  Compressor Trip Cryo Response (CTCR) for zero-quench mode*
  Compressor interlock switches for more reliability*
  Redundant PLC at A0 (redundant to MC-1) for compressors*
  Redundant communication between MC-1 and A0*
  Pneumatic actuators replacing old electric ones for more reliable valve operation
  System maintenance (purification, pumps, ...)
Status:
  CTCR installation done, safety review and commissioning ongoing
  Redundant PLC done
  Implementation of new alarms and actuator replacement still ongoing
*recommendation from a former review

## Slide 7: Kicker Upgrades
Reliability
  Redesign Bazookas and vacuum feedthrough for better mechanics and reduce sparking
  Refurbish Blumleins for more reliability
  Rewire thyratron heating circuit for improved reliability
  New electronics for better control
  Improve spare pool (spare, connectorized cable assembly)
Kicker strength
  Replace charging power supplies
  Redesign feedthrough to accommodate higher wattage resistors
Status:
  Refurbished old feedthroughs for beam commissioning Oct/early November
  Fabrication of new Bazookas and feedthroughs is coming along
  Blumleins fully refurbished, currently reinstalling in MC1 hall
  PS racks assembled, need power upgrade in hall to operate all 3 kickers

## Slide 8: Quadrupole Reliability Upgrades
New insulator plate (batman) to stabilize leads
Survey and possibly realign quad plates
New electronics for better operation
Install new RF system to reduce Coherent Betatron Oscillation
Status:
  All new Batman installed and leads realigned
  Preliminary test indicate ability to operate more reliable at higher voltages
  Performing long quad test next week
  New electronics ready for commissioning
  RF system installed, not needed for start of data taking, commission at a later time

## Slide 9: Outlook for next weeks
October 8-15: Quad and kicker testing plus Eddy current measurement
October 15: Ready for first beam commissioning with old kicker
November 8-15: Install new kickers
November 15: Start data taking with new kickers