## Slide 1: Muon Campus Status
Jim Morgan
Shutdown week 13
October 5, 2018

## Slide 2: Week 13 tunnel activities
V003 awaiting reconnection of power cable and LCW hoses
  Vacuum pipe welded in last Friday
M4 (to Mu2e) and M5 vacuum work continued
  M4 Line from V907 to Mu2e Shield Wall under rough vacuum
  M5 Line under vacuum
Ionization Cooling Wedges
  Final wiring terminations underway, motion check-out to follow
V003 back in place

## Slide 3: MDC dipole – Type used at H748
68 turns

## Slide 4: MDC007 coil winding (replacement for H748)

## Slide 5: MDC007 coil winding

## Slide 6: MDC007 coil winding – the first snag
Damaged conductor

## Slide 7: Upcoming
Transition to operation – tentative plan
  Mock secure this weekend
  Change back to safety system keys Tuesday afternoon
  Search and secure Tuesday afternoon
  Perform annual safety system tests early Wednesday
  Ops unlock power supplies and E.E. Support tests D:IB
  General power supply testing Wednesday and Thursday
H748 repair
  Updated schedule has magnet completion on approximately October 29 (was October 24 on first rough estimate)
  Several more days needed for transport and installation
  Will continue to explore “double-swap” with MDC at V907 and spare CDC-103 at low level