## Slide 1: Muon Campus Status
Jim Morgan
Transition from shut-down to operation
October 12, 2018

## Slide 2: Activities last week
Finished remaining shutdown-related tasks
  V003 dipole power cable and LCW hoses reconnected
  Final wiring of ionization cooling wedges
  Larger D:Q012 and D:Q013 power supplies connected to loads
  LCW headers for M4 Line to Mu2e connected into system
Transition to operation
  Mock secure completed Monday evening
  Ring and Extraction enclosures changed back to safety system keys Tuesday afternoon
  Ops followed with search and secure late Tuesday afternoon
  Performed annual safety system tests Wednesday morning
  Ops unlocked power supplies Wednesday
  E.E. Support tested D:IB (new switch gear) Wed/Thu

## Slide 3: H748 MDC dipole repair
MDCC007 repair
  Formerly used at V742 in M3 Line, replacement for leaking coil used to repair V003
  Considered best option for H748 due to lower risk of schedule slip
  Only enough annealed conductor available to make one coil set
  Estimate for completion of magnet repair was 10/29
  Several more days needed for transport and installation
MDCE001 repair
  Dipole that came from H748 and was received at T.D. 9/25
  Dismantled as time allowed, insulation was damaged during coil separation as expected
  Was not expected internal coil leak, tube from manifold was cracked
  Technical experts were able to drill out the old tube and install a new one, priority shifted to finishing repair of this dipole after hydro test
  Estimated completion date of 10/19

## Slide 4: MDC dipole – MDCC007 internal coil leak
Water bubbling up out of coil

## Slide 5: MDCE001 – on arrival at T.D.

## Slide 6: MDCE001 – opened up
Damaged conductor insulation

## Slide 7: MDCE001 – failed tube and repaired coil ready for insulation

## Slide 8: MDCE001 – insulation repair and core prep

## Slide 9: MDCE001 – Applying epoxy and clamping in mold

## Slide 10: Upcoming
Transition to operation – tentative plan
  Continue power supply testing today
  Thermal scans of magnets after more general power supply testing early next week
  Access opportunities next week, hope to receive MDCE001
  Prepare for resuming beam operation
H748 repair
  Magnet completion (MDCE001) now estimated for 10/19, then several more days for transport and installation
  MDCC007 repairs (will be spare) completed in November