## Slide 1: Cryo-assembly and Testing L2 Meeting
S. Feher
October 22nd , 2018

## Slide 2: Preparation for the DOE Review
Timeline:
Documentation to be ready by November 26th, 2018
L2 DOE Presentation rehearsals on the week of October 29th, 2018
L3 DOE Presentation rehearsals on the week of November 5th, 2018
MQXFAP2 Test Review on November 5th, 2018

## Slide 3: Q1/Q3 Cryo-assembly Fabrication – documentation
Cryostat assembly LQXFA/B FRS - Sandor
Acceptance plan - LQXFA/B Acceptance Plan - Sandor
FDR - Vertical Test Stand FDR – Joe (Gianluca editor)
PDR – editing Sandor
  LMQXFA – Tony/Rodger and LQXFA/B - Roger
  Horizontal Test Stand - Guram
Interfaces: ICD re-vised (still in preliminary phase but VMTF) – Tom editing for consistency
  VMTF – Structure (Joe, Dan); CM – Structure (Tony, Dan); CM – VMTF (Tony, Joe); Cryo – CM (Roger, Tony); HMTF – Cryo (Guram, Roger); Q1/Q3 – CERN (Sandor, Ezio)
Cost&Schedule
  BoE needs scrubbing – All (special meeting with Sandor)
  Primavera schedule –
    Parallel MS Project schedule for CM&Cryo – Sandor/Tony/Rodger/Roger
    Parallel MS Project for HMTF – Roger/Guram
Risk registry finalized – needs everybody to check it
Safety agreement - Tom

## Slide 4: FRS
LMQXFA FRS
  Updated version exist and being signed off by CERN
LQXFA/LQXFB FRS
  Updated version exist and being reviewed by CERN
Test FRS
  Needs to be reviewed to check whether any modifications needed

## Slide 5: PDR
CM chapter
  Stress analysis to be updated by (Bob Wands).
  Design drawings tree need to be updated – official version should be started
  3D model of the bus and expansion loops need to be developed
  Bas bar soldering fixture drawings to be shown and referenced
  Mock up pictures of the bus bar to be updated with the new one
  Lifting fixture procurement specification to be referenced
  ICB-a floor layout needs to be updated
  Assembly procedures needs to be updated – or rough traveler for the assembly procedure needs to be referenced
  Alignment section needs more detail based on CERN new QA steps that include alignment and dimensional measurements.

## Slide 6: PDR
Cry-assembly chapter
  Needs an update using latest Delio’s and Loyd’s drawings and calculations.
  Fabrication needs more detail:
    Assembly procedures a lot more steps – preliminary traveler steps (we so far envision) to be included
    Tests should refer to CM tests
    Alignment section need a lot more work and steps – based on CERN alignment group talks
  Shipping needs to be updated.
LQXFA Horizontal Test – needs update with the latest development

## Slide 7: ICDs
Interface Control Documents