## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly Reports
Guram Chlachidze
Oct. 22nd, 2018

## Slide 2: Cryo-mechanical upgrades
Adapter box & Interconnect design work in progress
  Operation at higher pressure
  Adapter box design review planned for beginning of October
External piping design work in progress
  LHe line from distribution box to Feed box
  LN2 supply to Feed box
  Stand 4 bayonets to be surveyed
The End box modifications in progress
  The End box disassembly is on hold, technicians expecting the final design
  Parts procurement was planned in October
Requisition for the lambda plug parts waiting procurement award
Cry-assembly adjustable supports design is complete
  Need the lead engineer approval to proceed with the drawings

## Slide 3: Instr. & mechanical upgrades
25 T crane upgrade
Delivery schedule was discussed with the vendor (Superior Crane Corp.)
  Revised crane delivery date is Feb. 25, 2019.
  Assembled and tested by March 4, 2019
  Old crane upgraded by March 11, 2019
  PO will be modified accordingly
  Another 16 k$ (direct) charged in September (?)
The same vendor will fabricate the overhead crane in ICBA
Magnetic measurement systems
All components arrived for the rotating coil system
RC measurement system will be assembled and tested with MQXFS1e
Most of the SSW components arrived
Work on the probe motion system is in progress (off-project)

## Slide 4: Other Off Project upgrades
QPM (Off-project)
AQD PC boards design is complete.
Power supplies will be procured for AQD chasses this week
DQD backplane PCB layout is complete, DQD controller design is 75% complete
AQD and DQD integration test (mu2e) is expected in Dec. 2018.
Procurement of CLIQ units: waiting for quotes from the vendor
Need interface document for the cryo-assembly instrumentation ports (CERN)