## Slide 1: LBNF/DUNE QA Plan
Kevin Fahey
5 June 2018

## Slide 2: PURPOSE
to implement quality in the construction of an operational LBNF facility and DUNE experiment while providing protection of LBNF/DUNE personnel, the public, and the environment

## Slide 3
Features :
Personnel training and qualification
Quality improvement programs
Document, records and configuration management
Work process control
Engineering design quality standards
Procurement quality processes
Inspection and acceptance testing
Management assessments
Independent assessments
Suspect/Counterfeit items prevention
Quality in scientific research

## Slide 4
QA Plan outlines the QA requirements for all LBNF/DUNE collaborators and subcontractors, henceforth referred to as Project Partners, and describes how the requirements shall be met
Plan is implemented by the development of quality plans, procedures and guides to accommodate those specific quality requirements

## Slide 5: SCOPE
QA Plan provides Quality Assurance requirements applicable to all Project Partners, encompassing all activities performed by or for the LBNF/DUNE Projects, from research and development (R&D) through facility acceptance and component commissioning
Subcontractors and Project Partners will be responsible for providing their deliverables, whether subsystems, components or services in accordance with applicable contracts and agreements.

## Slide 6
All parties will be responsible for implementing a quality plan that meet the requirements of this quality plan.
Oversight of the work of these parties will be the responsibility of the LBNF Project Manager, DUNE Technical Coordinator and LBNF/DUNE QA Manager.
Additional quality requirements for construction activities will be invoked through the application of the Construction Quality Management Program which is an addendum to this quality plan.

## Slide 7: Graded Approach
A key element of this QA Plan: applying a level of analysis, controls, and documentation commensurate with the potential for an environmental, safety, health or quality impact
Fermilab Quality Assurance Manual Chapter 12070: Graded Approach Procedure

## Slide 8
The Graded Approach seeks to tailor the kinds and extent of quality controls applied in the process of fulfilling requirements. Application of the graded approach entails:
Identify activities which present significant operational risks
Determine the risk levels
Determine the necessary controls and requirements to be applied
Determine the depth, extent, and degree of rigor in the application of requirements
Document and approve the determination

## Slide 9: QUALITY ASSURANCE PROGRAM
The LBNF and DUNE Projects are managed by Project teams as described in:
LBNF/DUNE Project Management Plan
DUNE Management Plan.
Specific QA plans shall be developed by Project Partners with the assistance of the LBNF/DUNE Quality Assurance Manager (QAM) for particular component or system quality assurance
Due to the limited scope of work of some of the Partners on the projects, they may elect to work under the LBNF/DUNE QA Plan for their scope of work.

## Slide 10
For contracted activities, such as that for conventional facilities and cryogenic infrastructures, additional QA plans developed by Architect/Engineer (A/E) firms, Construction Managers (CM), and other contractors will govern work in their areas of responsibility.
For both Near Site and Far Site Conventional Facilities (CF) and well as contractors for other subprojects, each construction contractor will work within its own QA plan and procedure system, which must comply with the requirements in this Plan and with its own QA program.
In case of conflict between sets of QA requirements, LBNF/DUNE Project Management will provide resolution.
Overall QA supervision, including all activities described above, is the responsibility of the LBNF Project Manager and DUNE Technical Coordinator.

## Slide 11: Responsibility for Project Management
The LBNF Sub-Project Managers and DUNE Consortia Leaders manage their Projects and are responsible for achieving performance goals.
The LBNF/DUNE QAM is responsible for ensuring that a quality system is established, implemented, and maintained in accordance with requirements.
The LBNF/DUNE QAM reports to the LBNF Project Manager and DUNE Technical Coordinator and provides oversight and support to the Project Partners to ensure a consistent quality program.

## Slide 12
The LBNF Sub-Project Managers and DUNE Consortia Leaders are responsible for quality within their Project and report their Quality Assurance issues to the LBNF Project Manager and DUNE Technical Coordinator and LBNF/DUNE QAM.
LBNF Sub-Project Managers and DUNE Consortia Leaders may designate Quality Assurance Representatives (QAR) within their organization to perform some of their work defined in this Quality Plan.
The LBNF Sub-Project Manager or DUNE Consortia Leader shall retain overall responsibility for these activities even though they have designated a QAR.

## Slide 13: Levels of Authority and Interface
The DUNE Management Plan, the LBNF/DUNE PMP, and this LBNF/DUNE Quality Assurance Plan (QAP) define the responsibility, authority, and interrelation of personnel who manage, perform, and verify work that affects quality.
The QAP defines the QA roles and responsibilities of these management and working levels of the LBNF and DUNE Projects.
All LBNF Team Members, collaborators, contractors, and subcontractors are responsible for the quality of the work that they do and for using guidance and assistance that is available.

## Slide 14
Each has the authority to stop work and report adverse conditions that affect quality of LBNF/DUNE products to their respective LBNF Sub-Project Manager or DUNE Consortia Leader and the LBNF/DUNE QAM.
The Sub-Project Manager or Consortia Leader responsible for LBNF/DUNE components or systems is required to determine and document their acceptance criteria.
The LBNF Project Manager, DUNE Technical Coordinator, Consortia Leaders, LBNF/DUNE QAM and Sub- Project Managers are all responsible for providing the resources needed to conduct the Project successfully, including those required to manage, perform and verify work that affects quality.
The LBNF/DUNE QAM may request personnel from across the LBNF and DUNE Project Teams to act on behalf of the LBNF/DUNE QAM to perform quality assurance functions, based on need. The requested personnel shall possess qualifications or receive the appropriate training required to perform these functions.

## Slide 15: PERSONNEL TRAINING AND QUALIFICATION
The LBNF Sub-Project Managers and DUNE Consortia Leaders are responsible for identifying the resources to ensure that their team members are adequately trained and qualified to perform their assigned work.
Before allowing personnel to work independently, they are responsible to ensure that their team members have the necessary experience, knowledge, skills, and abilities.

## Slide 16
Personnel qualifications are based on the following factors:
previous experience, education, and training
performance demonstrations or tests to verify previously acquired skills
completion of training or qualification programs
on-the-job training
Qualification and training requirements are provided in LBNF/DUNE Integrated ESH Plan.
All LBNF/DUNE Project Partners are responsible for ensuring that their training and qualification requirements are fulfilled, including periodic re-training to maintain proficiency and qualifications.

## Slide 17: QUALITY IMPROVEMENT
All LBNF and DUNE Project Partners participate in quality improvement activities that identify opportunities for improvement.
This quality-improvement process requires that any failures and non-conformances be identified and reported to the appropriate Sub-Project Manager or Consortia Leader; and, that root causes be identified and corrected.
Items, services, and processes that do not conform to specified requirements shall be identified and controlled to prevent their unintended use.

## Slide 18
Each Sub-Project Manager or Consortia Leader is responsible for reporting non-conformances to the LBNF/DUNE QAM and the LBNF/DUNE QAM will periodically report these non-conformances to LBNF/DUNE Project Management.
LBNF incorporates Root Cause Analysis and Corrective and Preventative Actions elements of the Fermilab Quality Assurance Manual Chapters 12050 and 12040, respectively.
Consortia Leaders may perform Root Cause analysis and Corrective and Preventive Actions under their own procedures.

## Slide 19
This problem identification, analysis and resolution process for quality consists of the following steps:
1) Identify problem
2) Understand the process
3) Grade the process and identify Root Cause Analysis (RCA) method
4) Identify possible causes
5) Collect and analyze data
6) Communicate Lessons Learned and document RCA
7) Implement Corrective and Preventative Action procedure

## Slide 20: Lessons Learned
To promote continuous improvement, the LBNF and DUNE Projects will develop a lesson learned program based on the Fermilab Office of Project Support Services’ Lessons Learned Program.
Where appropriate, improvement actions are taken to either promote the repeated application of a positive lesson learned, or prevent recurrence of a negative lesson learned.
Lessons learned shall be gathered throughout the Project life cycle.
As part of the transition to operations a lessons learned report will be submitted.

## Slide 21
The LBNF/DUNE QAM will periodically publish a best practices and lessons learned report.
Lessons learned from the LBNF and DUNE Projects will be screened for applicability to other organizations.
The LBNF/DUNE will periodically check external lessons learned sources for applicability to the LBNF and DUNE Projects.

## Slide 22: DOCUMENTS AND RECORDS
Engineering and scientific documents (including drawings) are prepared by LBNF/DUNE personnel to define the design, manufacture and construction.
Before these documents are put into effect they are reviewed and signed by the LBNF Sub-Project Manager, DUNE Consortia Leader or designee.
The LBNF and DUNE Project Offices manage all documents under a document control system as identified in the LBNF/DUNE Configuration Management Plan (CMP).
The system to control document preparation, approval, issuance to users, and revision is described in the CMP.

## Slide 23
Sub-Project Managers and Consortia Leaders will use the graded approach described in this plan to determine work in their scope that requires the LBNF/DUNE QAM review and signature.
Project documents that contain quality requirements shall be reviewed and approved by the LBNF/DUNE QAM.

## Slide 24: WORK PROCESSES
LBNF/DUNE team members are responsible for the quality of their work, and Project Partners are responsible for procuring the resources and support systems to enable their staff to complete their work with high quality.
All LBNF/DUNE work will be performed:
using methods that promote successful completion of tasks,
conformance to LBNF/DUNE requirements, and
compliance with the LBNF/DUNE Integrated ESH Plan.

## Slide 25
Work processes consist of:
a series of actions planned and
carried out by qualified personnel
using approved procedures, instructions and equipment,
under administrative, technical, and environmental controls,
to achieve a high quality result.

## Slide 26: Design Work Processes
The LBNF/DUNE Systems Engineering team will ensure that engineers and designers are knowledgeable about the requirements that control their design work.
Workflow for approval of drawings and specifications assure that pertinent disciplines review the design and include a Sub-Project Manager, Consortia Leader or designee signature.
The DUNE Consortia may document their design work processes in accordance with the LBNF/DUNE Configuration Management Plan in lieu of the following Systems Engineering website.

## Slide 27
LBNF uses a Systems Engineering website to document design work processes at:
https://fermipoint.fnal.gov/Project/LBNF/Project%20Office/Systems%20Engineering/SitePages/Home.aspx

## Slide 28: Fabrication Work Processes
Fabrication work on the LBNF and DUNE Projects shall be performed to established technical standards and administrative controls using approved instructions and procedures.
Fabrication work processes with QA inspections and tests shall be documented on Travelers that are retained with the hardware item.
Items, including consumables, shall be identified and controlled to ensure their proper use and prevent the use of incorrect, unaccepted, or unidentified items.

## Slide 29
The Projects will define a system of controls to ensure that items are:
handled,
stored,
shipped,
cleaned, and
preserved to prevent them from deteriorating, being damaged, or becoming lost.
Equipment used for process monitoring or data collection shall be calibrated and maintained.

## Slide 30
Work shall be performed safely, in a manner that ensures adequate protection for employees, the public, and the environment.
Team members, Project Partners, LBNF Project Management and the DUNE Technical Coordinator shall exercise a degree of care commensurate with the work and the associated hazards.
See the LBNF/DUNE Integrated ES&H Plan, [4] for more details on LBNF/DUNE integrated safety management systems.

## Slide 31: Change-Controlled Work Processes
Change-controlled work processes are those for which the LBNF and DUNE Change Control Boards (CCB) require that work, both design and fabrication is tracked.
The CCBs assign a unique tracking number to identify those design and fabrication items for which the associated change is effective.
The LBNF/DUNE Configuration Management Plan [6] defines the change control process in detail.

## Slide 32: DESIGN
The LBNF/DUNE design process provides appropriate control of design inputs and design products.
The primary design inputs are the scientific/engineering requirements (physics requirements, detector requirements, specifications, drawings, engineering reports, etc.).
The basis of the design process requires sound engineering judgment and practices, adherence to scientific principles, and use of applicable orders, codes and standards.
This basis of the design process naturally incorporates environment, health and safety concerns.

## Slide 33: Design Process
The LBNF/DUNE Systems Engineering website documentation defines the scope of design work for any given scientific/engineering work group.
Work groups will begin preliminary design of LBNF/DUNE by breaking their work down into sets of engineering drawings, specifications and reports. This is the design output.
Throughout the design process, engineers and designers work with LBNF/DUNE Sub-Project Managers, Consortia Leaders and the LBNF/DUNE QAM to determine QA inspection criteria of fabricated products and installations.

## Slide 34
Close coordination must be made with LBNF/DUNE scientists to assure the engineering satisfies the scientific requirements of the experiment.
Final Design work sets the final Quality Assurance parameters for the parts, assemblies and installations.
Design during Final Design and production is confined to Change-Controlled changes, as above; and, minor changes necessary to facilitate production, drawing error correction, material substitutions and similar functional areas.

## Slide 35: Design Verification and Validation
Design is verified and validated to an extent commensurate with its importance to safety, complexity of design, degree of standardization, state of the art, and similarity to proven design approaches.
Acceptable verification methods include but are not limited to any one or combination of
(1) design reviews,
(2) alternative calculations, and
(3) prototype, qualification testing and/or comparison of the new design with a similar proven design if available.

## Slide 36
Verification of work shall be completed before approval and implementation of the design
Design reviews shall verify and validate that the following criteria are met at the appropriate milestone:
Adherence to requirements
Technical adequacy of the design
Adequacy of work instructions
Thoroughness of specifications
Test results
Adequacy of Technical Reports
Adequacy of design calculations and drawings
Reliability and maintainability
Calibration program for measurement and test equipment

## Slide 37
Wherever the design method involves the use of computer software to make engineering calculations or static dynamic models of the structure, system, or component's functionality, the software must be verified to demonstrate that the software produces valid results.
The verification needs to be documented in a formal Report of Validation that is maintained in records that are accessible for inspection.
Exemptions may be made for commercially available software that is widely used and for codes with an extensive history of refinement and use by multiple institutions.
Exemptions affecting systems or components shall be identified to the LBNF/DUNE Systems Engineering team.

## Slide 38
Critical software and firmware computer codes, especially those codes that are involved in controlling LBNF/DUNE Data acquisitions systems (DAQ), shall also be subjected to reviews for verification and validation.

## Slide 39
Some items to be considered during computer code review are as follows:
Adequacy of code testing scheme
Code release control and configuration management
Output data verification against code configuration
Verification that code meets applicable standards
Verification of code compatibility to other systems that use the data
Verification that code meets applicable hardware requirements
Adequacy of code maintenance plans
Adequacy of code and data backup systems

## Slide 40
Validation ensures that any given design product conforms to LBNF/DUNE Science and Engineering Requirements on the Systems Engineering website.
In any review, validation of conformity to requirements follows verification that the engineering design or computer code meets all criteria.
Engineering designs and computer codes shall be validated, preferably before procurement, manufacture, or construction; but no later than acceptance and use of the item; this is to ensure the design or computer code:
Meets the LBNF/DUNE requirements,
Contains or makes reference to acceptance criteria, and
Identifies all characteristics crucial to the safe and proper use of the equipment or system and its associated interfaces

## Slide 41
Each inspection, test or review will feed the QA evaluation process, which is a comparison of results with acceptance criteria to determine acceptance or rejection.
Rejection identifies the need for Quality Improvement based on Section 4 of this document. In some cases, the outcome of the Quality Improvement process may be to request change(s) to the design requirements.
QA reporting formality escalates as the significance of the inspection, test or review nonconformance increases.
Higher levels of management must be aware of and participate in the correction of the most significant nonconformance. Section 4, Quality Improvement, identifies the required course of action when nonconformance is encountered.

## Slide 42: Procurement
Procurement controls will be implemented to ensure that purchased (Supplier) items and services meet LBNF/DUNE requirements and comply with this Quality Assurance Plan.
The LBNF Project Management, DUNE Technical Coordinator or Project Partners requesting procurement of items and services are responsible for providing all documentation that adequately describes the item or service being procured so that the Supplier can understand what is required for the Projects’ acceptance.
Development of this documentation may be achieved through the involvement of Sub-Project Managers and Consortia Leaders and established review and approval systems.

## Slide 43
The following factors will be considered for review and approval of this documentation:
Inclusion of technical performance requirements
Identification of required codes and standards, laws and regulations
Inclusion of acceptance criteria, including requirements for receiving inspection and/or source inspection
LBNF/DUNE requirements for vendor qualifications and certifications
LBNF/DUNE intention to perform acceptance sampling in lieu of full inspection and test item acceptance
NOTE: For Vendor Qualification and acceptance of purchased items or material by Project Partners this may be performed under their own institution requirements.

## Slide 44
Previously accepted Suppliers shall be monitored to ensure that they continue supplying acceptable items and services.
Source surveillance is the recommended method to ensure that items are free of damage and that specified requirements are met.
Supplier deliveries will be verified against previously established acceptance criteria.
Unacceptable Supplier items or services shall be documented.
Records of Supplier performance, Inspection Test Records (ITR) and contract-required submittals, are kept for future procurement consideration.

## Slide 45
Inspections shall be conducted to detect counterfeit and/or suspect parts.
For work funded by DOE, when counterfeit/suspect parts are found, they will be identified, segregated, and disposed of in accordance with the Fermilab Quality Assurance Manual Chapter 12020 Suspect/Counterfeit Items (S/CI) Program.
DUNE Consortia may use their own institution’s procedure for counterfeit/suspect parts.

## Slide 46: Inspection and Acceptance Testing
There are two inspection types in LBNF/DUNE:
1) inspections associated with Architecture/Engineer (A/E) design and construction (Conventional Facilities); and,
2) inspections associated with electrical, mechanical and structural component manufacture and installation.
Acceptance testing generally applies only to item 2 and to computer code.

## Slide 47
Inspections of A/E construction activities are established by the A/E responsible for the design and certification of the completed work.
Once the work is designed, the A/E will identify the applicable codes, standards and specific testing requirements to apply from a set of established criteria.
At the completion of specified stages of construction, the A/E signs off that the completed work is in compliance. LBNF will use a commissioning agent for the Conventional Facilities procurements.

## Slide 48
Equipment used for all inspections and tests shall be calibrated and maintained.
Calibration will be controlled by a system or systems making appropriate use of qualified calibration service providers.
Sub-Project Managers and Consortia Leaders shall ensure that equipment requiring calibration:
have their calibration status identified on the item or container,
are traceable back to the calibration documentation and
are tracked to ensure the equipment is calibrated at the required interval.
The LBNF/DUNE QAM shall oversee and support the LBNF and DUNE calibration programs.

## Slide 49
Inspection and testing of electrical, mechanical and structural components, associated services, and processes by Project Partners shall be conducted using acceptance and performance criteria.
ITR forms, Travelers, and a Traveler database are the primary tools used to organize this activity.
Inspections will be conducted in accordance with the Graded Approach.

## Slide 50: Assessments
LBNF/DUNE management at all levels shall regularly evaluate achievement of personnel relative to performance requirements and shall appropriately validate or update performance requirements and expectations to ensure quality of products and processes.
The management assessment process shall periodically include an evaluation of the organization's products and processes to determine whether the Project's missions are being fulfilled.
The results of management assessments that focus on means of improving the quality of work performed shall be reported to the appropriate responsible line or Project management level.

## Slide 51
When performance does not meet established standards, management shall, with the assistance of others with appropriate expertise, determine the cause and initiate corrective action. QA representatives may assist, lead, or facilitate cause investigations.

## Slide 52
The LBNF/DUNE QAM will plan reviews as independent assessments to assist LBNF Project Management and the DUNE Technical Coordinator in identifying opportunities for quality/performance-based improvement and to ensure compliance with specified requirements. Independent assessments of the LBNF and DUNE Projects can be requested by LBNF/DUNE management.
Independent assessments typically focus on quality or ESH&Q management systems, self- assessment programs, or other organizational functions identified by management.
The LBNF and DUNE Projects use a formal process for assigning responsibility in response to recommendations from independent assessments.
These recommendations are tracked to closure.

## Slide 53
Personnel conducting independent assessments shall be technically qualified and knowledgeable in the areas assessed.
A qualified lead assessor (auditor), who is a Subject Matter Expert (SME) in the technical area of assessment, is required.
The team may include other SMEs to evaluate the adequacy and effectiveness of activities only if they are not responsible for the work being assessed.

## Slide 54
The Fermilab Directorate appoints an independent Long Baseline Neutrino Committee (LBNC) to advise it and LBNF and DUNE Management. The role of this standing committee is described in the LBNF/DUNE PMP.
The DOE and other funding agencies perform external assessments that provide an objective view of performance and thus contribute to the independent assessment process.
Since such assessments are not under the control of LBNF/DUNE, they are not necessarily considered a part of the independent assessment criterion.
However, LBNF/DUNE management considers external assessment results in determining the scope and schedule of independent assessments.