## Slide 1
Status & Plans
Eric James
Far Detector Technical Board Meeting
November 29, 2018

## Slide 2: TDR
Production of TDR volumes on the needed time scale remains highest collaboration priority
My understanding is that we met the deadline for producing first drafts of the SP-HV, SP-APA, and SP-DAQ chapters
Targeting the release of these three chapters to the LBNC prior to end of December

## Slide 3: Near-term Schedule
Consortium | 1st draft | 2nd draft | LBNC
SP-HV | November 2, 2018 | December 7, 2018 | December 21, 2018
SP-APA | November 2, 2018 | December 7, 2018 | December 21, 2018
SP-DAQ | November 2, 2018 | December 7, 2018 | December 21, 2018
SP-PDS | November 30, 2018 | January 11, 2019 | January 25, 2019
SP-CISC | November 30, 2018 | January 11, 2019 | January 25, 2019
TC | November 30, 2018 | January 11, 2019 | January 25, 2019
PHYSICS | November 30, 2018 | January 11, 2019 | January 25, 2019

## Slide 4: TDR Draft Schedule
  December: SP high voltage, SP APAs, SP DAQ
  January: SP photon detection system, SP CISC, Technical Coordination
  February: SP electronics, DP electronics
  March: DP high voltage, SP installation/integration
  April: DP photon detection system, SP Calibration
  May: DP DAQ, DP installation/integration, DP CISC
  June: DP CRPs, DP Calibration
  July: Final version of complete TDR to LBNC
(note: month indicated implies end-of-month delivery)

## Slide 5: QA/QC and ES&H
Heard from Kevin about plans for how his team will interact with the consortia to further develop QA/QC plans
At last meeting asked consortia to nominate contact persons for QA/QC and ES&H
Only one response received up to this point – needed as soon as possible now that our QA Specialist (Jim Mateyack) is in place

## Slide 6: ProtoDUNEs
There will be a meeting on December 4th at CERN starting at 2:30pm (Geneva time) to discuss the ProtoDUNE-SP run plan for 2019
Per Gina’s presentation, consortia should propose needed data sets and tests and identify the required resources
Current expectation is that there will be a small (3-5 person) on-site team to maintain the detector and provide support

## Slide 7: Schedule
The final versions of the TDR volumes will incorporate updated schedule information that accounts for the current state of the excavation schedule for the underground areas
For the moment, the excavation schedule remains a work-in-progress, and we do not want to “jump the gun” on advertising new dates until we are confident that we have the correct ones in hand

## Slide 8: Costs
Need to put together a plan for next iteration
Don’t expect that there will be a lot of changes to the cost estimates themselves (still based primarily on ProtoDUNE)
Big Issue is establishing a common format and providing a consistent level of backup material
Will propose a plan for this at next Technical Board Meeting – Next iteration due by March

## Slide 9: Schedule/Cost Work Days
Between now and the end of the year, I would like to schedule days where Ami and I can meet with consortia leadership team members on an individual basis to work on further developing our construction schedule and cost estimates
For consortia centered in Europe, Ami and I plan to be at CERN during the week of Dec. 3 and are leaving open the days of Dec. 5-6 to hopefully have some of these interactions

## Slide 10: Upcoming Schedule
DAQ 30% Design Review: Dec 3-4 @ CERN
ProtoDUNE-SP 2019 Run Plan Meeting: Dec 4 @ CERN
LBNC Meeting: Dec 7-9 @ CERN
LBNF/DUNE-US Project Review: Jan 8-10 @ FNAL
DUNE Collaboration Meeting: Jan 28-Feb 1 @ CERN
APA 60% Design Review: Feb 7-8 @ PSL
CE Mechanical 60% Design Review: Feb 11-12 @ BNL
RRB Meeting: March 14-15 @ FNAL
LBNC Meeting: April 1-3 @ FNAL

## Slide 11: LBNC Meeting Next Week
Agenda has been finalized (DocDB #11563)
Presenters are requested to post their slides to the practice talk agenda page by Wednesday, December 5th
  https://indico.fnal.gov/event/19173/
Practice talks will be the afternoon of December 6th at CERN starting at 1pm
  https://indico.cern.ch/event/777482 (Vidyo connection)

## Slide 12: Detector Specifications
Executive Board approved and took ownership of parameter specifications list for SP FD at its last meeting on 11/15 (DocDB #11074)
As requested by LBNC, a document has been written that maps DUNE primary physics goals into the five specifications on this list identified as the primary physics drivers (DocDB #11431)
Next step is to repeat this process for the DP FD
  Need to discuss with relevant consortia leadership teams next week at CERN