## Slide 1
Conventional Facilities (WBS 121.06)
Steve Dixon
PIP-II Independent Project Review
4-6 December 2018

## Slide 2: Outline
Scope/Deliverables
Requirements
Interfaces
Preliminary Design
Design Review Plan
Technical Progress to Date
Organization
Steps to CD-2
ESH&Q
Risks and Mitigations
Responses to CD-1 recommendations
Breakout Session topics
Summary

## Slide 3: About Me:
PIP-II Level 2 Manager for Conventional Facilities
Relevant Experience
  Licensed Architect;
  Project Management Professional (PMP);
  LEED Accredited Professional;
  26+ years at Fermilab;
  NOvA Project L2 Manager for Site and Buildings;
    2014 CD-4
    2015 U.S. DOE Secretary’s Award for Excellence
  General Plant Project Manager for 15+ years
    Short Baseline Neutrino (SBN) Near Detector Building;
    Short Baseline Neutrino (SBN) Far Detector Building;
    Experimental Operations Center;

## Slide 4: Scope and Deliverables
Conventional Facilities includes the design, procurement and construction of the utilities, roads, structures, enclosures and buildings to support the installation, assembly and operation of the technical components. [1]
WBS
  121.06.01 – Project Management and Coordination
  121.06.02 – Site Preparation
  121.06.03 – Cryogenics Plant Building (23,245 square feet)
  121.06.04 – Utility Plant Building (21,275 square feet)
  121.06.05 – Linac Complex (88,550 square feet)
  121.06.06 – Booster Connection (7,750 square feet)
Charge #1
[1] See WBS Dictionary in PIP-II-doc-599 for complete description

## Slide 5: Scope and Deliverables
Conventional Facilities includes the design, procurement and construction of the utilities, roads, structures, enclosures and buildings to support the installation, assembly and operation of the technical components.
WBS
  121.06.01 – Project Management and Coordination
  121.06.02 – Site Preparation – CD-3A Request
  121.06.03 – Cryogenics Plant Building – CD-3A Request
  121.06.04 – Utility Plant Building
  121.06.05 – Linac Complex – CD-3B Request
  121.06.06 – Booster Connection – CD-3B Request
Charge #1

## Slide 6: Scope and Deliverables
Cryo Plant Building
Utility Plant Building
Linac Complex
Booster
Connection

## Slide 7: Conventional Facilities System Requirements
Conventional Facilities Systems Function and Configuration Document [1]
Facility Scope
  Associated conventional facilities including enclosures, equipment galleries, and utilities. The linac enclosure will be constructed with a length to accommodate at least two HB650 cryomodules beyond the nominal compliment required for 800 MeV.
Functional Requirements
  The siting of the PIP-II facility will be consistent with future replacement of the existing 8-GeV Booster with either an 8 GeV Rapid Cycling Synchrotron or superconducting pulsed linac.
  The siting of the PIP-II facility will be consistent with future upgrades to provide 100 kW beams to the Mu2e hall on the Muon Campus.
  The SC Linac will be constructed in a manner that allows installation and commissioning without interruption to ongoing accelerator operations.
  Facility Lifetime equal to or greater than 40 years
Safety Requirements
  The Project will be built to applicable DOE and FNAL engineering, safety, and radiation standards as outlined in the Fermilab Engineering Manual and Fermilab ES&H Manual.
Charge #1
[1] Conventional Facilities Systems Function and Configuration Document, TeamCenter Document ED0008133
Notes: Mention that these flow down from Global Requirement Document (TeamCenter ED0008053)

## Slide 8: Interfaces
Project Interfaces
  Managed through PIP-II processes [1]
  ED0007697 – Site Preparation
  ED0007698 – Cryogenic Plant Building
  ED0007699 – Utility Plant Building
  ED0007700 – Linac Complex
  ED0007702 – Booster Connection
  Conventional Facilities interfaces with all Level 2 subprojects
Fermilab Interfaces
  Infrastructure Connections (Managed through FESS processes)
  General Plant Projects (Managed through FESS processes)
  Accelerator Operations (Managed through AD processes)
International Interface (Managed through WBS 121.02)
  Cryogenic plant is Indian partner deliverable
Charge #1
[1] See PIP-II Systems Engineering Management Plan at PIP-II-doc-1539
FESS is Facilities Engineering Services Section
SC4-Dixon

## Slide 9: Preliminary Design and Design Maturity
Site Preparation (WBS 121.06.02)
  Site Clearing construction package[1]
  Site Work construction package[2]
  Electrical Feeder construction package[2]
  Site Restoration/Landscaping construction package[2]
  Final Design Completion scheduled for January 2019
Cryogenics Plant Building (WBS 121.06.03)
  Technical Requirements Complete [3]
  Final Design Completion scheduled for Q2 FY19
Charge #1
View Looking Southwest
[1] See TeamCenter ED0008374
[2] See TeamCenter ED0008459
[3] See TeamCenter ED0008373
SC4-Dixon
SC4-Wielgos

## Slide 10: Preliminary Design and Design Maturity
Conceptual Design Complete:
  Utility Plant Building (WBS 121.06.04)
  Linac Complex (WBS 121.06.05)
    High Bay Building
    Linac Tunnel
    Linac Gallery
    Beam Transfer Line
  Booster Connection (WBS 121.06.06)
Charge #1

## Slide 11: Design Review Plan
Charge #2
Review Class | L2 WBS | L3 WBS | Activity ID | Key Design Elements Reviewed / Activity Name | Review Date | Teamcenter ED# | Indico Link | Other Review Record Link
Conceptual Design Review | 121.6 |  |  | Conventional Facilities | 19-Sep-16 | ED0005473 |  | 
Conceptual Design Review | 121.6 |  |  | Value Engineering of CF | 18-Jan-18 |  |  | PIP-II-doc-1377
Requirements Review | 121.6 |  |  | Conventional Facilities | 6-Apr-18 | ED0007517 |  | 
Preliminary Design Review | 121.6 | 121.6.02 | CFSP10150 | CnvF_SitePrep_Des: T6 MS - PDR for Site Prep | 4-Sep-18 | ED0008236 |  | 
Final Design Review | 121.6 | 121.6.02 |  | Site Clearing Package | 8-Oct-18 |  |  | FESS CCR Database
Preliminary Design Review | 121.6 | 121.6.03 | CFCB21990 | CnvF_CryoB_Des: T6 MS - PDR for Cryoplant Building | 18-Mar-19 |  |  | 
Preliminary Design Review | 121.6 | 121.6.05 | CFLC11700 | CnvF_Cmplx_Des: T6 MS - PDR for Linac Complex | 1-May-20 |  |  | 
Preliminary Design Review | 121.6 | 121.6.06 | CFBC21790 | CnvF_ BstrC_Des: T6 MS - PDR for Booster Connection | 1-May-20 |  |  | 
Preliminary Design Review | 121.6 | 121.6.04 | CFUB21890 | CnvF_UtilB_Des: T6 MS - PDR for Utility Building | 2-Mar-20 |  |  | 

## Slide 12: Progress to Date Since CD-1
General Progress Milestones
  January 2018 - Value Engineering Workshop with the CF team [1]
  April 2018 – Received updated cost/schedule estimate [2]
  June 2018
    Completed Geotechnical Engineering Investigation [3]
    Chartered and held the first meeting of the PIP-II Architectural Advisory Board [4]
  July 2018
    Received favorable wetland determination for the US ACOE [5]
    Developed preliminary shielding strategy for Cryogenics Plant Building with 121.03 (Accelerator Systems)
  November 2018 – Preliminary Design Report
  December 2018 – Completed the A/E recompete process
Charge #1, 2
[1] See PIP-II-doc-1377
[2] See PIP-II-doc-333
[3] See PIP-II-doc-1533
[4] See PIP-II-doc-1308 and PIP-II-doc-1548
[5] See PIP-II-doc-1630

## Slide 13: Progress to Date Since CD-1
Site Preparation – WBS 121.06.02
  Design is ~90% Complete (scheduled for completion in January 2019)
  Developed a Site Clearing construction package [1]
  Received Authorization for Site Clearing package [1]
Cryo Plant Building – WBS 121.06.03
  Completed Technical Requirements Design [2]
  Completed Water Quality Testing [3]
Charge #1, 2
[1] See TeamCenter ED0008374
[2] See TeamCenter ED0008373
[3] See PIP-II-doc-155

## Slide 14: Organization
WBS 121.06.01
Project Management
S. Dixon
WBS 121.06.02
Site Preparation
R. Wielgos
WBS 121.06.03
Cryoplant Building
S. Dixon (Act.)
WBS 121.06.04
Utility Plant Building
E. Huedem
WBS 121.06.05
Linac Complex
S. Dixon
WBS 121.06
CONVENTIONAL FACILITIES
S. Dixon
System Manager
WBS 121.06.06
Booster Connection
R. Wielgos

## Slide 15: Next Steps toward CD-2/3A
Site Preparation – WBS 121.06.02 (CD-3A Request)
  Complete the Site Clearing construction (FY19)
    (Goal: Ready to start construction at the time of the Groundbreaking)
Cryo Plant Building – WBS 121.06.03 (CD-3A Request)
  Complete Final Design (anticipated for Q3 FY19);
  Initiate Procurement Processes to be ready to start construction (anticipated for Q2 of FY19);
  Construction start dependent CD-3A approval and EA FONSI.
CD-2 Activities
  Coordination Mock Up of Linac Tunnel (anticipated in FY19);
  External Independent Cost Estimate.
Charge #5
EA is Environmental Assessment
FONSI is Finding Of No Significant Impact

## Slide 16: Schedule
Charge #3

## Slide 17: Schedule With CD Approval Requests
Charge #3
CD-3A Request
CD-3B Request
Prior to CD-2/3A Approved

## Slide 18: T5 Milestones
Charge #5

## Slide 19: Environment Safety and Health (ES&H)
Consider and plan for ES&H issues throughout the project life cycle
Conceptual Design Phase
  ES&H input includes review of the design, input from Tritium Task Force and Life Safety Analysis [1]
Design Phase
  ES&H is considered in A/E selection process;
  ES&H is included in design reviews;
  Implement Safety by Design process;
  Incorporate Hazard Analysis Report hazards in the design process [2]
Procurement/Construction Phase
  Include safety performance as part of the subcontractor selection process;
  Detail the responsibilities for team members including the Construction Subcontractor and Fermilab Construction Coordinator;
  Independent oversight by ESH&Q Section
Charge #6
[1] Life Safety Analysis can be found at PIP-II-doc-120
[2] Hazard Analysis Report can be found at PIP-II-doc-140

## Slide 20: Quality Management
Charge #6
Integrated Team Approach
  PIP-II Project Processes [1]
  A/E Design Processes *
  A/E Commissioning * Processes
  FESS Subject Matter Experts
  Laboratory Experts
  Construction Subcontractor *
(*) Quality requirements are incorporated into consultant selection and subcontract terms and conditions
[1] PIP-II Quality Assurance Plan is at PIP-II-doc-142
See PIP-II-doc-2291 for Quality Assurance Responsibility Matrix
SC4-Dixon

## Slide 21: WBS 121.06 Risk Management
Top 3 Risks
Conventional Facilities Risks
  High Risks: 0
  Medium Risks: 13
  Low Risks: 30
Note: RT-121-01-006 – Inflation Exceeds Assumption is a Project Management Medium Risk
Charge #2,7
RI-ID | Title
RT-121-06-001 | Subproject requirements changes impact the Conventional Facilities
RT-121-06-002 | Accelerator shutdown schedule changes
RT-121-06-003 | Construction bids exceed estimates
SC4-Dixon

## Slide 22: Response to Recommendations
Director’s CD-1 Review (October 2017) [1]
  2 Recommendations, both closed
DOE CD-1 Review (December 2017) [2]
  3 Recommendations, all closed
P2MAC Review (March 2018) [3]
  3 Recommendations, all closed
Charge # 8
[1] Review ID 47866
[2] Review ID 48107
[3] Review ID 48469
SC4-Dixon

## Slide 23: Breakout Sessions
Conventional Facilities In Depth
  Schedule, Risks, Interfaces, ESH&Q and Review Recommendations
Site Preparation
Laboratory Interfaces
Cryogenics Plant Building (Joint Session with SRF/Cryo)
Requirements Documentation
SC4-Dixon
SC4-Wielgos
SC4-Wielgos
SC3-Hansen
SC4-Dixon
SC2-Hunt
SC4-Dixon

## Slide 24: Summary
Conventional Facilities scope and deliverables are understood and are based on requirements;
Project Processes are in place and functioning;
  (Risk Management, ES&H, Quality Management, Reviews)
CD-3A Scope (Site Preparation and Cryo Plant Building) is understood and progressing;
We are on track for CD-2/3A
Thank you for your attention and we look forward to your feedback

## Slide 25: END