## Slide 1
WBS121.04.06 – Linac Installation and Commissioning Overview
SC2 Accelerator Complex Upgrades, Linac Install. and Comm.
Fernanda G. Garcia
PIP-II IPR
4-6 December 2018

## Slide 2: Outline
Installation and Commissioning
  WBS 121.04 overview
Statement about PIP2IT mission
Changes since CD-1
  boundaries between CF - Building Infrastructure - Linac Installation
Risks
Final Remarks

## Slide 3: WBS 121.04 Overview
Scope of WBS 121.04
  WBS 121.04.01 Project Management
  WBS 121.04.02 Warm Front-End
    normal conducting warm front end, PIP2IT HEBT line
  WBS 121.04.03 Test Infrastructure
    3 test stands for PIP-II cavities test and cryomodules RF cold test, including cryogenics distribution
  WBS 121.04.04 Building Infrastructure
    cooling/power/compress gas/racks/cables proc.
  WBS 121.04.05 Linac Installation
    cable pulls and termination, alignment network, installation machine components, design cryomodule stands, mover and warm units support, logistic
  WBS 121.06.06 Beam Commissioning
    Beam commissioning plan for PIP2IT and PIP-II, high level applications, temporary diagnostic carts
Completion of WBS 121.04
    When PIP-II achieve all 4 key performance parameters
Execution
  WBS 12.04 primarily contains DOE funded tasks performed at Fermilab
  There are also in-kind contribution towards magnets for the WFE and 650 warm region which means there are joint design efforts and integration for these elements

## Slide 4
Installation and Commissioning
  WBS 121.04 overview
  What’s in this presentation and what you will see in this session
Statement about PIP2IT mission
Changes since CD-1
  boundaries between CF - Building Infr. - Linac Installation
Intermediate Milestones (?)
Risks
Final Remarks

## Slide 5: PIP-II Injector Test (PIP2IT)
PIP-II Injector Test (PIP2IT)
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
Now
FY20

## Slide 6: Slide from P. Derwent presented at CD-1

## Slide 7: PIP-II Injector Test (PIP2IT)
All Hands Meeting May’2018

## Slide 8: PIP-II Injector Test (PIP2IT)
Phase 1: retirement of risks associated with operation of the PIP-II linac in pulsed mode as required for neutrino operations and described in the CDR (1% duty factor). The primary risks to be retired during this period (now-2020) include:
Achievement of required beam characteristics from the ion source through the SSR1 cryomodule
  Operated 2 mA, 20 Hz, 550 msec through MEBT ✓
Demonstration of MEBT chopper operations at a level required for Booster injection
  Operated 1 (of 2) prototype kickers with these parameters ✓
Demonstration of the operation of the HWR cryomodule, with beam, in close proximity to the MEBT beam absorber
Demonstration of stable beam acceleration in the protoSSR1 cryomodule, under the full control of prototype RF control systems, including resonance control within the cavities
40 m, ~25 MeV
30 keV
RFQ
MEBT
HWR
SSR1
HEBT
LEBT
2.1 MeV
10 MeV
25 MeV
Now
FY20
SC2-Prost

## Slide 9
Installation and Commissioning
  WBS 121.04 overview
  What’s in this presentation and what you will see in this session
Statement about PIP2IT mission
Changes since CD-1
  boundaries between
    Conventional Facility
    Building Infrastructure
    Linac Installation
Risks
Final Remarks

## Slide 10: Overview of changes from CD-1
Organization
Significant modified from CD-1 to provide more effective structure for managing
The 121.04 WBS was created as a result of the new structure
  Split Installation and General System Services into 3 pieces
    121.04.05 Linac Installation
    121.04.06 Beam Commissioning
    121.04.04 Building Infrastructure
Scope of work was re-distributed accordingly among the L3 levels
  Reflected on the Interfaces and Requirement documents

## Slide 11: Changes since CD-1
Warm Front End
Scope unchanged
Test Infrastructure
Scope inherited/added
  Added PIP2IT cave setup to test PIP-II 650 cryomodules in conjunction with SSR
  Added Horizontal Test Stand -2 (HTS-2) at Meson Detector Building (MDB)
  Inherited cryogenic distribution line scope for PIP2IT from SRFCRYO
Scope removed
  Modifications to CMTS1 to test PIP-II 650 cryomodules
PIP2IT Test Cave
SSR 325MHz Test Stand
HWR/650 MHz Test Stand
SC2-Prost
SC2-Leibfritz

## Slide 12: Changes since CD-1
  Building Infrastructure
  New WBS L3 structure since CD-1
    Scope inherited/added
      Inherited general system services scope from Installation
        Close collaboration with conventional facility
      Added cables and connectors procurement
  Linac Installation
  Scope changed since CD-1
    Scope removed:
      beam transfer lines installation move to Rings Installation under Accelerator Upgrades
    Scope inherited/added:
      Added design and build of the warm unit structures
      Added cryomodules ready for installation transportation from storage area to the PIP-II complex
SC2-Hunt
SC2-Baffes

## Slide 13
  Beam Commissioning
  New WBS L3 structure since CD-1
    Scope inherited/added
      Added PIP2IT beam commissioning
      Inherited High Level Applications development
      Added Accelerator Readiness Review (ARR)
Changes since CD-1
SC2-Garcia

## Slide 14: Boundaries between Conventional Facility / Building Infrastructure / Installation

## Slide 15
Installation and Commissioning
  WBS 121.04 overview
  What’s in this presentation and what you will see in this session
Statement about PIP2IT mission
Changes since CD-1
  boundaries between CF - Building Infr. - Linac Installation
Risks
Final Remarks

## Slide 16: Risk Management (121.04)
Charge #2,7
Link to Risk Register: https://fermipoint.fnal.gov/organization/ocoo/ippm/Lists/Risk%20Register/all-risks.aspx
Linac Installation and Commissioning Risks
  High Risk: 0
  Medium Risk: 5
  Low Risk: 4
Details during individual sub-systems presentations

## Slide 17: Final Remarks
Since the previous IPR considerable work has been conducted in preparation for CD-2/3A
  Management
    New WBS structure implemented and scope adjusted accordingly
    Build up staff
    Ongoing work on developing a comprehensive resource loading schedule
    All functional requirements and interfaces were revised
      currently under review – next step approval process
    Risks were revised
  Next presentations more details on all fronts
    requirements, interfaces, technical status and detailed risks
    Let’s start!