## Slide 1
WBS121.04.06 – Beam Commissioning
SC2 Accelerator Complex Upgrades, Linac Install. and Comm.
Fernanda G. Garcia
PIP-II IPR
4-6 December 2018

## Slide 2: Outline
Scope/Deliverables
Requirements
Interfaces
Preliminary Design, Maturity
Technical Progress to Date
ESH&Q
Risks and Mitigations
Summary

## Slide 3
Many thanks to the Beam Commissioning team
A. Shemyakin , L. Prost, A. Saini
for their valuable discussion and contributions to this talk

## Slide 4: About Me:
Role
  L2 manager for Installation and Commissioning
  L3 manager for Beam Commissioning
Relevant Experience
  Scientist – 22 years of experience at the lab
  14 years in Accelerator Division
    10 years Linac Group Leader
    PIP Deputy Project Manager
    PIP L2 manager for Linac Upgrade
    PIP L3 manager for Linac 200 MHz RF Power Upgrade
  L2 manager for SBN-FD (ICARUS) Installation and Integration (2015-2018)
  Head of 400 MeV Transfer Line (2004-2008)
    Designed new injection scheme lattice into Booster
    Leadership role during installation and commissioning phase

## Slide 5: Scope and Deliverables
The PIP-II Beam Commissioning WBS scope includes the work related with
  Beam commissioning of the accelerator sections (Warm Front End (WFE), Super-Conducting Linac (SCL), Beam Transfer Line (BTL)/Beam Absorber Line (BAL)), including beam commissioning of booster
    Ensure readiness of plans/procedures for commissioning preparation and commissioning
    Ensure readiness of tools
    Establish teams
    Organize, execute, analyze beam commissioning data
Charge #2
WBS Dictionary pip2-docdb#599
WFE
WFE
SCL linac
main absorber / BAL
booster
does not require
program shutdown
Deliverable is a machine achieving objective KPP’s that is handed off to operations
BTL

## Slide 6: PIP-II Beam Parameters
    Requirements for future injection into the Booster:
      0.55 ms x 20 Hz at 5 mA from the Radio Frequency Quadrupole (RFQ)
      Medium Energy Beam Transport (MEBT) chopping system removes ~half of all bunches to create a non-periodic pattern optimized for filling the Booster RF buckets.
Charge #2

## Slide 7: Beam Commissioning Requirements
FRS: ED0008026,
Beam commissioning plan
  Complete suite of procedures, documentation and schedule for beam measurements
High Level Applications
  Provide list of applications needs during beam commissioning to Controls
  Support development and test of applications
Beam commissioning shifts
  Setup tools to document results and findings during shifts
  Collaborate with Accelerator Physics lattice group
    Perform and communicate optics results to AP lattice group
    Optimize accelerator performance based on simulation results
  Shielding Validation
    Support shielding validation effort
Charge #2
pip2-docdb#2495

## Slide 8: Interfaces
The nature of interfaces of this WBS is organization and scheduling
  Therefore, does not fit in the normal structure of an Interface document
Interfacing with mostly all Accelerator Systems WBS as far as coordination and schedule of beam commissioning period
  Accelerator Physics
    Beam dynamics and simulation
    Instrumentation
    LLRF
    Controls
      High level applications
and interfacing within the 121.04 WBS
  Linac Installation
    Schedule coordination
    Documentation handoff
    Hardware checkout
Charge #2

## Slide 9: Preliminary Design and Design Maturity
Developing a phased commissioning strategy
  At a conceptual level
  Based on beam commissioning experience at similar machines
    SNS had 7 stages interleaved with installation activities,
    “… Although having many beam commissioning stages complicated planning and installation activities, the benefit was well worth this complication.”
No reviews in this WBS have taken place, yet
Charge #2
J. Galambos, HB2006

## Slide 10: Parameters Affecting the Commissioning Strategy
PIP-II superconducting section starts at 2.1 MeV
  Low energy compared to SNS (185 MeV) and ESS (90 MeV)
    SNS/ESS normal conducting section use insertable devices
  Large phase advance through low-energy SRF
    ~10π to 185 MeV and ~4π to 800 MeV
    Similar to SNS/ESS for the same energies
No insertable devices in SC linac (2.1 – 800 MeV)
  Diagnostics: beam position monitors, laser wires, current monitors
Charge #2

## Slide 11: PIP-II Phase Advance Through the SCL
(A. Saini). Red arrows – LWs, green rectangles – ACCT
HWR SSR1 SSR2 LB650 HB650

## Slide 12: Progress to Date
Organization
  Bi-weekly commissioning meetings started in Q1FY19
    Frequency will be adjusted as needed throughout commissioning
Tasks to perform
  PIP2IT beam is the precursor for PIP-II beam commissioning plan
    WFE prepares the beam with the proper characteristics
    Goal: accelerate beam through the HWR and protoSSR1
      gain experience accelerating proton beam through superconducting cavities
      understand the beam loss at frequency transition (longitudinal tails)
      develop/optimize LLRF resonance control loops algorithms
      test the MPS compatibility with SRF tolerance
  Apply lessons learned post PIP2IT to further develop PIP-II commissioning
    Review beam commissioning experience
    Review the tools/applications/simulations/monitoring required for the commissioning phase
Charge #1

## Slide 13: Preparation for PIP-II Commissioning at PIP2IT
LEBT scheme provides constant beam properties throughout the pulse
  Beam parameters at 10 µs and at the end of a 0.55 ms pulse are the same to within several %
Variation of beam parameters through 0.5 ms pulse. Left – normalized vertical emittance and image integral (proportional to the beam current). Right – Twiss parameters.
Charge #1
First beam thru superconducting linac will be at low intensity, short pulse length (10 µs ) and low repetition rate “diagnostic mode”

## Slide 14: Preparation for PIP-II Commissioning at PIP2IT
Initially, the beam to be accelerated thru the superconducting region will be scraped in the MEBT with two set of scrapers
  4 plates in each, ~90º phase advance
“low-emittance beam” mode
5 mA beam is scraped vertically to 1.5 mA.
Phase portrait of the nominal 5 mA beam.
Charge #1

## Slide 15: Phased Commissioning
Beam commissioning at PIP-II foreseen to occur in series with installation activities
  Phased commissioning approach
    Warm Front End (WFE) (2.1 MeV)
    Superconducting Linac – Phase 1 & 2
    Beam transmitted to the straight ahead dump
    Beam transmitted to the main absorber (BAL)
    Beam transmitted to the Booster injection region (BTL)
Charge #2

## Slide 16: Phases in the WFE & Superconducting Linac
WFE (0.030 - 2.1 MeV)
  Goal:
    recover WFE beam parameters obtained
    at PIP2IT and set up the machine for
    SCL beam commissioning
  Configuration:
    Ion Source (IS), Low Energy Beam Transport (LEBT), RFQ, and MEBT
  Beam mode:
    up to full power to the MEBT absorber
Superconducting section (2.1 – 800 MeV)
  Goal:
    instrumentation commissioning, RF synchronization, pass beam through the superconducting section, measure rms beam properties, beam transmission
  Configuration: two commissioning break-points
    Phase 1 (~ 35 MeV – end of SSR1)
    Phase 2 (~185 MeV – end of SSR2)
    temporary diagnostic line with a low-power beam stop for each
  Beam mode:
    low-emittance mode with low duty factor
Charge #1
WFE
WFE
SCL linac
main absorber / BAL
booster

## Slide 17: Phases for Transfer Lines
Beam to the straight ahead dump and main absorber
  Goal:
    measure transverse optics of the
    transfer line; demonstrate long beam
    pulses operation, achieve KPP#1&2
  Configuration:
    all cryomodules and warm units
    installed and checked out,
    upstream hardware fully operational including LLRF beam-loading compensation
    transfer line up to main absorber installed and checked out
  Beam mode: diagnostic mode, capability for long beam pulses
Beam to Booster Injection
  Goal:
    transport beam to the booster injection region and inject into the ring, achieve KPP#3
  Configuration: last portion of the booster transfer line
    equipment installed and checked out
    Booster injection region installed and checked out
  Beam mode:
    diagnostic mode, establish circulating beam in the Booster
Charge #1
WFE
WFE
SCL linac
main absorber / BAL
Booster
Straight-ahead dump

## Slide 18: ESH
Beam commissioning activities will follow the Fermilab and PIP-II safety standards and practices
  PIP-II Integrated Safety Management Plan pip2-docdb #141
  Laboratory and DOE standards and practices
    Prior to beginning beam commissioning, an Accelerator Readiness Review is required
      Requirements established in DOE O 420.2C, “Implementation Guide for Safety of Accelerator Facilities”
      Beam commissioning is planned as a staged approach which will result on a staged Accelerator Readiness Review
      Plan will be worked out with Fermi Site Office and appropriate documented
    Fermi Radiological Control Manual, Fermi ES&H Manual
Planning Phase
    Implement Safety by Design process
    Incorporate Project Hazard Analysis Report (PHAR) in the planning process
      Hazards include:
        Radiation Hazards:
          Residual radioactivity after beam operations
          Radiation dose rates in excess outside the enclosure
      Radiation safety is a significant part of the PIP-II Project – within L3 Accel. Phys. WBS
Charge #6

## Slide 19: Quality Management
Quality Assurance and Control
  PIP-II Project Quality Assurance Plan pip2-docdb #142
Create the details QC plan of the beam commissioning phase
  Documentation
    Daily savings
    Develop machine operation procedures and documentation
  Apply lessons learned from similar accelerators
    From SNS, significant testing and operational experience led to better understanding of the systems
  Transition to operations
    Involve Accelerator Division Operation Department (AD/Ops) at earliest opportunity
      Possibly during commissioning at a limited scope
    Collaborate with AD/Ops to integrate with accelerator complex standards
      LOTO procedures, monitoring tools and programs, saves, e-log,
      Provide support during transition
Charge #6

## Slide 20: WBS 121.04.06 Risk Management
Charge #2,7
Beam Commissioning Risks
  High Risk: 0
  Medium Risk: 2
  Low Risk: 1
RT-121-04-002 Machine has performance problems during commissioning
Mitigation: This is a technical risk with a high impact to schedule & cost
PIP2IT will enable a variety of system-level tests to be performed on many critical systems providing opportunity for the majority of the issues to be identified and addressed before the accelerator components are installed in PIP-II tunnel
Perform cold RF-cryomodule test on all cryomodules
Verification of RF power systems before and after installation
First version of machine protection system is functional and has been tested at PIP2IT. Further development is needed to meet all requirements. However, is inevitable that problems will be discovered during commissioning

## Slide 21: WBS 121.04.06 Risk Management
Charge #2,7
Beam Commissioning Risks
  High Risk: 0
  Medium Risk: 2
  Low Risk: 1
RT-121-04-019 Vacuum incident during beam commissioning
Mitigation: This is a technical risk with a high impact to schedule & cost
The design of the MEBT takes in to account vacuum management techniques to protect the superconducting section of the machine. Furthermore, the final MEBT for PIP-II will be longer to increase the separation between the absorber and the first cryomodule
System is installed at the PIP2IT - awaiting beam tests in FY20

## Slide 22: Summary
  Requirements and interfaces are identified
  Conceptual beam commissioning plan is in place
  PIP2IT has been and will be an important part of PIP-II
    WFE beam parameters already demonstrated
    Superconducting beam running period will refine the PIP-II beam commissioning plan
  Risks are identified and mitigation in place
  Initial assessment of hazards analysis
  Thank you for your attention

## Slide 23: END