## Slide 1
Cryogenics Plant Building (WBS 121.06.03)
Breakout Session
Steve Dixon
PIP-II IPR
4-6 December 2018

## Slide 2: Charge Questions Addressed

## Slide 3: Outline
Scope/Deliverables
Requirements
Interfaces
Preliminary Design, Maturity
Technical Progress to Date
ESH&Q
Risks and Mitigations
Summary

## Slide 4: About Me:
PIP-II Level 2 Manager for Conventional Facilities
Relevant Experience
  Licensed Architect;
  Project Management Professional (PMP);
  LEED Accredited Professional;
  26+ years at Fermilab;
  NOvA Project L2 Manager for Site and Buildings;
    2014 CD-4
    2015 U.S. DOE Secretary’s Award for Excellence
  General Plant Project Manager for 15+ years
    Short Baseline Neutrino (SBN) Near Detector Building;
    Short Baseline Neutrino (SBN) Far Detector Building;
    Experimental Operations Center;

## Slide 5: Scope and Deliverables [1]
WBS 121.06.03.01 – Project Management and Coordination
  Project management for the Cryoplant Building including the oversight and coordination of the technical effort, project planning and scheduling, cost estimating, risk and contingency analysis, and reporting. Includes travel costs for management, technical coordination, and vendor visits.
WBS 121.06.03.02 – Detailed and Final Design
  Services needed for the design of the Cryo Plant Building work scope. It describes the labor resources, materials and services, including architectural/engineering services, necessary for planning, oversight and engineering and design.
WBS 121.06.03.03 – Construction on Site
  Procurement and management for all contracted labor, materials, tools, equipment, and services needed for the construction of the Cryo Plant Building work scope. It describes the labor resources, materials and services necessary organization, planning, oversight and engineering, design, inspection and administration (EDIA) of the construction work on the Fermilab site.
Charge #2
[1] Definitions from WBS Dictionary, PIP-II-doc-599

## Slide 6: WBS L3 System Requirements
Charge #2

## Slide 7: Functional Requirements Specification [1]
Charge #2
[1] See TeamCenter Document ED0006718

## Slide 8: Technical Requirements Specification [1]
Charge #2
[1] See TeamCenter Document ED0006719

## Slide 9: Interfaces
Project Interfaces (Managed through PIP-II processes) [1]
  ED0007698 – Interface Control Document
  WBS 121.02 - SRF & Cryo Systems
    WBS 121.02.05 – Cryo Plant (B. Hansen)
    WBS 121.02.06 – Cryogenic Distribution (A. Dalesandro)
Fermilab Interfaces
  Infrastructure Connections (Managed through FESS processes)
  General Plant Projects (Managed through FESS processes)
International Interface (Managed through WBS 121.02)
  Cryogenic plant is Indian partner deliverable
Charge #2
FESS is the Facilities Engineering Services Section
[1] See PIP-II Systems Engineering Management Plan at PIP-II-doc-1539

## Slide 10: Preliminary Design and Design Maturity
Technical Requirements Phase
  Started in May 2018;
  Completed in September 2018;
Detailed/Final Design
  Goal is to start in December 2018
  Complete in May 2019
  Dependent on architect/engineer award;
Goal: 90% Design Maturity by CD-3A Review
Charge #2

## Slide 11: Schedule Detail
Charge #2
From 18OCT18 Integrated Project Team Meeting
Cryo Plant Building and Site Preparation Design Complete
Schedule and Cost Known

## Slide 12: Progress to Date
Developed preliminary shielding strategy with 121.03 (Accelerator Systems)
Requirement and Specification Review [1]
Industrial Cooling Water Quality Testing Complete [2]
Technical Requirements Phase (40% Design) [3]
Charge #1
From TeamCenter Document ED0008373
[1] See TeamCenter ED0008588
[2] See PIP-II-doc-155
[3] See TeamCenter ED0008373

## Slide 13: Progress to Date
Charge #1
From TeamCenter Document ED0008373

## Slide 14: Environment Safety and Health (ES&H)
Design Phase Incorporates:
  Architect/Engineer selection included ES&H considerations;
  Life Safety Assessment requirements; [1]
  Safety By Design process;
  Input from Tritium Task Force;
  Input from Hazard Analysis Report (HAR) hazards [2]
Charge #6
[1] Life Safety Analysis can be found at PIP-II-doc-120
[2] Hazard Analysis Report can be found at PIP-II-doc-140

## Slide 15: Quality Management
Charge #6
Process to date include:
  Requirement and Specification Review (PIP-II process)
  Comment and Compliance Review (FESS/E process)
  QAQC Process Report (A/E process)

## Slide 16: Risk Management
Cryogenic Plant Building Related Risks
RT-121-06-001 – Subproject Requirement Change
RT-121-06-003 – Construction Bids Exceed Estimates
RT-121-06-005 – Cryoplant Design Requirements
RT-121-06-008 – Cryoplant Cooling Water
RT-121-06-039 – Cryogenic Plant Building BO Delayed
Charge #2,7

## Slide 17: Steps to CD-3A (Cryogenics Plant Building)
Complete the Construction Package
  Design complete;
  Specifications complete;
  Updated cost/schedule estimate
  Anticipated for May 2019
Favorable EA FONSI
  Anticipated in December 2018;
Procurement Process
  Advanced Acquisition Plan (start in January 2019)
  Subcontractor Outreach Program
EA is Environmental Assessment
FONSI is Finding Of No Significant Impact

## Slide 18: Summary
Cryogenics Plant Building is a CD-3A request;
Good progress on the design since CD-1;
Design of the Cryogenic Plant Building is based on the requirements from two potential cryogenics plant vendors;
On track for a CD-3A Review in Q3 FY19;
On track to achieving the goal of having the building and supporting infrastructure ready in advance of cryogenic equipment arrival;
Thanks for your time.

## Slide 19: END