## Slide 1
121.03.09 – Beam Instrumentation
Instrumentation
L3 Manager – Vic Scarpine & Brian Drendel
PIP-II IPR
4-6 December 2018

## Slide 2: Outline
Scope/Deliverables
Requirements
Interfaces
Preliminary Design, Maturity
Technical Progress to Date
ESH&Q
Risks and Mitigations
Summary

## Slide 3: About Me:
Vic Scarpine – L3 Manager for PIP-II beam instrumentation
  Accelerator Division Application Physicist III in FNAL AD Instrumentation Department
  15 years experience in development and operation of beam instrumentation
  Relevant linac experience
    Development of HINS front-end beam instrumentation
    Development of Fermilab RFQ commissioning beam instrumentation
    Development of PIP2IT beam instrumentation

## Slide 4: About Me:
Brian Drendel – CAM for PIP-II beam instrumentation
  Engineering Physicist
  27 years of operational accelerator experience with an emphasis on controls and instrumentation
  Seven years of Level 3 and CAM project management experience
    FNAL AD/Muon Department
    L3 AIP Controls and Instrumentation (completed)
    L3 and CAM g-2 Controls and Instrumentation (completed)
    L3 and CAM Mu2e Controls and Instrumentation (currently in implementation phase)
    CAM PIP2 Controls

## Slide 5: Scope and Deliverables
Scope
  Design, procurement, fabrication, and testing of beam instrumentation systems for the commissioning and operation of the PIP-II accelerator.
    Includes warm front-end, SC linac and linac-to-booster transfer line
    Includes PIP2IT
  PIP-II beam instrumentation WBS is divided into:
    Beam Position Monitor System
    Beam Current Monitor System
    Beam Loss Monitor System
    Beam Profile Monitor Systems
      Transverse Profile Monitors
      Transverse Emittance Monitors
  There are no in-kind contributions for PIP-II or PIP2IT beam instrumentation
Charge #2

## Slide 6: WBS L3 System Requirements
Beam instrumentation functional requirements defined in FRS ED0008303
  Beam instrumentation systems shall be capable of measurements of short commissioning beam pulses as well as nominal length operational beam pulses, for pulses repetition rates up to 20 Hz.
Beam position monitor (BPM) system shall:
  Measure the average transverse position, phase and intensity via warm and cold BPMs for each beam pulse
  Measure the beam energy in the linac-to-booster transfer line dispersion region for each beam pulse
    FRS ED0008303 – Beam Instrumentation
    FRS ED0003675 – MEBT BPM
Charge #2

## Slide 7: WBS L3 System Requirements
Beam loss monitor (BLM) system shall:
  Detect beam loss through the measure of ionizing particles and neutrons
  Measure relative beam loss for each beam pulse in the linac and transport line.
  Provide relative beam loss information for each beam pulse to the Machine Protection System.
    FRS ED0008303 – Beam Instrumentation
Charge #2

## Slide 8: WBS L3 System Requirements
Beam current monitor (BCM) system shall:
  Measure the average current and intensity of the beam transported through the warm front-end, SC Linac, and linac-to-booster transfer beamline for each beam pulse.
  Provide differential beam current measurements to the Machine Protection System for each beam pulse.
  Measure the MEBT chopper bunch-by-bunch extinction efficiency
    FRS ED0008303 – Beam Instrumentation
Charge #2

## Slide 9: WBS L3 System Requirements
Beam transverse profile monitor (BTP) systems shall:
  Measure average beam transverse profiles in the warm front-end, SC linac and linac-to-booster transfer line when requested
  Be non-invasive and meet particle-free requirements in the SC linac
    FRS ED0008303 – Beam Instrumentation
    FRS ED0004340 – MEBT wire scanner
Beam transverse emittance monitor (BTE) systems shall:
  Measure the beam transverse emittance in the warm front-end, SC linac and linac-to-booster transfer line when requested
    FRS ED0008303 – Beam Instrumentation
    FRS ED0004080 – MEBT emittance scanner
Charge #2

## Slide 10: Interfaces
Important interfaces for beam instrumentation:
  Mechanical installation and alignment of detectors on beamline
  Timing and controls from Controls system
  Clock signals from LLRF
  Beam diagnostic information to Controls
  Beam information to machine protection (Controls)
  Infrastructure:
    Power, rack space, cables, etc
    Laser hut and laser-light transport through linac
Interfaces identified and being managed though interface controls documents
  Teamcenter document ED0007694
Charge #2

## Slide 11: Preliminary Design and Design Maturity
Beam Current Measurements
Three types of Beam Current Monitor (BCM) pickups
  Toroids or ACCTs
  DC (Direct Current) Current Transformer (DCCT)
  Wall current monitors
Based on systems currently operating at Fermilab
  Raw signals are conditioned in a “transition board,” digitized and processed by a digitizer, and interfaces to the control system through a front-end
  All three types of pickups have been installed and operated at PIP2IT
  Resources will be applied to the design, programming, and testing of alternatives to the current electronics front end standard
    Tie to industry standards to reduce customization
    Use common framework for high-performance systems
Very Mature
Charge #2

## Slide 12: Progress to date – ACCT at PIP2IT
Full scale: ±12 mA
BW: < 3 Hz to 1 MHz
Droop: < 2% per ms
Risetime: 350 ns (10-90%)
Noise at 10 mA: ~1.5 mA rms
Sensor saturation: 2 mT
Magnetic shielding
In-flange design
Installed in PIP2IT beamline
ACCT
Installed
in MEBT
15 ms
Toroid
Charge #1

## Slide 13: Progress to date – MEBT Chopper Extinction Measurement
Use downstream Resistive Wall Current Monitors (RWCM)
Extinction
  Can average over many bunches or take a single shot measurement
  Measurement BW < 1 Hz
  Fits to bunch shape
  Measure impact on adjacent bunches
  Installed in PIP2IT MEBT
Charge #1
MEBT Measurements

## Slide 14: Preliminary Design and Design Maturity
Beam Position Monitors
4-button BPM vacuum pickup
  Separate designs for warm and cold BPMs
Electronics
  Analog transition boards
  FPGA-controlled digitizers for signal analysis
Software
  FPGA firmware
  Front-end controller
  Controls interface
MEBT BPMs installed and operational at PIP2IT
Beam Loss Monitors
Pickups
  Ionization beam loss monitors
  Fast PMT-based beam loss monitors
  Neutron detectors
Electronics
  Analog transition boards
  FPGA-controlled digitizers for signal analysis
Software
  FPGA firmware
  Front-end controller
  Controls interface
Very Mature
Very Mature
Charge #2

## Slide 15: Progress to date – MEBT BPM Development at PIP2IT
Warm 4-buttom BPMs imbedded in quad doublets
Narrow-band DAQ with FPGA-based electronics
12 channel, 14 bit, 125 MHz boards
Analog filter and amplifier boards
Status:
BPMs operational
  Average position, phase, intensity per beam pulse
  Position resolution ~10 mm
  Phase resolution ~0.2 deg
Time-of-flight BPM installed and tested
  BPM on movable stage
  Energy resolution ~0.3%
Charge #1

## Slide 16: Preliminary Design and Design Maturity
Transverse beam profiles
Wire-based transverse profile monitor – Very Mature
  Two-wire secondary emission monitors
  Linear motion actuators and FPGA-based signal processing electronics
  Installed into warm MEBT and transfer beamline
Laser-based transverse beam profile monitor – Under Development
  Installed in cold section of SC Linac
  Single laser source located in a laser room, outside of the beam enclosure and near the ion source.
  Enclosed line transports laser light from the laser room via fiber optics or free-space to each laser transverse profile monitor locations
  Laser monitor will include a light-tight optics box with required optics and motion to provide the required laser scanning across the beam, as well as electron collection to measure the profile
Charge #2

## Slide 17: Progress to date – Prototype Wire Scanner at PIP2IT
Installed in MEBT
Beam Current
Horz
Vert
Charge #1

## Slide 18: Progress to date – Prototype Laser Wire Profiler
Components all coming together
  Laser and optics testing underway in A0 laser lab
    Testing and characterizing laserwire
  PIP2IT vacuum chamber constructed
  PIP2IT Laser hut nearly complete
    Need to install safety interlock system
Laser System under test in A0 laser lab
Laserwire
Laser Hut
PIP2IT Door
Charge #1

## Slide 19: Preliminary Design and Design Maturity
Transverse emittance monitor systems
  LEBT and MEBT
    Allison-style emittance scanners
    PC-based data acquisition and controls
    Very mature
  Transfer line
    laser-based emittance scanner
      Similar to existing system at Spallation Neutron Source (SNS)
    Under development
Charge #1,2
MEBT Emittance

## Slide 20: ESH&Q
Safety is an essential element in all work we do
  Project Integrated ES&H Management Plan (docdb #141)
  Laboratory and DOE standards and practices
    Fermi Radiological Control Manual
    Fermi ES&H Manual
Quality Assurance and Control
  Project Quality Assurance Plan (docdb #142)
Primary issues for beam instrumentation are electrical and laser safety
Electrical hazards associated with these systems are covered under the codes below:
  National Electrical Code, NFPA 70
  OSHA 29 CFR, Part 1910, Subpart S, Electrical
  Fermilab ESH&Q Manual, Fermilab Electrical Safety Program
Lasers present a unique hazard for PIP-II profile instrumentation. These systems are covered under safety documents:
  Fermilab FESHM 4260 – Lasers
  ANSI Z136.1 – Safe Use of Lasers
  Inclusion of lab laser safety officer in design and development
Charge #6

## Slide 21: Risk Management
Medium-level and low-level risks for beam instrumentation in project risk registry:
RT-121-03-008 – Choice of laser profiling technology impacts infrastructure design – medium risk
  Low-power laser system VS high-power laser system
Beam instrumentation integration into MPS – medium risks
  RT-121-03-010 – Adequate real-time bandwidth between instrumentation and MPS
    Does communication between MPS and instrumentation meet performance requirements?
  RT-121-03-009 – Adequate instrumentation performance for MPS
    Does beam instruments supplying MPS information have adequate performance?
RT-121-03-016 – Adequate linac physical space for beam instrumentation – low risk
Charge #2,7

## Slide 22: Risk Mitigation: Choice of laser profiling technology for transverse beam profiles
Two options for laser profiling: (1) low-power lasers or (2) high-power lasers
Low-power laser option is preferred but needs beam measurements as proof of operation
High-power laser option has been demonstrated at SNS but is more complicated and has risk of damage to optical vacuum windows from laser power
Plan to test low-power option with beam at PIP2IT in MEBT and HEBT – this is critical to laser profiling system choice
If unsuccessful then fall back to high-power option for PIP-II
Laser profiling PIP-II infrastructure design allows for possibility of either laser option as final choice
Charge #2,7

## Slide 23: Risk Mitigation: Beam instrumentation integration into MPS
RT-121-03-010 – Adequate real-time bandwidth between instrumentation and MPS
  Mitigate by architecture of instrumentation and MPS systems
  Architecture drives design of instrumentation electronics and software development requirements
  Test system performance on bench and PIP2IT
RT-121-03-009 – Adequate instrumentation performance for MPS
  Mitigate by choice of instrumentation architecture
    Pickups and electronics
  System noise presents biggest unknown
    Using PIP2IT to understand noise issues
Charge #2,7

## Slide 24: Summary
Instrumentation development for PIP-II proceeding
Instrumentation designs based on well tested technology
  Many systems evolved for other FNAL beam instrumentation
  New systems (e.g. laser profiling) leveraging experience from other laboratories
Path to completing preliminary design is understood
Many instrumentation systems being tested at PIP2IT
  Testing at PIP2IT invaluable to instrumentation development
  PIP2IT is essential to reducing project risk

## Slide 25: END