## Slide 1
Peter Wilson – SBN Program Coordinator
SBN Oversight Board
30 November 2018
SBN Program Status

## Slide 2: Outline
ICARUS technical progress
SBND technical progress
December Director’s review

## Slide 3: Far Detector - ICARUS
Exterior Filters
Cryogenic Dewars
Cold Vessels (TPCs and PMTs inside)
Proximity Cryogenics
Removable Wall Panel
Side CRT
Top CRT and Overburden
(not shown)
Not shown in alcoves (mezzanine and pit):
DAQ racks
Controls racks
Bottom CRT
TPC Electronics
(not shown)
Two 33 ton cranes

## Slide 4: ICARUS Installation Progress
Post rigging installation on schedule:
  Vacuum test completed
  Top cold shield installed and complete system pressure tested
  Warm vessel roof installed, welded and leak checked
  Installation of steel structures completed:
    CRT top steel, cryogenic platform and stairs
    Guardrails
  Installation of feedthrough crosses is in progress
  Installation of feedthrough flanges to start next week
  Proximity cryogenics components in transit from CERN
    Arrived in New York this week, delivery to FNAL early December
  Demaco (CERN contractor) scheduled to start proximity cryogenics installation on Jan 28
TPC 1 Complete
Vessel 2 Ready
Chimney Installation
(collaboration)
Cold shield pressure test
Warm vessel roof installation

## Slide 5: ICARUS Installation Progress
Post rigging installation on schedule:
  Vacuum test completed
  Top cold shield installed and complete system pressure tested
  Warm vessel roof installed, welded and leak checked
  Installation of steel structures completed:
    CRT top steel, cryogenic platform and stairs
    Guardrails
  Installation of feedthrough crosses is in progress
  Installation of feedthrough flanges to start next week
  Proximity cryogenics components in transit from CERN
    Arrived in New York this week, delivery to FNAL early December
  Demaco (CERN contractor) scheduled to start proximity cryogenics installation on Jan 28
TPC 1 Complete
Vessel 2 Ready
Top CRT structure
Access stairs
Cryogenics platform

## Slide 6: ICARUS Installation Progress
Post rigging installation on schedule:
  Vacuum test completed
  Top cold shield installed and complete system pressure tested
  Warm vessel roof installed, welded and leak checked
  Installation of steel structures completed:
    CRT top steel, cryogenic platform and stairs
    Guardrails
  Installation of feedthrough crosses is in progress
  Installation of feedthrough flanges to start next week
  Proximity cryogenics components (far and near detector) in transit from CERN
    Six of ten containers at port in New York, delivery to FNAL in early December
  Demaco (CERN contractor) scheduled to start proximity cryogenics installation on Jan 28
TPC 1 Complete
Vessel 2 Ready
Installing feedthrough crosses
Attaching decoupling cards to flanges

## Slide 7: ICARUS Progress
TPC electronics production in final phase (INFN)
  On track to complete delivery to FNAL by May
Cosmic Ray Tagger (CRT)
  Bottom modules installed in 2017 (Double Chooz spares courtesy of U. Chicago)
  Top module production has at Frascati (CERN/INFN)
    First modules complete in January 2019
    Complete assembly in summer 2019
  Sides re-use MINOS far detector modules (FNAL/US), completing design of SiPM board
    Review of final prototype in January 2019
    SiPMs ordered
  Common electronics for top, sides and SBND – designed by U. Bern, commercialized by CAEN
  DAQ/event builder code
DAQ servers ordered (FNAL/INFN)
Prototype SiPM board and cable shroud for MINOS Modules
PreProduction Top CRT Module
@ Bologna

## Slide 8: ICARUS Milestones to I-1 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Vessels rigged into building | P. Wilson | 16-Aug-2018 | 16-Aug-2018 |  | 16-Aug-2018
Manholes welded and vacuum test successful | C. Montanari | 10-Oct-2018 | 03-Oct-2018 |  | 11-Oct-2018
Warm Vessel roof complete | C. James | 15-Nov-2018 | 9-Nov-2018 |  | 31-Oct-2018
Cryo Platform complete | C. James | 15-Dec-2018 | 12-Oct-2018 |  | 04-Oct-2018
Proximity cryogenics installation begins | B. Norris | 15-Jan-2019 | 30-Jan-2019 |  | 
DBB & flanges installation complete and tested | A. Fava | 15-Feb-2019 | 21-Feb-2019 |  | 
Cold proximity cryogenics installation complete | B. Norris | 15-Apr-2019 | 23-Apr-2019 |  | 
1st T300 readout installation complete | A. Fava | 15-Mar-2019 | 11-Mar-2019 |  | 
All detector readout installed | A. Fava | 1-May-2019 | 19-Apr-2019 |  | 
Begin vacuum pumping | C. Montanari | 15-Jul-2019 | 15-May-2019 |  | 
Cryogenic operation approved | B. Norris | 15-Jul-2019 | 28-Jun-2019 |  | 
I1: ICARUS detectors ready to fill with LAr | P. Wilson | 30-May-2019 | 28-Jun-2019 |  | 

## Slide 9: Near Detector - SBND
Cryogenic Dewars
TPC
Proximity Cryogenics
Side CRT
Top CRT and Overburden
Readout racks
20 ton crane
Top CRT
Cryostat

## Slide 10: SBND TPC Progress
Joint responsibility of UK, US-NSF, FNAL
UK: Cathode plane, two anode planes, HV feedthrough
US-NSF: field cage, two anode planes, HV feedthrough
FNAL: support integration and assembly
Recent Milestones:
Aug 2018 1st UK and US anode planes completed
Sept 2018 Field cage completed
Oct 2018 1st UK anode delivered to FNAL
Sept 2018 Test of assembly fixture at FNAL
Nov 2018 2nd US anode plane completed
Dec 2018 US anodes delivered to FNAL
Feb 2019 2nd UK anode delivered to FNAL
Assembly facility at Dzero Assembly
building
1st Manchester APA at FNAL in DZero clean tent
Yale – 2nd APA ready to ship

## Slide 11: SBND TPC Electronics Progress
Cold electronics (BNL):
  Design very similar to ProtoDUNE (eg same FE ASIC)
  Use cold qualified commercial off the shelf ADC
Warm backend (Columbia – Nevis)
  Update of MicroBooNE design
Vertical slice test in summer 2018 with LArIAT TPC
  good noise performance
  No major issues with Nevis electronics
  Proximity of HV to cables and electronics caused FE channel failures and data corruption, very different detector configuration than SBND
Addressing lessons from ProtoDUNE
  FE ASIC “ledge effect” – large charge depositions cause a dead period of several hundred microsecs
  Ongoing investigations by ProtoDUNE and at BNL
  Mitigated by modifying layout of FE board to include 1-2GOhm resistor and operation with higher baseline setting
  Continuing study of physics effects
Production Readiness Review – Nov 29
  Recommends proceeding with production
LArIAT TPC w/ SBND electronics
Ledge effect @protoDUNE
amplitude
Time tic

## Slide 12: SBND Photo Detection Progress
120 SBND PMTs are now in the Coherent CAPTAIN-Mills Detector (CCM)
  Fill with LAr ~now
Electronics and DAQ are ready, the HV breakout boxes will be finished soon
ARAPUCA group has made prototypes to be tested in argon at the end of November
ARAPUCA group ready to purchase feedthroughs as soon as bar group makes a final decision about connectors and costs
CCM preparing to test PMTs at LANL
ARAPUCA prototypes

## Slide 13: SBND Cryostat
Outer steel structure + GTT designed membrane cryostat
  Joint responsibility of CERN, FNAL and INFN
SBND will be 3rd generation prototype for DUNE designed by CERN:
  WA105 1x1x3  protoDUNEs  SBND
  Steel structure design updated to match LBNF/DUNE as closely as possible
Status:
  General agreement between CERN-FNAL-INFN on sharing of responsibilities
  Final design of steel structure nearly complete
  Ready to start final design study for membrane cryostat by GTT
SBND Cryostat Model
Cryostat Top Interfaces

## Slide 14: SBND Milestones to S-1 SBND ready to move
Intermediate Milestone | Owner | Baseline Date | Forecast Date (Schedule) |  | Actual Date
First set of APAs shipped to Fermilab | K. Mavrokoridis | 24-Sept 2018 | 28-Dec-2018 |  | 
PO for COTS ADCs placed | H. Chen | 10-Oct-2018 | 30-Nov-2018 |  | 30-Oct-2018
All TPC Components at Fermilab | K. Mavrokoridis | 1-Mar-2019 | 26-Feb-2019 |  | 
Complete atf assembly at DAB | J. Zennamo | 1-May-2019 | 8-Apr-2019 |  | 
50% of motherboards delivered to Fermilab | H. Chen | 15-May-2019 | 15-Apr-2019 |  | 
APAs and CPAs installed in atf | J. Zennamo | 15-Jun-2019 | 23-May-2019 |  | 
Field cage assembly complete | J. Zennamo | 15-Jul-2019 | 2-Jul-2019 |  | 
Cold electronics installed and tested | H. Chen | 23-Aug-2019 | 8-Aug-2019 |  | 
S1: TPC ready to move to SBN ND | A. Schukraft | 30-Aug-2019 | 8-Aug-2019 |  | 

## Slide 15: SBND Milestones to S-2 Ready to Fill
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
GTT Design Study Begins | M. Nessi | 1-Feb-2019 | 1-Jan-2019 |  | 
Delivery of warm box steel | M. Nessi | 15-Jun-2019 | 30-Apr-2019 |  | 
Warm vessel installation complete | M. Nessi | 15-Jul-2019 | 29-May-2019 |  | 
TPC Transport to ND building complete | J. Zennamo | 15-Sept-2019 | 16-Aug-2019 |  | 
Cryostat material arrives at Fermilab | M. Nessi | 1-Oct-2019 | 22-Aug-2019 |  | 
Cryostat top plug is ready to attach to atf | M. Nessi | 1-Nov-2019 | 23-Sept-2019 |  | 
Membrane Cryostat Completed | M. Kim | 1-Mar-2020 | 22-Jan-2020 |  | 
Plug welded to cryostat | M. Kim, J. Zennamo | 15-Apr-2020 | 6-Mar-2020 |  | 
Cryogenic operation approved | M. Geynisman | 1-Jul-2020 | 1-Jun-2020 |  | 
S2: SBND detector is ready to fill with liquid Argon | A. Schukraft | 15-Jul-2020 | 1-Jun-2020 |  | 

## Slide 16: SBN Director’s Review – Dec 2018
A Director’s Review for SBN will be held Dec 17-19 2018
The charge and review format will be similar to the June 2018 review:
  Focus on schedule elements and integrated schedule
  Will include more detail on commissioning plans
  Session on DOE costs
Charge is posted on the indico page for this meeting
Review agenda is being finalized now
Preparation for review
  Schedules for both ICARUS and SBND have been updated in October
    Includes integration of commissioning milestones
  Updated estimate of DOE costs including commissioning costs

## Slide 17: Backup

## Slide 18: ICARUS Milestones to I-2 Detector Filled
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Cold shield cooldown complete | C. Montanari | 7-Aug-2019 | 15-Jul-2019 |  | 
Vessels filled with LAr, ready for HV | M. Geynisman | 30-Sept-2019 | 10-Sept-2019 |  | 
Drift HV operational | F. Garcia | 15-Oct-2019 | 30-Sept-2019 |  | 
PMTs operational | G. Raselli | 30-Oct-2019 | 15-Oct-2019 |  | 
Cryogenics commissioning complete | M. Geynisman | 30-Nov-2019 | 22-Oct-2019 |  | 
Cosmic tracks are observed in the TPC | A. Fava | 30-Nov-2019 | 22-Oct-2019 |  | 
I2: detector is filled with liquid argon and ready for physics commissioning (LAr purity adequate for physics has been achieved) | P. Wilson | 30-Nov-2019 | 22-Oct-2019 |  | 

## Slide 19: ICARUS Milestones to I-3a ready for physics data – CRT operational
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Top CRT panels delivered to Fermilab | U. Kose | 30-Sept-2019 | 31-Jul-2019 |  | 
Slow controls operational for all detector systems | K. Biery | 31-Oct-2019 | 30-Sept-2019 |  | 
DAQ operational with >5Hz output | K. Biery | 31-Oct-2019 | 30-Sept-2019 |  | 
Detector system timing synchronized with beam | K. Biery | 30-Nov-2019 | 31-Oct-2019 |  | 
Trigger system operational | A. Guglielmi | 31-Dec-2019 | 30-Nov-2019 |  | 
Top CRT panels are installed and ORC’ed | U. Kose/A. Fava | 31-Jan-2020 | 5-Dec-2019 |  | 
I3a: ICARUS detectors are ready for physics data – CRT is operational | P. Wilson | 31-Jan-2020 | 5-Dec-2019 |  | 

## Slide 20: ICARUS Milestones to I-3a ready for physics data – shielding in place
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Shielding blocks in place | C. James | 28-Feb-2020 | 6-Feb-2020 |  | 
I3b: ICARUS detectors are ready for physics data – Shielding in place | P. Wilson | 28-Feb-2020 | 6-Feb-2020 |  | 

## Slide 21: SBND Milestones to S3 Detector Filled
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Laser system installation complete | I. Kreslo | 1-Oct-2020 | 31-Mar-2020 |  | 
Detector checkout at 130-150 K complete | M. Stancari | 15-Nov-2020 | 16-Oct-2020 |  | 
Vessels filled with LAr, ready for HV | M. Geynisman | 21-Dec-2020 | 30-Oct-2020 |  | 
Drift HV operational | A. Schukraft | 31-Jan-2021 | 1-Dec-2020 |  | 
PMTs operational | R. Van de Water | 31-Jan-2021 | 20-Nov-2020 |  | 
Cryogenics commissioning complete | M. Geynisman | 28-Feb-2021 | 15-Dec-2020 |  | 
Cosmic tracks are observed in the TPC | M. Stancari | 28-Feb-2021 | 15-Dec-2020 |  | 
S3: SBND detector is filled with liquid argon and ready for physics commissioning (LAr purity adequate for physics has been achieved) | A. Schukraft/M. Stancari | 28-Feb-2021 | 15-Dec-2020 |  | 

## Slide 22: SBND Milestones to S-4a ready for physics data – CRT operational
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Top CRT panels delivered to Fermilab | I. Kreslo | 1-Jul-2019 | 1-Apr-2019 |  | 
Slow controls operational for all detector systems | S. Gallopini | 15-Sept-2020 | 17-Jul-2020 |  | 
DAQ operational with >5Hz output | W. Badgett | 1-Nov-2020 | 2-Oct-2020 |  | 
Detector system timing synchronized with beam | W. Badgett | 15-Nov-2020 | 11-Sept-2020 |  | 
Trigger system operational | W. Badgett | 15-Jan-2021 | 15-Dec-2020 |  | 
Top CRT panels are installed and ORC’ed | I. Kreslo | 31-Mar-2021 | 11-Jan-2021 |  | 
S4a: SBND detectors are ready for physics data – CRT is operational | M. Stancari | 31-Mar-2021 | 19-Jan-2021 |  | 

## Slide 23: SBND Milestones to S-4b ready for physics data – shielding in place
Intermediate Milestone | Owner | Baseline Date | Forecast Date |  | Actual Date
Shielding blocks in place | C. James | 21-Apr-2021 | 8-Feb-2021 |  | 
CRT system complete and fully commissioned | I. Kreslo | 30-Apr-2021 | 15-Feb-2021 |  | 
S4b: SBND detectors are ready for physics data – Shielding | M. Stancari | 30-Apr-2021 | 15-Feb-2021 |  |