## Slide 1: Long Baseline Neutrino Committee December 2018 CERN, Geneva Switzerland
Introduction
Montgomery
December 7, 2018

## Slide 2: Contents
LBNC Scope and Process
Charge to December 2018 LBNC
Planning for TDR Reviews

## Slide 3: Scope of LBNC
LBNC is used by the Director for oversight of the international experiment DUNE.
Oversight of LBNF is limited to those aspects of DUNE which feed directly into DUNE activities. (Below was discussed between LBNC and LBNF leadership but not yet been ratified by Director.)
  Cryostat and Cryogenic Systems
  Beamline Implementation and Near Site Implementation
  Management of LBNF-DUNE Interfaces
  Monitoring of Risks to International Milestones
  Regular Plenary Status Report, (subgroup as needed.)

## Slide 4: LBNC/NCG Process
Approval of Technical Proposal (IDR)
  Done
Approval of Baseline
  Review of TDR by LBNC (initial cost estimates available to LBNC)
    Individual reviews for each component.
    It is recognized that separate components of DUNE will achieve the various stages of readiness at different times.
  Review of Cost & Schedule by NCG
    Member from relevant LBNC TDR Review team
  Recommendation(s) to Director and RRB
Approval for Construction
  Appropriate Readiness Reviews
Progress Review
  Includes Monthly Report

## Slide 5: Charge for December 2018 LBNC
The LBNC will hear about the progress in a number of areas including the general progress of each of DUNE, LBNF, and ProtoDUNE. There will be in depth presentations covering the development of the Dual Phase option, including a look forward to 2019 with ProtoDUNE DP, and preparations for a TDR. We will also hear about TDR and CDR preparations in a few key areas.
The LBNC will prepare a written report, which will include descriptions of the status of each of these items. Inter alia, this report will inform a presentation of the overall preparations of DUNE, which may be requested for the DOE LBNF-DUNE IPR in early January, 2019.
An abbreviated verbal closeout will be presented on Sunday afternoon.
Our goal will be to leave CERN with an advanced draft of the full report in hand.

## Slide 6: Approach
In order to facilitate achieving this, we have made tentative assignments for the attending LBNC members.
Note that both Angela Fava, our Scientific Secretary and David MacFarlane, our outgoing chair are expected to be active participants.
The assignments are shown below;
  the name in Bold Face is requested to take the lead in writing.
  We are looking for approximately 0.5 – 0.75 pages per item except for the Dual Phase which has several sub sections, so should be longer.
  We will discuss the expectations in the Executive session at the beginning of the meeting, but if anyone feels that the task is not acceptable, please contact mont@jlab.org.

## Slide 7: Assignments
DUNE Overall Status 50 mins (35+15) Stefan Soldner Rembold -- Exec Summary: Montgomery
LBNF Status 45 mins (30+10) Chris Mossey
LBNF Status: Laxdal, MacFarlane
ProtoDUNE-SP Report (and lessons-learned) 45 min (35+10) Gina Rameika
PD SP Status: Charlton, Fava, Montgomery
Dual-Phase
  Results from the 1x1x3 m^3 Demonstrator 30 mins (20+10) Sebastien Murphy
  LEM Production & Testing 30 mins (20+10) Edoardo Mazzucato
  CRP Assembly & Cold-Box Testing 30 mins (20+10) Dominique Duchesneau
  ProtoDUNE-DP Installation 30 mins (20+10) Filippo Resnati
  DUNE-DP IDR & TDR Status 30 mins (20+10) Dario Autiero
DUAL Phase Status: Proudfoot, Fuerst, Galbiati, Mondal

## Slide 8: Assignments
TDR/CDR Preparation Status
  Overall View/Plan/Status 35 mins (25+10) Tim Bolton (Remote)
TDR Overall Status: Charlton, Montgomery
  Physics TDR Status/Preview 35 mins (25+10) Jon Urheim
Physics TDR Status: Heinemann, Huber
  Computing Organization Status 35 mins (25+10) Heidi Schellman
Computing Plans: Boehnlein, Heinemann
  APA TDR Status/Preview 35 mins (25+10) Christos Touramanis
APA TDR Status: Monroe, MacFarlane,
Near Detector CDR Status/Preview 35 mins (25+10) Alan Bross
Near Detector Status Mondal, Huber, Fava

## Slide 9: Relevant Dates 2019
DOE LBNF/DUNE IPR January 7-9
Fermilab PAC January 17-19
DUNE RRB March 14, 15
LBNC April 1-3
Fermilab PAC ????
LBNC July 31-August 2
DUNE RRB September 18-20

## Slide 10: DUNE TDR Plan 11/17/2018
Consortium | 1st draft | 2nd draft | LBNC
SP-HV | November 2, 2018 | December 7, 2018 | December 21, 2018
SP-APA | November 2, 2018 | December 7, 2018 | December 21, 2018
SP-DAQ | November 2, 2018 | December 7, 2018 | December 21, 2018
SP-PDS | November 30, 2018 | January 11, 2019 | January 25, 2019
SP-CISC | November 30, 2018 | January 11, 2019 | January 25, 2019
TC | November 30, 2018 | January 11, 2019 | January 25, 2019
PHYSICS | November 30, 2018 | January 11, 2019 | January 25, 2019
SP-CE | December 14, 2018 | February 8, 2019 | February 22, 2019
DP-Electronics | December 14, 2018 | February 8, 2019 | February 22, 2019
Computing Exec Summary | December 14, 2018 | February 8, 2019 | February 22, 2019
DP-HV | February 1, 2019 | March 1, 2019 | March 29, 2019
SP-IIC | February 1, 2019 | March 1, 2019 | March 29, 2019
DP-PDS | March 1, 2019 | April 5, 2019 | April 26, 2019
SP-Calibration | March 1, 2019 | April 5, 2019 | April 26, 2019
SP-Exec Summary | March 1, 2019 | April 5, 2019 | April 26, 2019
ND-Exec Summary | March 1, 2019 | April 5, 2019 | April 26, 2019
DP-IIC | April 5, 2019 | May 10, 2019 | May 31, 2019
DP-DAQ | April 5, 2019 | May 10, 2019 | May 31, 2019
DP-CISC | April 5, 2019 | May 10, 2019 | May 31, 2019
DP-Calibration | May 10, 2019 | June 7, 2019 | June 28, 2019
DP-CRP | May 10, 2019 | June 7, 2019 | June 28, 2019
DP-Exec Summary | May 10, 2019 | June 7, 2019 | June 28, 2019
Overall Exec Summary | May 10, 2019 | June 7, 2019 | June 28, 2019
TDR Final |  |  | July 26, 2019

## Slide 11: Tentative DUNE TDR Review Plan
These dates represent possible primary face-to-face review dates
were discussed between DUNE Spokes, TC, and LBNC principals
(Angela, David & Mont)
and are to be further discussed in December LBNC Meeting
Physics February
TC February
SP-1 Late February
Computing March
ND April
SP-2 April depends on adjusting DUNE schedule
DP-1 May
DP-2 June depends on adjusting DUNE schedule
Especially the DP would be very challenging for DUNE

## Slide 12: TDR Review Teams
Team 1 Executive Summary ~5 members
Team 2 Physics ~4 members
Team 3 Single Phase Far Detector ~ 8 members
Team 4 Dual Phase Far Detector ~ 8 members
Team 5 Technical Coordination ~ 5 members
Team 6 Computing ~ 4 members
Team 7 Near Detector ~ 6 members
We might concatenate some, Montgomery would try to attend several
We have discussed tentative team line-ups with Director